## Multi-Process Timeline
Bonneville Power Administration - Provider of Choice - Multi-Process Timeline
| Last Updated: | 2024-12-09 | [5 empty] | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-24 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31
| Purpose: This timeline is focused on Provider of Choice contract development, implementation, and closely related processes. It is provided is for informational purposes only. It does not reflect all BPA public processes or details. Details and dates are subject to change. See individual BPA public process websites and documentation for historical and/or the most up-to-date information. For Provider of Choice inquiries, please email post2028@bpa.gov. | [6 empty] | F Y 2 0 2 5 | [11 empty] | F Y 2 0 2 6 | [11 empty] | F Y 2 0 2 7 | [11 empty] | F Y 2 0 2 8 | [11 empty] | F Y 2 0 2 9 | [11 empty] | F Y 2 0 3 0 | [11 empty] | F Y 2 0 3 1 | [11 empty] | F Y 2 0 3 2
[8 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
[8 empty] | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2031 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032 | 2032
Order | Process | Process Sub-Category | Description | Start Date | No Later Than Date | Frequency/ Detail | Updates From Last Version | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01
1 | Provider of Choice | Contract Development | Draft Contract templates release |  | 2025-03-12 | One-Time |  | X |  | X |  |  | X
2 | Provider of Choice | Contract Development | Public Comment Period (4 weeks): All draft contract templates | 2025-03-12 | 2025-04-09 | One-Time | [6 empty] | X | X
3 | Provider of Choice | Contract Development | Contract workshops | 2024-04-10 | 2025-05-30 | One-Time |  | X | X | X | X | X |  |  | X
4 | Provider of Choice | Contract Development | All final contract templates released: Mid-June |  | 2025-06-17 | One-Time | [9 empty] | X
5 | Provider of Choice | Contract Offer, ROD, Execution | Customer request for offer process (includes product choice) | 2025-04-09 | 2025-06-01 | One-Time | [7 empty] | X | X | X
6 | Provider of Choice | Contract Offer, ROD, Execution | Contract ROD release |  | 2025-08-28 | One-Time | [11 empty] | X
7 | Provider of Choice | Contract Offer, ROD, Execution | BPA internal processes to draft contract offers (Mid-June to Sept.) | 2025-06-17 | 2025-09-30 | One-Time | [9 empty] | X | X | X | X
8 | Provider of Choice | Contract Offer, ROD, Execution | Contract offers sent to customers | 2025-08-28 | 2025-09-30 | One-Time | [12 empty] | X
9 | Provider of Choice | Contract Offer, ROD, Execution | Customers sign contracts and send to BPA |  | 2025-12-05 | One-Time | [15 empty] | X
10 | Provider of Choice | Contract Offer, ROD, Execution | All contracts executed (Dec. 31, 2025) |  | 2025-12-31 | One-Time | [15 empty] | X
| Provider of Choice | NR Block Policy | NR Block Policy | 2025-03-01 | 2025-08-28 | One-Time | New process | [5 empty] | Draft | Comment Period |  |  |  | Final
11 | Provider of Choice | CHWM Implementation Policy | CHWM Implementation Policy: Comment Period, Drafts and Final Release | 2024-10-22 | 2025-08-28 | One-Time |  | Draft | Comment Period |  |  |  | Draft Final |  |  |  |  | Final
12 | Provider of Choice | Power Delivery | Start of power delivery under POC contracts |  | 2028-10-01 | Start; ongoing | [49 empty] | X
13 | PRDM-29 | Other Processes | Proposed Procedural Schedule | 2024-11-13 | 2025-05-21 | One-Time |  |  | X | X | X | X | X | X | X
14 | BP Rate Cases | Other Processes | BP-26 Proposed Procedural Schedule (and ongoing rate cases) | 2024-11-13 | 2025-07-24 | Rate period |  |  | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | BP-26 | [27 empty] | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | BP-29 | [15 empty] | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | BP-31 | [15 empty] | BP-33 | BP-33 | BP-33 | BP-33 | BP-33 | BP-33 | BP-33 | BP-33 | BP-33
16 | Day-Ahead Market | Other Processes | Release Draft Day Ahead Market Policy |  | March 2025 | One-Time | [6 empty] | X
15 | Energy Conservation Agreement | Other Agreements | ECA Development: Public Process (Winter 2026 - Spring 2028) | 2026-01-01 08:00 | 2028-07-01 17:00 | One-Time | [16 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
24 | DSI Agreement | Other Agreements | DSI Agreement: Scope, plan, offer, execute | TBD | TBD | Timeline TBD
25 | PNGC Preservation Agreements | Other Agreements | PNGC Preservation Agreements | TBD | TBD | Timeline TBD
26 | 5b/9c Net Req'mts Policy | Other Processes | Net Reqmts Policy: 5b/9c Development, comment period & ROD | 2026-09-01 | 2027-03-30 | One time; Est'd timing; subject to change | [24 empty] | X | X | X | X | X | X | X
27 | Environmental Attribute Accounting Process | Other Processes | Environmental Attribute Accounting Process; after Final ROD of BP-29 7i; then every rate period thereafter. | 2028-08-01 | 2028-09-30 | Rate period | [47 empty] | X | X | [22 empty] | X | X | [22 empty] | X | X
29 | Residential Exchange | Other Processes | Sub-Phase 3: REP Settlement Evaluation Process and Decision (7i) | 2024-09-01 | 2025-03-01 | One-Time |  | X | X | X | X | X | X
30 | Residential Exchange | Other Processes | Phase 2: Traditional REP Preparation Phase | 2025-10-01 | 2028-10-01 | One-Time | [13 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
31 | Resource Program | Other Processes | Resource Program development process (and ongoing Resource Programs) | 2025-04-01 | 2026-08-30 | Ongoing | [7 empty] | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | RP 26 | [7 empty] | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | RP 28 | [7 empty] | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | RP 30 | [7 empty] | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32 | RP 32
32 | Resource Program | Other Processes | Resource Program Document published (and ongoing Resource Programs) |  | 2026-09-30 | Ongoing |  |  |  |  | RP 24 | [19 empty] | RP 26 | [23 empty] | RP 28 | [23 empty] | RP 30 | [23 empty] | RP 32
17 | WRAP (for Load Following) | Other Processes | First binding season begins |  | 2027-11-01 | One-Time | [38 empty] | X
18 | WRAP (for Load Following) | Other Processes | Customer send BPA QCC and joint accreditation for Winter Forward Showing information |  | 2026-11-01 | Annual | [26 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X
19 | WRAP (for Load Following) | Other Processes | Customer send BPA QCC and joint accreditation Summer Forward Showing information |  | 2027-06-01 | Annual | [33 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X
20 | WRAP (for Load Following) | Other Processes | Customer send BPA a forecast of physical resource gen schedule in advance of WRAP winter season |  | 2027-10-01 | Annual | [37 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X | [11 empty] | X
21 | WRAP (for Load Following) | Other Processes | Customer send BPA a forecast of physical resource gen schedule in advance of WRAP summer season |  | 2027-05-01 | Annual | [32 empty] | X | [11 empty] | X | [23 empty] | X | [11 empty] | X | [11 empty] | X
22 | WRAP (for Load Following) | Other Processes | Customer Submit Day-Ahead physical resource schedule(s) for WRAP winter season |  | 2027-10-31 | Annual | [37 empty] | X | X | X | X | X | X | [6 empty] | X | X | X | X | X | X | [6 empty] | X | X | X | X | X | X | [6 empty] | X | X | X | X | X | X | [6 empty] | X | X | X | X | X | X
23 | WRAP (for Load Following) | Other Processes | Customer Submit Day-Ahead physical resource schedule(s) for WRAP summer season |  | 2028-05-31 | Annual | [44 empty] | X | X | X | X | X | [7 empty] | X | X | X | X | X | [7 empty] | X | X | X | X | X | [7 empty] | X | X | X | X | X | [7 empty] | X | X | X | X | X
33 | Planned Product Net Requirements Transparency Process |  | BPA publishes planned product customer draft net requirements |  | 2027-07-08 | Rate period | [34 empty] | X | [23 empty] | X | [23 empty] | X
34 | Planned Product Net Requirements Transparency Process |  | Public comment period (2 weeks) | 2027-07-19 | 2027-08-02 | Rate period | [34 empty] | X | [23 empty] | X | [23 empty] | X
35 | Planned Product Net Requirements Transparency Process |  | BPA update and publish final net requirements |  | 2027-08-07 | Rate period | [35 empty] | X | [23 empty] | X | [23 empty] | X
36 | Planned Product Net Requirements Transparency Process |  | Customer deadline to update for first FY of rate period |  | 2028-01-31 | Rate period | [40 empty] | X | [23 empty] | X | [23 empty] | X
37 | Planned Product Net Requirements Transparency Process |  | Customer deadline to update for second FY of rate period |  | 2029-01-31 | Rate period | [52 empty] | X | [23 empty] | X
38 | Above-CHWM Election |  | One-time election within 60 calendar days after BPA publishes final CHWMs from FY 2026 CHWM Calc Process. |  | 2027-06-30 | One-time | Corrected the process name | [32 empty] | X
40 | Above-CHWM Load Process |  | BPA publish draft Above-CHWM amounts |  | 2027-05-21 | Rate period; pending comments on CHWM Impl. Pol. | [32 empty] | X | [23 empty] | X | [11 empty] | X | [23 empty] | X
41 | Above-CHWM Load Process |  | Public comment period (2 weeks) |  | 2027-06-05 | Rate period; pending comments on CHWM Impl. Pol. | [32 empty] | X | X | [22 empty] | X | X | [10 empty] | X | X | [22 empty] | X | X
42 | Above-CHWM Load Process |  | BPA resolve comments and calculate final Above-CHWM amounts |  | 2027-06-28 | Rate period; pending comments on CHWM Impl. Pol. | [33 empty] | X | [23 empty] | X | [11 empty] | X | [23 empty] | X
43 | Above-CHWM Load Process |  | BPA publish final Above-CHWM amounts |  | 2027-07-01 | Rate period; pending comments on CHWM Impl. Pol. | [34 empty] | X | [23 empty] | X | [11 empty] | X | [23 empty] | X
39 | Tier 2 Short-Term Election Deadline |  | Customer Tier 2 Short-Term Election deadline |  | 2027-07-31 | Rate period | [34 empty] | X | [23 empty] | X | [11 empty] | X | [23 empty] | X
44 | Slice Implementation | Slice Creditworthiness Agreement | Slice Creditworthiness Agreement Development | TBD | TBD | One-time
| Slice Implementation | Slice Operations Forum (SOF) | SOF Charter (Draft and Final) | 2/28/2026 (Draft) | 3/31/2026 (Final) | One-time | New | [16 empty] | X | X
45 | Slice Implementation | Provider of Choice Slice Application (POCSA) | POSCA Development leading to Oct. 1, 2028 Deployment Date | 2026-01-01 | 2028-10-01 | One-time; detailed timing subject to change | Updated description and date | [15 empty] | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
46 | CHWM Implementation Processes | Conservation Adj | Verify CY 2023 NEEA savings breakout by qualifying customer | 2024-09-01 | 2024-12-31 | One-time | End date updated | X | X | X
47 | CHWM Implementation Processes | Conservation Adj | Deadline to submit self-funded conservation for FY 2022 and FY 2023. Exact deadline for September 2025 has yet to be set. | 2024-09-01 | Sept. 2025 | One-time | End date updated | X | X | X | X | X | X | X | X | X | X | X | X
48 | CHWM Implementation Processes | Attachment A | Draft Attachment A published for comment (CHWM Implementation Policy) | 2024-10-29 | 2024-11-13 | One-time |  | X | X
49 | CHWM Implementation Processes | Attachment A | Final Attachment A published (CHWM Implementation Policy). All resource removal requests will be complete by publication. | 2024-08-25 | 2024-08-28 | One-time | [11 empty] | X
50 | CHWM Implementation Processes | CHWM Model Updates | Publish update with acutal TRL and NLSLs | 2024-10-19 | 2024-10-19 | One-time |  | X
51 | CHWM Implementation Processes | CHWM Model Updates | Publish updated model with adjustment option | 2024-12-31 | 2025-01-31 | One-time | End date extended |  |  | X | X
52 | CHWM Implementation Processes | NLSL | AE outreach to customer on NLSL determinations | 2024-12-01 | 2/29/2025 | One-time | Extended timeline |  |  | X | X | X
53 | CHWM Implementation Processes | Weather Normalization | Publish weather normalization approach via presentation |  | 2024-10-22 | One-time |  | X
54 | CHWM Implementation Processes | Weather Normalization | Deadline to submit a comment to use a different weather station | 2024-10-22 | 2024-12-31 | One-time |  | X | X | X
55 | CHWM Implementation Processes | Weather Normalization | Deadline to provide monthly irrigation amounts/system distribution losses and any hourly load data required by notice | 2024-10-22 | 2025-01-31 | One-time |  | X | X | X | X
56 | CHWM Implementation Processes | Weather Normalization | BPA delivers initial weather normalation data for customers to review | 2025-02-28 | 2025-03-31 | One-time | [5 empty] | X | X
57 | CHWM Implementation Processes | Weather Normalization | Comment period on weather normalized loads |  | 2025-06-15 | One-time | [9 empty] | X
58 | CHWM Implementation Processes | Weather Normalization | Publish final weather normalized loads |  | 2025-08-29 | One-time | [11 empty] | X
59 | CHWM Implementation Processes | Economic and CF/CT Adjustment | Deadline to request economic or CF/CT adjustment | 2024-09-01 | 2024-10-01 | One-time |  | X
60 | CHWM Implementation Processes | Economic and CF/CT Adjustment | AE outreach to customer if more information in required | 2024-10-28 | 2024-11-30 | One-time |  | X | X
61 | CHWM Implementation Processes | Economic and CF/CT Adjustment | Determination of whether customer met requirements for either adjustment shared to customer |  | 2024-11-29 | One-time |  |  |  | X | X
63 | CHWM Implementation Processes | Economic and CF/CT Adjustment | Deadline to submit data for adjustments |  | 2024-10-15 | One-time |  | X
64 | CHWM Implementation Processes | Economic and CF/CT Adjustment | AE outreach to customer if needed regarding data |  | 2024-11-11 | One-time |  |  | X
65 | CHWM Implementation Processes | Economic and CF/CT Adjustment | Share final economic adjustment amounts with customers |  | 2024-12-22 | One-time |  |  |  | X
62 | CHWM Implementation Processes | Economic and CF/CT Adjustment | Reminder to economic and CF/CT adjustment customers that data will be required shortly after fiscal year ends |  | 2025-08-01 | One-time | Corrected date to 2025 | [10 empty] | X
66 | CHWM Implementation Processes | Economic and CF/CT Adjustment | Deadline to submit CF/CT data to qualify for an adjustment during BP-29 (calculated during the Above-CHWM Load Process) |  | 2027-04-01 | One-time | [31 empty] | X
67 | CHWM Implementation Processes | Economic and CF/CT Adjustment | Deadline to submit CF/CT data to qualify for an adjustment. |  | 2028-10-31 | One-time | [49 empty] | X
68 | CHWM Implementation Processes | FY 2026 Calculation | Publish draft CHWMs |  | 2026-02-19 | One-time | [17 empty] | X
69 | CHWM Implementation Processes | FY 2026 Calculation | Public Comment Period on calculation |  | 2026-03-05 | One-time | [17 empty] | X | X
70 | CHWM Implementation Processes | FY 2026 Calculation | Publish preliminary final CHWMs |  | 2026-04-02 | One-time | [19 empty] | X
71 | CHWM Implementation Processes | FY 2026 Calculation | Publish notice of final CHWMs |  | 2026-04-14 | One-time | [19 empty] | X
72 | CHWM Implementation Processes | Dispute Resolution | Deadline to request dispute resolution |  | 2026-04-13 | One-time | [19 empty] | X
73 | CHWM Implementation Processes | Dispute Resolution | Hearing on dispute resolution |  | TBD | One-time | [19 empty] | X | X
74 | CHWM Implementation Processes | Dispute Resolution | Deadline to hold hearing on dispute resolution matters |  | 2026-05-11 | One-time | [19 empty] | X | X
75 | CHWM Implementation Processes | Dispute Resolution | Publish and notice final CHWMs |  | 2026-05-31 | One-time | [20 empty] | X
Formulas:
March 2025 = [TBD]+14

## BPA Websites
Select BPA Public Process Resources
For more information about individual BPA public processes, please visit bpa.gov:
Provider of Choice | https://www.bpa.gov/energy-and-services/power/provider-of-choice
Provider of Choice-related Implementation, including CHWM implementation | https://www.bpa.gov/energy-and-services/power/provider-of-choice/implementation
Day-Ahead Market | https://www.bpa.gov/learn-and-participate/projects/day-ahead-market
Energy Efficiency | https://www.bpa.gov/energy-and-services/efficiency
Post-2028 Residential Exchange Program | https://www.bpa.gov/energy-and-services/power/residential-exchange-program/post-2028-rep
Power Rates | https://www.bpa.gov/energy-and-services/rate-and-tariff-proceedings/power-rates
Public Rate Design Methodology 2029 | https://www.bpa.gov/energy-and-services/rate-and-tariff-proceedings/public-rate-design-methodology-2029
Resource Program | https://www.bpa.gov/energy-and-services/power/resource-planning
Western Resource Adequacy Program (WRAP) | https://www.bpa.gov/learn-and-participate/projects/western-resource-adequacy-program

## Versions
Multi-Process Timeline | Version Date: | 2024-11-12
Multi-Process Timeline | Version Date: | 2024-12-09