## Feasibility Studies
| Bonneville Power Administration (FERC 845) Feasibility Study Completion Report |  |  |  | 2024-12-21 04:46
FERC Order 845 | A | B | C | D | E
Year | Number of Completed Feasibility Study Requests | Number of Feasibility Study Requests Completed more than 45 days | Number of Feasibility Study Requests Incomplete more than 45 days | Mean Completion Time (Days) | Percentage of Studies Exceeding Completion Timeline E=(B+C)/(A+C)
2021 Q4 | 10 | 6 | 0 | 100 | 60
2022 Q1 | 10 | 9 | 1 | 148 | 91
2022 Q2 | 14 | 14 | 1 | 116 | 100
2022 Q3 | 4 | 2 | 3 | 84 | 71
2022 Q4 | 10 | 9 | 10 | 113 | 95
2023 Q1 | 9 | 9 | 12 | 232 | 100
2023 Q2 | 7 | 7 | 21 | 178 | 100
2023 Q3 | 2 | 2 | 24 | 99 | 100
2023 Q4 | 5 | 5 | 70 | 220 | 100
2024 Q1 | 7 | 7 | 109 | 288 | 100
2024 Q2 | 67 | 67 | 145 | 522 | 100
2024 Q3 | 0 | 0 | 0 | 0 | 0

## Phase 1 Cluster Studies
| Bonneville Power Administration (FERC 845) Phase 1 Cluster Study Completion Report |  |  |  | 2024-12-21 04:46
FERC Order 845 | A | B | C | D | E
Year | Number of Completed Phase 1 Cluster Study Requests | Number of Phase 1 Cluster Study Requests Completed more than 120 days | Number of Phase 1 Cluster Study Requests Incomplete more than 120 days | Mean Completion Time (Days) | Percentage of Studies Exceeding Completion Timeline E=(B+C)/(A+C)
2021 Q4 | 0 | 0 | 0
2022 Q1 | 0 | 0 | 0
2022 Q2 | 0 | 0 | 0
2022 Q3 | 0 | 0 | 0
2022 Q4 | 0 | 0 | 0
2023 Q1 | 0 | 0 | 0
2023 Q2 | 0 | 0 | 0
2023 Q3 | 0 | 0 | 0
2023 Q4 | 0 | 0 | 0
2024 Q1 | 0 | 0 | 0
2024 Q2 | 0 | 0 | 0
2024 Q3 | 0 | 0 | 0

## System Impact Studies
| Bonneville Power Administration (FERC 845) System Impact Studies |  |  |  | 2024-12-21 04:46
FERC Order 845 | A | B | C | D | E
Year | Number of Completed System Impact Study Requests | Number of System Impact Study Requests Completed more than 90 days | Number of System Impact Study Requests Incomplete more than 90 days | Mean Completion Time (Days) | Percentage of Studies Exceeding Completion Timeline E=(B+C)/(A+C)
2021 Q4 | 6 | 3 | 0 | 116 | 50
2022 Q1 | 5 | 4 | 0 | 128 | 80
2022 Q2 | 12 | 8 | 1 | 145 | 69
2022 Q3 | 21 | 11 | 3 | 122 | 58
2022 Q4 | 11 | 10 | 5 | 168 | 94
2023 Q1 | 9 | 6 | 5 | 145 | 79
2023 Q2 | 12 | 7 | 6 | 196 | 72
2023 Q3 | 9 | 4 | 6 | 162 | 67
2023 Q4 | 5 | 4 | 11 | 339 | 94
2024 Q1 | 1 | 1 | 13 | 198 | 100
2024 Q2 | 12 | 11 | 15 | 459 | 96
2024 Q3 | 0 | 0 | 0 | 0 | 0

## Phase 2 Cluster Studies
| Bonneville Power Administration (FERC 845) Phase 2 Cluster Study Completion Report |  |  |  | 2024-12-21 04:46
FERC Order 845 | A | B | C | D | E
Year | Number of Completed Phase 2 Cluster Study Requests | Number of Phase 2 Cluster Study Requests Completed more than 180 days | Number of Phase 2 Cluster Study Requests Incomplete more than 180 days | Mean Completion Time (Days) | Percentage of Studies Exceeding Completion Timeline E=(B+C)/(A+C)
2021 Q4 | 0 | 0 | 0
2022 Q1 | 0 | 0 | 0
2022 Q2 | 0 | 0 | 0
2022 Q3 | 0 | 0 | 0
2022 Q4 | 0 | 0 | 0
2023 Q1 | 0 | 0 | 0
2023 Q2 | 0 | 0 | 0
2023 Q3 | 0 | 0 | 0
2023 Q4 | 0 | 0 | 0
2024 Q1 | 0 | 0 | 0
2024 Q2 | 0 | 0 | 0
2024 Q3 | 0 | 0 | 0

## Facility Studies Old
| Bonneville Power Administration (FERC 845) Facility Studies |  |  |  | 2024-12-21 04:46
FERC Order 845 | A | B | C | D | E
Year | Number of Completed Facility Study Requests | Number of Facility Study Requests Completed more than 180 days | Number of Facility Study Requests Incomplete more than 180 days | Mean Completion Time (Days) | Percentage of Studies Exceeding Completion Timeline E=(B+C)/(A+C)
2021 Q4 | 1 | 1 | 2 | 304 | 100
2022 Q1 | 4 | 4 | 2 | 409 | 100
2022 Q2 | 1 | 1 | 3 | 385 | 100
2022 Q3 | 2 | 1 | 3 | 339 | 80
2022 Q4 | 3 | 2 | 6 | 443 | 89
2023 Q1 | 5 | 5 | 7 | 488 | 100
2023 Q2 | 7 | 7 | 8 | 556 | 100
2023 Q3 | 4 | 3 | 13 | 377 | 94
2023 Q4 | 7 | 6 | 14 | 469 | 95
2024 Q1 | 4 | 4 | 22 | 618 | 100
2024 Q2 | 14 | 11 | 28 | 536 | 93
2024 Q3 | 0 | 0 | 0 | 0 | 0

## Facility Studies
| Bonneville Power Administration (FERC 845) Facility Studies |  |  |  | 2024-12-21 04:46
FERC Order 845 | A | B | C | D | E
Year | Number of Completed Facility Study Requests | Number of Facility Study Requests Completed more than Completion Schedule | Number of Facility Study Requests Incomplete more than Completion Schedule | Mean Completion Time (Days) | Percentage of Studies Exceeding Completion Timeline E=(B+C)/(A+C)
2021 Q4 | 1 | 0 | 2 | 304 | 67
2022 Q1 | 4 | 0 | 2 | 409 | 33
2022 Q2 | 1 | 0 | 3 | 385 | 75
2022 Q3 | 2 | 0 | 3 | 339 | 60
2022 Q4 | 3 | 0 | 6 | 443 | 67
2023 Q1 | 5 | 0 | 7 | 488 | 58
2023 Q2 | 7 | 0 | 8 | 556 | 53
2023 Q3 | 4 | 0 | 13 | 377 | 76
2023 Q4 | 7 | 0 | 14 | 469 | 67
2024 Q1 | 4 | 0 | 22 | 618 | 85
2024 Q2 | 14 | 0 | 28 | 536 | 67
2024 Q3 | 6 | 0 | 34 | 501 | 85

## Withdrawn Requets Old
|  | FERC ORDER 845: Withdrawn Requests |  |  | 2024-12-21 04:46
| A | B | C | D | E | F
Year | Number of Requests Withdrawn | Number Requests Withdrawn Before Study Agreement | Number Withdrawn Before Completion of System Impact Study | Number Withdrawn Before Completion of Facility Study | Number Withdrawn After Exec of GI Agreement | Mean Time (Days) Study Withdrawl - Request Received
2021 Q4 | 2 | 1 | 1 | 2 | 0 | 288
2022 Q1 | 4 | 1 | 2 | 2 | 0 | 2431
2022 Q2 | 9 | 4 | 6 | 8 | 0 | 458
2022 Q3 | 4 | 3 | 3 | 3 | 0 | 410
2022 Q4 | 3 | 1 | 3 | 3 | 0 | 169
2023 Q1 | 13 | 9 | 12 | 13 | 0 | 221
2023 Q2 | 13 | 6 | 10 | 12 | 0 | 532
2023 Q3 | 6 | 2 | 6 | 6 | 0 | 292
2023 Q4 | 1 | 0 | 0 | 1 | 0 | 943
2024 Q1 | 9 | 8 | 8 | 8 | 0 | 393
2024 Q2 | 8 | 0 | 4 | 7 | 0 | 768
2024 Q3 | 0 | 0 | 0 | 0 | 0 | 0

## Withdrawn Requets
|  | FERC ORDER 845: Withdrawn Requests |  |  | 2024-12-21 04:46
| A | B | C | D | E | F
Year | Number of Requests Withdrawn | Number Requests Withdrawn Before Study Agreement | Number Withdrawn Before Completion of Phase 2 Cluster Study | Number Withdrawn Before Completion of Facility Study | Number Withdrawn After Exec of GI Agreement | Mean Time (Days) Study Withdrawl - Request Received
2021 Q4 | 2 | 1 | 0 | 2 | 0 | 288
2022 Q1 | 4 | 1 | 0 | 2 | 0 | 2431
2022 Q2 | 9 | 4 | 0 | 8 | 0 | 458
2022 Q3 | 4 | 3 | 0 | 3 | 0 | 410
2022 Q4 | 3 | 1 | 0 | 3 | 0 | 169
2023 Q1 | 13 | 9 | 0 | 13 | 0 | 221
2023 Q2 | 13 | 6 | 0 | 12 | 0 | 532
2023 Q3 | 6 | 2 | 0 | 6 | 0 | 292
2023 Q4 | 1 | 0 | 0 | 1 | 0 | 943
2024 Q1 | 9 | 8 | 0 | 8 | 0 | 393
2024 Q2 | 8 | 0 | 0 | 7 | 0 | 768
2024 Q3 | 41 | 0 | 0 | 37 | 0 | 456

## 845P -Delayed Study Report
|  | FERC 845P - Delayed Study Report | 2024-12-21 04:46
Request Number | Study | Reason for Delay | Remedial Action
G0639 | FAS
G0641 | FAS
G0642 | ISIS
G0642 | FAS
G0643 | FAS
G0643 | ISIS
G0650 | FAS
G0651 | FAS
G0654 | ISIS
G0655 | ISIS
G0657 | FAS
G0660 | FAS
G0662 | ISIS
G0663 | FAS
G0663 | ISIS
G0664 | ISIS
G0665 | FAS
G0668 | FAS
G0669 | ISIS
G0669 | FAS
G0670 | FAS
G0671 | FAS
G0676 | ISIS
G0676 | FAS
G0677 | FAS
G0678 | ISIS
G0678 | FAS
G0679 | FAS
G0679 | ISIS
G0680 | FAS
G0680 | ISIS
G0681 | FAS
G0681 | FES
G0682 | ISIS
G0683 | FES
G0683 | FAS
G0684 | FAS
G0684 | ISIS
G0686 | FES
G0686 | FAS
G0686 | FAS
G0686 | ISIS
G0687 | FES
G0687 | ISIS
G0687 | FAS
G0688 | FES
G0688 | ISIS
G0689 | ISIS
G0689 | FES
G0689 | FAS
G0691 | ISIS
G0691 | FAS
G0692 | FES
G0693 | FES
G0694 | FES
G0695 | FES
G0696 | FES
G0697 | FES
G0698 | FES
G0699 | FES
G0700 | FES
G0701 | FES
G0702 | FES
G0704 | FES
G0705 | ISIS
G0705 | FAS
G0705 | FES
G0706 | FAS
G0706 | ISIS
G0707 | FAS
G0707 | ISIS
G0708 | FES
G0709 | ISIS
G0709 | FAS
G0710 | FAS
G0711 | FES
G0711 | ISIS
G0712 | ISIS
G0712 | FES
G0713 | FAS
G0713 | ISIS
G0714 | FAS
G0714 | FES
G0714 | ISIS
G0715 | FES
G0715 | ISIS
G0715 | FAS
G0716 | ISIS
G0716 | FAS
G0717 | ISIS
G0717 | FAS
G0718 | FES
G0718 | ISIS
G0720 | ISIS
G0720 | FAS
G0720 | FES
G0721 | ISIS
G0721 | FAS
G0722 | ISIS
G0723 | ISIS
G0723 | FES
G0724 | FES
G0724 | ISIS
G0725 | ISIS
G0725 | FES
G0728 | FES
G0729 | ISIS
G0729 | FES
G0730 | ISIS
G0730 | FAS
G0731 | FES
G0731 | FAS
G0732 | FES
G0733 | FAS
G0734 | FAS
G0735 | FES
G0737 | ISIS
G0738 | FAS
G0739 | FES
G0741 | FES
G0741 | FAS
G0743 | FES
G0744 | ISIS
G0745 | FES
G0745 | ISIS
G0746 | FAS
G0746 | ISIS
G0746 | FES
G0747 | FES
G0748 | FES
G0748 | ISIS
G0749 | ISIS
G0749 | FES
G0750 | FES
G0751 | FES
G0752 | FES
G0753 | FES
G0754 | FES
G0757 | FES
G0758 | FES
G0759 | FES
G0760 | FES
G0761 | FES
G0762 | FES
G0763 | FES
G0764 | ISIS
G0764 | FES
G0765 | FAS
G0767 | FES
G0768 | FES
G0769 | ISIS
G0770 | FAS
G0770 | ISIS
G0771 | ISIS
G0771 | FAS
G0772 | ISIS
G0773 | FES
G0774 | FES
G0777 | FES
G0778 | FES
G0781 | FES
G0782 | FES
G0785 | FES
G0786 | FES
G0787 | FES
G0788 | FES
G0791 | FES
G0792 | FES
G0793 | ISIS
G0793 | FES
G0794 | FES
G0794 | ISIS
G0795 | FES
G0796 | FES
G0797 | FES
G0798 | FES
G0799 | FES
G0800 | FES
G0801 | FES
G0802 | FES
G0803 | FES
G0804 | FES
G0805 | FES
G0806 | FES
G0807 | FES
G0808 | FES
G0809 | FES
G0810 | FES
G0811 | FES
G0812 | FES
G0813 | FES
G0815 | FES
G0816 | FES
G0817 | FES
G0818 | FAS
G0819 | FES
G0820 | FES
G0821 | FAS
G0822 | FES
G0824 | FES
G0825 | FES
G0826 | FES
G0828 | FES
G0829 | FES
G0830 | FES
G0832 | FAS
G0833 | FES
G0833 | ISIS
G0834 | FES
G0835 | FES
G0837 | FAS
G0838 | FES
G0839 | FES
G0840 | FES
G0841 | FES
G0843 | FES
G0844 | FES
G0846 | FES
G0847 | FAS
G0848 | FES
G0849 | FES
G0850 | FES
G0852 | FES
G0853 | FES
G0854 | ISIS
G0855 | FES
G0856 | FES
G0857 | FES
G0858 | FES
G0860 | FES
G0861 | FES
G0862 | ISIS
G0863 | ISIS
G0864 | ISIS
G0865 | FES
G0866 | FES
G0867 | FES
G0869 | FES
G0870 | FES
G0871 | FES
G0872 | FES
G0873 | FES
G0874 | FES
G0875 | FES
G0876 | FES
G0877 | FES
G0878 | FES
G0879 | FES
G0880 | FES
G0881 | FES
G0882 | FES
G0883 | FES
G0884 | FES
G0885 | FES
G0886 | FES
G0887 | FES
G0888 | FES
G0889 | FES
G0890 | FES
G0891 | FES
G0892 | FES
G0893 | FES
G0894 | FES
G0895 | FES
G0896 | FES
G0897 | FES
G0898 | FES
G0899 | FES
G0900 | FES
G0901 | FES
G0902 | FES
G0903 | FES
G0904 | FES
G0905 | FES
G0906 | FES
G0907 | FES
G0908 | ISIS
G0909 | FES
G0910 | FES
G0911 | FES
G0912 | FES
G0913 | FES
G0914 | FES
G0915 | FES
G0916 | FES
G0917 | FAS
G0918 | FES
G0919 | ISIS
G0920 | FES
G0921 | FES
G0922 | FES
G0923 | FES
G0924 | FES
G0925 | FES
G0926 | FES
G0927 | FES
G0928 | FES
G0929 | FES
G0930 | FES
G0931 | FES
G0932 | FES
G0933 | FES
G0934 | FES
G0935 | FES
G0936 | FAS
G0937 | FES
G0938 | FES
G0939 | ISIS
G0940 | ISIS
G0941 | ISIS
G0942 | FES
G0944 | FES
G0945 | FES
G0946 | FES
G0947 | FES
G0948 | FES
G0949 | FES
G0950 | FES
G0951 | FES
G0952 | FES
G0953 | FES
G0954 | FES
G0955 | FES
G0956 | FES
G0957 | FAS
G0958 | FES
G0959 | FES
G0960 | FES
G0961 | FES
G0962 | FES
G0963 | FES
G0964 | FES
G0965 | FES
G0966 | FES
G0967 | FES
G0969 | FES
G0970 | FES
G0971 | FES
G0972 | FES
G0973 | FES
G0974 | FES
G0975 | FAS
G0976 | FAS
G0978 | FAS
G0979 | FES
G0980 | FES
G0981 | FES
G0982 | FES
G0983 | FES
G0985 | FES
G0986 | FES
G0987 | FES
G0988 | FES
G0989 | FES
G0990 | FES
G0991 | FES
G0992 | FES
G0993 | FES
G0994 | FES
G0995 | FES
G0996 | FES
G0997 | FES
G0998 | FES
G1000 | FES
G1001 | FES
G1002 | FES
G1003 | FAS
G1004 | FAS
G1005 | FES
G1007 | FES
G1008 | FAS
G1009 | FES
G1010 | FES
G1012 | FES
G1013 | FES
G1014 | FES
G1015 | FES
G1016 | FES
G1017 | FES
G1018 | FES
G1019 | FES
G1020 | FES
G1021 | FES
G1022 | FES
G1023 | FES
G1024 | FES
G1025 | FES
G1027 | FES
G1028 | FES
G1029 | FES
G1030 | FES
G1031 | FES
G1032 | FES
G1033 | FES
G1034 | FES
G1035 | FES
G1036 | FES
G1037 | FES
G1038 | FES
G1039 | FES
G1040 | FES
G1041 | FES
G1042 | FES
G1043 | FES
G1044 | FES
G1045 | FES
G1046 | FES
G1047 | FES
G1048 | FES
G1049 | FES
G1050 | FES
G1051 | FES
G1052 | FES
G1053 | FES
G1054 | FES
G1055 | FES
G1056 | FES
G1057 | FES
G1058 | ISIS
G1062 | ISIS
G1063 | ISIS
G1064 | FAS
G1067 | FAS