## Sheet1
|  |  | Bonneville Power Administration Interconnection Request Queue |  |  |  |  | 2024-12-21 16:01
Note: Requests with queue positions lower than 200 were submitted prior to adoption of LGIP/SGIP.
Please see the Comments for additional details.
Generator Interconnection technical study reports are available upon request to |  |  | studyrequest@bpa.gov | [26 empty] | Reports
Request Number | Request Date | Project Name | Requestor | Comments | Point Of Interconnection | Status | State | County | Connection Type | Requested In-Service Date | Agreed To: (Blank=TBD) | Max Summer MW | Max Winter MW | Interconnection Type | Generator Type 1 | Fuel Source 1 | MW1 | Generator Type 2 | Fuel Source 2 | MW2 | Generator Type 3 | Fuel Source 3 | MW3 | MW Total | Cluster | Related Transmission Request | Reason Not Completed | Feasibility Study | Phase 1 Cluster Study | System Impact Study | Phase 2 Cluster Study | Facilities Study | Surplus Interconnection Service Request | Repower
L0637 | 2024-12-11 10:01 | 125 MW 115 kV Sacajawea Tap | Columbia Rural Electric Association |  |  | RECEIVED | WA | Walla Walla | LL | 2027-12-16 |  | 125 | 125 |  | Other | Other | 125 | [6 empty] | 125 |  |  | . | [5 empty] | FALSE
L0636 | 2024-11-21 10:47 | McNary 230 kV Looped | Umatilla Electric Cooperative |  | McNary Substation | RECEIVED |  | Umatilla | LL | 2027-11-21 |  | 1256 | 1256 |  | Other | Other | 1256 | [6 empty] | 1256 |  |  | . | [5 empty] | FALSE
G1071 | 2024-10-25 16:15 |  |  | 835 kW project | Central Electric Cooperative's (CEC) 12.5kV distribution line served via CEC's Knott Substation | RECEIVED | OR | Deschutes | GI | 2025-08-01 | 2025-08-01 | 0.9 | 0.9 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0635 | 2024-10-24 14:50 | SUB 20.8 kV Load Addition | Springfield Utility Board |  | Alvey Substation | BPA COMPLETED |  | Lane | LL | 2025-09-01 | 2025-09-01 | 8 | 8 |  | Other | Other | 7.2 | [6 empty] | 7.2 |  |  | . | [5 empty] | FALSE
L0634 | 2024-10-22 15:24 | VIC Load Addition | Clark Public Utilities |  |  | STUDY |  | Clark | LL | 2026-06-30 | 2026-06-30 | 40 | 40 |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
L0633 | 2024-10-21 12:47 | Hot Springs-Camas Prairie Substations Load Addition | Mission Valley Power |  | Hot Springs Substation | RECEIVED |  | Sanders | LL | 2027-10-24 |  | 9 | 9 |  | Other | Other | 8.2 | [6 empty] | 8.2 |  |  | . | [5 empty] | FALSE
L0632 | 2024-10-14 08:19 | Redmond 69 kV to 115 kV | Central Electric Cooperative, Inc. |  |  | STUDY |  | Deschutes | LL | 2027-10-16 | 2027-10-16 | 50 | 50 |  | Other | Other | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
L0631 | 2024-10-02 15:55 | Hyundai Load | Eugene Water & Electric Board |  | Lane Substation or Eugene-Alvey No 2 115kV line | STUDY |  | Lane | LL | 2027-10-04 |  | 200 | 200 |  | Other | Other | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0630 | 2024-10-02 13:01 | Data Storage Facility | Columbia Rural Electric Association |  | Lower Monumental-McNary No. 1 500 kV line | STUDY | WA | Walla Walla | LL | 2027-10-03 | 2027-10-03 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0629 | 2024-10-01 07:50 | Basalt 230 kV Load | Umatilla Electric Cooperative |  | McNary Substation via McNary-Wanapa Switching Station No 1 230 kV line | RECEIVED | OR | Umatilla | LL | 2027-01-02 | 2027-01-02 | 154 | 154 |  | Other | Other | 153.4 | [6 empty] | 153.4 |  |  | . | [5 empty] | FALSE
L0628 | 2024-09-25 09:12 | Thompson Creek Mine Load | Salmon River Electric Cooperative, Inc. |  | Round Valley Substation | RECEIVED | ID | Custer | LL | 2027-09-25 | 2027-09-25 | 28 | 28 |  | Other | Other | 28 | [6 empty] | 28 |  |  | . | [5 empty] | FALSE
L0627 | 2024-09-23 14:55 | University of Oregon Loads | Eugene Water & Electric Board |  | Alvey Substation | RECEIVED | OR | Lane | LL | 2027-09-24 |  | 19 | 19 |  | Other | Other | 19 | [6 empty] | 19 |  |  | . | [5 empty] | FALSE
L0626 | 2024-09-19 13:02 | Staley Substation | Inland Power & Light Company |  | Bell-Addy No. 1 115 kV | STUDY | WA | Spokane | LL | 2027-09-20 |  | 19 | 19 |  | Other | Other | 18.1 | [6 empty] | 18.1 |  |  | . | [5 empty] | FALSE
L0624 | 2024-09-11 15:13 | New Plymouth Substation | Benton Rural Electric Association |  | TBD | RECEIVED | WA | Benton | LL | 2027-09-12 | 2027-09-12 | 15 | 15 |  | Other | Other | 15 | [6 empty] | 15 |  |  | . | [5 empty] | FALSE
L0621 | 2024-09-06 15:30 | West Richland Data Center Campus | Benton Rural Electric Association |  | Ashe-Slatt No 1 500 kV line; Ashe-Marion No 2 500 kV line | STUDY | WA | Benton | LL | 2028-03-01 | 2028-03-01 | 912 | 912 |  | Other | Other | 912 | [6 empty] | 912 |  |  | . | [5 empty] | FALSE
L0622 | 2024-09-06 15:30 | Plymouth Data Center Campus | Benton Rural Electric Association |  | McNary-John Day No. 2 500 kV line | WITHDRAWN | WA | Benton | LL | 2028-09-01 |  | 864 | 864 |  | Other | Other | 864 | [6 empty] | 864 |  |  | . | [5 empty] | FALSE
L0620 | 2024-09-04 11:55 | Project Dune | City of Richland, Washington |  | TBD | RECEIVED | WA |  | LL | 2027-11-01 | 2027-11-01 | 99 | 99 |  | Other | Other | 99 | [6 empty] | 99 |  |  | . | [5 empty] | FALSE
L0625 | 2024-09-04 09:53 | Five Mile 115 kV | Avista Corporation |  | Bell 115 kV Substation | RECEIVED | WA | Spokane | LL | 2027-09-17 |  | 36 | 36 |  | Other | Other | 35.7 | [6 empty] | 35.7 |  |  | . | [5 empty] | FALSE
L0623 | 2024-09-04 09:47 | Trentwood 115 kV | Avista Corporation |  | Trentwood Substation | RECEIVED | WA | Spokane | LL | 2027-09-11 |  | 80 | 80 |  | Other | Other | 79.3 | [6 empty] | 79.3 |  |  | . | [5 empty] | FALSE
L0619 | 2024-08-28 15:51 | New 115 kV Creston Substation | Inland Power & Light Company |  | Bell-Creston 115 kV line | STUDY | WA | Spokane | LL | 2027-09-03 |  | 10 | 10 |  | Other | Other | 9.8 | [6 empty] | 9.8 |  |  | . | [5 empty] | FALSE
L0618 | 2024-08-26 08:02 | Monmouth | City of Monmouth |  | Monmouth Substation | RECEIVED | OR | Polk | LL | 2027-08-28 |  | 30 | 30 |  | Other | Other | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
L0617 | 2024-08-22 10:48 | Parker Substation Additional 4.3 MW | Blachly-Lane Electric Cooperative |  | BPA Eugene-Alderwood 115-kV line | RECEIVED | OR | Lane | LL | 2025-08-23 |  | 5 | 5 |  | Other | Other | 4.3 | [6 empty] | 4.3 |  |  | . | [5 empty] | FALSE
G1070 | 2024-08-19 10:57 |  |  |  | Tucannon River: Puget Sound Energ 115kV Feeder 1 | STUDY | WA | Columbia | GI | 2027-08-31 | 2027-08-31 | 157 | 157 | ERIS | Photovoltaic | Solar | 109.6 | Energy Storage | Battery | 109.9 |  |  |  | 219.5 |  |  | . | [5 empty] | TRUE
L0616 | 2024-08-09 10:27 | Tiger Highway | Avista Corporation |  | Colville-Republic No 1 115kV line | RECEIVED | WA | Stevens | LL | 2027-08-12 |  | 12 | 12 |  | Other | Other | 11.7 | [6 empty] | 11.7 |  |  | . | [5 empty] | FALSE
L0615 | 2024-07-31 08:46 | AE BTC | Public Utility District No. 1 of Cowlitz County |  | Lexington-Longview No 1 115kV line | STUDY | WA | Cowlitz | LL | 2025-12-31 | 2025-12-31 | 50 | 50 | [10 empty] | 0 |  |  | . | [5 empty] | FALSE
G1069 | 2024-07-23 05:47 |  |  |  | 43.439458, -118.704502 for 9.9 MW; 43.438922, -118.704502 for 9.9 MW at Harney 115kV Substation | RECEIVED | OR | Harney | GI | 2025-03-31 |  | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0614 | 2024-06-25 17:10 | Hy2Gen Phase 2 | Public Utility District No. 1 of Cowlitz County |  | Longview Substation | STUDY | WA | Cowlitz | LL | 2027-06-27 | 2027-06-27 | 380 | 380 |  | Other | Other | 380 | [6 empty] | 380 |  |  | . | [5 empty] | FALSE
G1068 | 2024-06-21 13:45 |  |  | 781.82 kW Request | Sifton 115kV Substation | STUDY | WA | Clark | GI | 2024-11-07 |  | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0613 | 2024-06-21 12:17 | Sunheaven 3 Substation | Public Utility District No. 1 of Benton County |  | Horse Heaven Substation 115 kV | STUDY | WA | Benton | LL | 2027-06-24 |  | 5.4 | 5.4 |  | Other | Other | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
L0612 | 2024-06-21 11:48 | Agri-Northwest Coffin Rd Substation | Public Utility District No. 1 of Benton County |  | McNary-Badger Canyon No 1 115kV line | STUDY | WA | Benton | LL | 2027-06-27 |  | 6 | 6 |  | Other | Other | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
L0611 | 2024-06-12 14:26 | Kitsap Peninsula Load | Puget Sound Energy, Inc. |  | Kitsap Substation | RECEIVED | WA | Kitsap | LL | 2034-12-31 | 2034-12-31 | 150 | 150 |  | Other | Other | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
L0609 | 2024-05-20 14:17 | PW1 & PW2 | Clatskanie People's Utility District |  | Allston Substation | STUDY | WA | Columbia | LL | 2027-05-20 | 2027-05-20 | 500 | 500 |  | Other | Other | 250 | Other | Other | 250 |  |  |  | 500 |  |  | . | [5 empty] | FALSE
L0610 | 2024-05-20 14:17 | PW1 & PW2 | Clatskanie People's Utility District |  | Allston Substation | STUDY | WA | Columbia | LL | 2027-05-20 | 2027-05-20 | 105 | 105 |  | Other | Other | 105 | [6 empty] | 105 |  |  | . | [5 empty] | FALSE
L0608 | 2024-05-20 10:18 | Port Angeles 20 MW Load Addition | City of Port Angeles |  | Port Angeles Substation | STUDY | WA | Clallam | LL | 2027-05-21 | 2027-05-21 | 20 | 20 |  | Other | Other | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0607 | 2024-05-15 11:55 | CT-6 | Public Utility District No. 1 of Cowlitz County |  | Lexington Substation | BPA COMPLETED | WA | Cowlitz | LL | 2027-05-16 | 2027-05-16 | 1.9 | 1.9 |  | Other | Other | 1.9 | [6 empty] | 1.9 |  |  | . | [5 empty] | FALSE
G1067 | 2024-05-09 11:50 |  |  |  | Bell-Boundary #1 230 kV line | STUDY | WA | Adams | GI | 2024-10-01 |  | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0606 | 2024-05-08 14:28 | Industrial Load Addition | The City of McMinnville, a municipal corporation of the State of Oregon, acting by and through its Water and Light Commission |  | McMinnville Substation | STUDY COMPLETED | OR | Yamhill | LL | 2027-05-16 | 2027-05-16 | 50 | 50 |  | Other | Other | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
L0605 | 2024-04-24 09:00 | Lower Valley Load Growth | Lower Valley Energy, Inc. |  | Teton 115 kV Substation | STUDY | WY | Teton | LL | 2025-04-25 | 2025-04-25 | 0 | 0 | [10 empty] | 0 |  |  | . | [5 empty] | FALSE
G1066 | 2024-04-23 16:56 |  |  |  | Salem Alumina 115 kV line | STUDY | OR | Marion | GI | 2024-06-01 |  | 1 | 1 | ERIS | Photovoltaic | Solar | 0.4 | [6 empty] | 0.4 |  |  | . | [5 empty] | FALSE
G1065 | 2024-04-22 09:11 |  |  |  | BPA FEEDER: ALBANY L184, 12kV FEEDER to NETL BYPASS DISCONNECT (POLE SWITCH). INTERCONNECTION TO OCCUR ON THE NETL SIDE OF THE BYPASS DISCONNECT | RECEIVED | OR | Linn | GI | 2025-09-30 | 2026-09-30 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G1064 | 2024-04-16 09:09 |  |  |  | UEC Westland to McNary 230 kV line that terminates in the 230 kV Bay 16 terminal of the McNary Substation. | STUDY | OR | Umatilla | GI | 2026-01-01 |  | 15 | 15 | ERIS | Energy Storage | Battery | 15 | [6 empty] | 15 |  |  | . | [5 empty] | FALSE
L0604 | 2024-04-12 13:19 | South Ellensburg Substation | City of Ellensburg |  | Ellensburg-Moxee No 1 115kV line | STUDY | WA | Kittitas | LL | 2027-04-15 | 2030-06-28 | 26 | 26 |  | Other | Other | 26 | [6 empty] | 26 |  |  | . | [5 empty] | FALSE
L0603 | 2024-04-10 13:11 | Getchell Substation | Public Utility District No. 1 of Snohomish County |  | Snohomish-Murray 230kV line | STUDY | WA | Snohomish | LL | 2027-06-15 | 2027-06-15 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0602 | 2024-04-04 08:28 | Forge Ahead 105 MW | City of Richland, Washington |  | White Bluffs 115kV Substation | RECEIVED | WA | Columbia | LL | 2028-01-31 | 2028-01-31 | 105 | 105 |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0601 | 2024-04-02 12:28 | Trammel Crow Data Center | Public Utility District No. 1 of Cowlitz County |  | Longview Substation | WITHDRAWN | WA | Cowlitz | LL | 2024-04-03 | 2029-10-31 | 240 | 240 |  | Other | Other | 240 | [6 empty] | 240 |  |  | . | [5 empty] | FALSE
L0600 | 2024-04-01 16:20 | Silverado Substation Alternate Feed | Public Utility District No. 1 of Clallam County |  | Port Angeles-Sappho No 1 115 kV line | WITHDRAWN | WA | Clallam | LL | 2027-04-02 | 2027-04-02 | 21.5 | 21.5 |  | Other | Other | 21.5 | [6 empty] | 21.5 |  |  | . | [5 empty] | FALSE
L0599 | 2024-03-25 07:34 | Pacific Northwest Renewable Energy's 22 MW Load | Public Utility District No. 1 of Grays Harbor County Washington |  | Aberdeen Substation | STUDY COMPLETED | WA | Grays Harbor | LL | 2025-10-01 | 2027-03-25 | 14.5 | 14.5 |  | Other | Other | 14.5 | [6 empty] | 14.5 |  |  | . | [5 empty] | FALSE
L0598 | 2024-03-22 14:56 | Green Hydrogen Project | Public Utility District No. 1 of Whatcom County |  | Intalco Substation | RECEIVED | WA | Whatcom | LL | 2027-03-25 | 2028-10-01 | 304 | 304 |  | Other | Other | 304 | [6 empty] | 304 |  |  | . | [5 empty] | FALSE
L0597 | 2024-03-21 14:01 | Refinery Substation Load Addition | Public Utility District No. 1 of Whatcom County |  | Bellingham Substation | BPA COMPLETED | WA | Whatcom | LL | 2027-03-21 | 2028-10-01 | 15 | 15 |  | Other | Other | 15 | [6 empty] | 15 |  |  | . | [5 empty] | FALSE
L0596 | 2024-03-21 08:34 | Nucor Steel Mill | Public Utility District No. 1 of Cowlitz County |  | Longview Substation | STUDY | WA | Cowlitz | LL | 2027-03-21 | 2029-10-31 | 110 | 110 |  | Other | Other | 110 | [6 empty] | 110 |  |  | . | [5 empty] | FALSE
L0595 | 2024-03-20 09:27 | CLPUD-CPI Loop Tie Project | Central Lincoln People's Utility District |  | Toledo Substation | STUDY | OR | Lincoln | LL | 2027-03-19 | 2027-03-19 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0594 | 2024-03-13 07:42 | Hy2Gen | Public Utility District No. 1 of Cowlitz County |  | BPA's Longview Substation | STUDY | WA | Cowlitz | LL | 2027-03-18 | 2029-10-31 | 380 | 380 |  | Other | Other | 380 | [6 empty] | 380 |  |  | . | [5 empty] | FALSE
L0593 | 2024-03-11 11:02 | Dutch Canyon Substation | Columbia River People's Utility District |  | St Johns-St Helens No 1 115kV line | STUDY COMPLETED | WA | Columbia | LL | 2027-03-12 | 2027-03-12 | 49.5 | 49.5 |  | Other | Other | 49.5 | [6 empty] | 49.5 |  |  | . | [5 empty] | FALSE
L0592 | 2024-03-11 10:02 | Donald Nys Substation | Columbia River People's Utility District |  | Longview-Allston No. 4 115kV line | STUDY COMPLETED | WA | Columbia | LL | 2027-03-12 |  | 35 | 35 |  | Other | Other | 35 | [6 empty] | 35 |  |  | . | [5 empty] | FALSE
L0591 | 2024-02-21 16:25 | Diesel Refinery Additional Load | Clatskanie People's Utility District |  | Allston-Driscoll 115kV | STUDY | WA | Columbia | LL | 2026-02-22 |  | 38 | 38 |  | Other | Other | 38 | [6 empty] | 38 |  |  | . | [5 empty] | FALSE
G1063 | 2024-01-23 14:41 |  |  |  | Morrow Flat 230kV | STUDY | OR | Umatilla | GI | 2026-12-01 | 2026-12-31 | 100 | 100 | ERIS | Energy Storage | Battery | 65 | Photovoltaic | Solar | 110 |  |  |  | 175 |  |  | . | [5 empty] | TRUE
G1062 | 2024-01-22 10:48 |  |  |  | Longhorn 230kV | STUDY | OR | Umatilla | GI | 2026-12-31 | 2026-12-31 | 200 | 200 | ERIS | Photovoltaic | Solar | 130 | Energy Storage | Battery | 75 |  |  |  | 205 |  |  | . | [5 empty] | TRUE
L0590 | 2023-12-19 15:53 | Mapleton | Central Lincoln People's Utility District |  | BPA's Mapleton Substation | STUDY | OR | Lane | LL | 2026-12-20 | 2026-12-20 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G1059 | 2023-12-15 07:41 |  |  |  | Grizzly Substation | WITHDRAWN | OR | Jefferson | GI | 2029-12-01 | 2029-12-01 | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G1060 | 2023-12-15 07:41 |  |  |  | Grizzly Substation | WITHDRAWN | OR | Jefferson | GI | 2029-12-01 | 2029-12-01 | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G1061 | 2023-12-15 07:41 |  |  |  | Grizzly Substation | WITHDRAWN | OR | Jefferson | GI | 2029-03-01 | 2029-03-01 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | [5 empty] | FALSE
L0588 | 2023-12-14 16:40 | Bonanza 115 kV | Central Electric Cooperative, Inc. |  | BPA's Bonanza Substation (planned) | STUDY | OR | Crook | LL | 2026-12-20 | 2026-12-20 | 50 | 50 |  | Other | Other | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
L0589 | 2023-12-14 16:40 | Hidden Canyon | Central Electric Cooperative, Inc. |  | BPA's Bonanza Substation (planned) | STUDY | OR | Crook | LL | 2026-12-20 | 2026-12-20 | 23 | 23 |  | Other | Other | 23 | [6 empty] | 23 |  |  | . | [5 empty] | FALSE
G1058 | 2023-12-13 10:14 |  |  |  | Sifton Substation at 115 kV | STUDY | WA | Clark | GI | 2027-12-31 | 2027-12-31 | 20 | 20 | NRIS & ERIS | Energy Storage | Battery | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0587 | 2023-12-04 15:08 | Harrisburg Substation 115 kV-12.47 kV | Consumers Power, Inc. |  | BPA's Harrisburg Substation | STUDY | OR | Linn | LL | 2026-12-05 | 2026-12-05 | 14 | 14 |  | Other | Other | 14 | [6 empty] | 14 |  |  | . | [5 empty] | FALSE
G1047 | 2023-11-22 19:05 |  |  |  | On the Columbia-Coulee 230kV transmission line approximately 20 miles northeast of Columbia substation. | STUDY | WA | Grant | GI | 2026-12-31 | 2026-12-31 | 150 | 150 | NRIS & ERIS | Energy Storage | Battery | 150 | Photovoltaic | Solar | 150 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G1057 | 2023-11-22 13:59 |  |  |  | De Moss - Fossil No. 1 115kV line. | WITHDRAWN | OR | Gilliam | GI | 2028-12-31 | 2028-12-31 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 150 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G1055 | 2023-11-22 13:01 |  |  |  | Maupin-Redmond No 1 230 kV line | STUDY | OR | Wasco | GI | 2032-12-01 | 2032-12-01 | 1300 | 1300 | NRIS & ERIS | Energy Storage | Battery | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G1056 | 2023-11-22 13:01 |  |  |  | La Pine Substation at 230 kV | STUDY | OR | Deschutes | GI | 2030-11-01 | 2030-11-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G1053 | 2023-11-22 12:43 |  |  |  | Bonanza Substation at 500 kV | STUDY | OR | Crook | GI | 2031-12-01 | 2031-12-01 | 1300 | 1300 | NRIS & ERIS | Energy Storage | Battery | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G1054 | 2023-11-22 12:43 |  |  |  | Bonanza Substation at 500 kV | STUDY | OR | Crook | GI | 2031-12-01 | 2031-12-01 | 1300 | 1300 | NRIS & ERIS | Energy Storage | Battery | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G1051 | 2023-11-22 12:38 |  |  | Grid-Charged BESS | La Pine Substation at 230 kV | STUDY | OR | Deschutes | GI | 2030-12-02 | 2030-12-02 | 1300 | 1300 | NRIS & ERIS | Photovoltaic | Solar | 1300 | Energy Storage | Battery | 1300 |  |  |  | 2600 |  |  | . | [5 empty] | FALSE
G1052 | 2023-11-22 12:38 |  |  |  | La Pine Substation at 230 kV | STUDY | OR | Deschutes | GI | 2030-12-02 | 2030-12-02 | 1300 | 1300 | NRIS & ERIS | Photovoltaic | Solar | 1300 | Energy Storage | Battery | 1300 |  |  |  | 2600 |  |  | . | [5 empty] | FALSE
G1049 | 2023-11-22 12:33 |  |  |  | Brasada-Harney No 1 115 kV line | STUDY | OR | Harney | GI | 2029-12-03 | 2029-12-03 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G1050 | 2023-11-22 12:33 |  |  |  | LaPine Substation at 230 kV | STUDY | OR | Deschutes | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G1048 | 2023-11-22 12:24 |  |  | BESS is grid charging | Shelton-Fairmont No 4 230 kV line | STUDY | WA | Mason | GI | 2027-12-01 | 2027-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 100 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G1046 | 2023-11-21 19:04 |  |  |  | On the Cheshire-Alderwood 115kV transmission line approximately 1 mile west of Cheshire substation. | STUDY | OR | Lane | GI | 2026-12-31 | 2026-12-31 | 100 | 100 | NRIS & ERIS | Energy Storage | Battery | 100 | Photovoltaic | Solar | 100 |  |  |  | 200 |  |  | . | [5 empty] | FALSE
G1045 | 2023-11-21 19:02 |  |  |  | Roundup Substation at 230 kV | STUDY | OR | Umatilla | GI | 2026-12-31 | 2026-12-31 | 32 | 32 | NRIS & ERIS | Energy Storage | Battery | 32 | Photovoltaic | Solar | 32 |  |  |  | 64 |  |  | . | [5 empty] | FALSE
G1044 | 2023-11-21 19:01 |  |  |  | On the Cheshire-Alderwood 115kV transmission line approximately 2.75 miles west of Cheshire substation. | STUDY | OR | Lane | GI | 2026-12-31 | 2026-12-31 | 21 | 21 | NRIS & ERIS | Energy Storage | Battery | 21 | Photovoltaic | Solar | 21 |  |  |  | 42 |  |  | . | [5 empty] | FALSE
G1043 | 2023-11-21 18:59 |  |  |  | On the Rocky Ford-Coulee 230kV transmission line approximately 21 miles northeast of Rocky Ford substation. | STUDY | WA | Grant | GI | 2026-12-31 | 2026-12-31 | 150 | 150 | NRIS & ERIS | Energy Storage | Battery | 150 | Photovoltaic | Solar | 150 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G1042 | 2023-11-21 17:32 |  |  |  | Ashe-Marion No 2 500 kV line. | STUDY | OR | Sherman | GI | 2027-01-06 | 2027-01-06 | 300 | 300 | NRIS & ERIS | Energy Storage | Battery | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G1041 | 2023-11-21 17:29 |  |  |  | Ashe-Marion No 2 500 kV line. | STUDY | OR | Sherman | GI | 2027-01-06 | 2027-01-06 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | Energy Storage | Battery | 250 |  |  |  | 750 |  |  | . | [5 empty] | FALSE
G1039 | 2023-11-21 15:14 |  |  |  | Midway Substation at 230kV | STUDY | WA | Benton | GI | 2030-12-31 | 2030-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | [5 empty] | FALSE
G1040 | 2023-11-21 15:14 |  |  |  | Midway Substation at 230kV | STUDY | WA | Benton | GI | 2030-12-31 | 2030-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | [5 empty] | FALSE
G1037 | 2023-11-21 15:11 |  |  |  | Midway Substation | STUDY | WA | Benton | GI | 2030-12-31 | 2030-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 | Transition Cluster |  | . | [5 empty] | FALSE
G1038 | 2023-11-21 15:11 |  |  |  | Midway Substation | STUDY | WA | Benton | GI | 2030-12-31 | 2030-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | [5 empty] | FALSE
G1036 | 2023-11-21 13:59 |  |  |  | Big Eddy-Troutdale No 1 230 kV line | STUDY | OR | Hood River | GI | 2028-10-31 | 2028-03-12 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 234 | [6 empty] | 234 |  |  | . | [5 empty] | FALSE
G1034 | 2023-11-21 13:57 |  |  |  | Rocky Reach-Columbia No 1 230 kV line | STUDY | WA | Kittitas | GI | 2028-10-31 | 2028-10-31 | 400 | 400 | NRIS & ERIS | Wind Turbine | Wind Turbine | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G1035 | 2023-11-21 13:57 |  |  |  | Chief Joseph Substation at 230 kV | STUDY | WA | Douglas | GI | 2028-10-28 | 2028-10-28 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G1033 | 2023-11-21 13:56 |  |  |  | Targhee-Drummond No 1 115 kV line | STUDY | ID | Fremont | GI | 2028-10-28 | 2028-10-28 | 170 | 170 | NRIS & ERIS | Photovoltaic | Solar | 170 | [6 empty] | 170 |  |  | . | [5 empty] | FALSE
G1032 | 2023-11-21 13:55 |  |  |  | Grand Coulee-Hanford No 1 500 kV line | STUDY | WA | Grant | GI | 2028-10-31 | 2028-10-31 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G1031 | 2023-11-21 13:51 |  |  |  | McNary-Ross No 1 345 kV line | STUDY | WA | Klickitat | GI | 2028-05-02 | 2028-05-02 | 250 | 250 | NRIS & ERIS | Photovoltaic | Solar | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G1030 | 2023-11-21 13:42 |  |  |  | Rocky Ford-Grand Coulee No 1 230kV line | STUDY | WA | Grant | GI | 2028-12-29 | 2028-12-29 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 100 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G1029 | 2023-11-21 13:40 |  |  |  | Grandview-Red Mountain No 1 115 kV line | STUDY | WA | Benton | GI | 2027-12-31 | 2027-12-31 | 125 | 125 | NRIS & ERIS | Photovoltaic | Solar | 125 | [6 empty] | 125 |  |  | . | [5 empty] | FALSE
G1028 | 2023-11-21 12:54 |  |  |  | Stanfield Substation at 230 kV | WITHDRAWN | OR | Umatilla | GI | 2027-12-31 | 2027-12-31 | 400 | 400 | NRIS | Energy Storage | Battery | 200 | Photovoltaic | Solar | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G1027 | 2023-11-21 10:46 |  |  |  | Stanfield Substation at 230 kV | STUDY | OR | Umatilla | GI | 2028-12-01 | 2028-12-01 | 260 | 260 | NRIS & ERIS | Photovoltaic | Solar | 260 | [6 empty] | 260 |  |  | . | [5 empty] | FALSE
G1017 | 2023-11-21 10:00 |  |  |  | LaPine-Chiloquin No 1 230kV line | STUDY | OR | Klamath | GI | 2029-06-01 | 2029-06-01 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 508.5 | Energy Storage | Battery | 515.1 |  |  |  | 1023.6 |  |  | . | [5 empty] | FALSE
G1018 | 2023-11-21 10:00 |  |  |  | LaPine-Chiloquin No. 1 230kV line. | STUDY | OR | Klamath | GI | 2030-11-15 | 2030-11-15 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 508.5 | Energy Storage | Battery | 515.1 |  |  |  | 1023.6 |  |  | . | [5 empty] | FALSE
G1019 | 2023-11-21 10:00 |  |  |  | LaPine-Chiloquin No 1 230kV line. | STUDY | OR | Klamath | GI | 2030-11-15 | 2030-11-15 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 508.5 | Energy Storage | Battery | 515.1 |  |  |  | 1023.6 |  |  | . | [5 empty] | FALSE
G1020 | 2023-11-21 10:00 |  |  |  | LaPine-Chiloquin No 1 230kV line. | STUDY | OR | Klamath | GI | 2030-11-15 | 2030-11-15 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 508.5 | Energy Storage | Battery | 515.1 |  |  |  | 1023.6 |  |  | . | [5 empty] | FALSE
G1021 | 2023-11-21 10:00 |  |  |  | Lexington Substation | STUDY | WA | Cowlitz | GI | 2028-12-01 | 2028-12-01 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 530.4 | [6 empty] | 530.4 |  |  | . | [5 empty] | FALSE
G1022 | 2023-11-21 10:00 |  |  |  | Lexington Substation | STUDY | WA | Cowlitz | GI | 2030-11-15 | 2030-11-15 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 530.4 | [6 empty] | 530.4 |  |  | . | [5 empty] | FALSE
G1023 | 2023-11-21 10:00 |  |  |  | Ponderosa Substation | STUDY | OR | Lake | GI | 2030-06-01 | 2030-06-01 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 508.5 | Energy Storage | Battery | 515.1 |  |  |  | 1023.6 |  |  | . | [5 empty] | FALSE
G1024 | 2023-11-21 10:00 |  |  |  | Ponderosa Substation | STUDY | OR | Lake | GI | 2030-11-15 | 2030-11-15 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 508.5 | Energy Storage | Battery | 515.1 |  |  |  | 1023.6 |  |  | . | [5 empty] | FALSE
G1025 | 2023-11-21 10:00 |  |  |  | Columbia Substation | STUDY | WA | Douglas | GI | 2029-12-01 | 2029-12-01 | 250 | 250 | NRIS & ERIS | Wind Turbine | Wind Turbine | 530.4 | Photovoltaic | Solar | 508.5 | Energy Storage | Battery | 515.1 | 1554 | Transition Cluster |  | . | [5 empty] | FALSE
G1026 | 2023-11-21 10:00 |  |  |  | Schultz Substation | WITHDRAWN | WA | Kittitas | GI | 2029-12-01 | 2029-12-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 315.6 | [6 empty] | 315.6 |  |  | . | [5 empty] | FALSE
G1016 | 2023-11-21 09:37 |  |  |  | Wautoma-Knight No 1 500kV line | STUDY | WA | Klickitat | GI | 2029-12-31 | 2029-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G1014 | 2023-11-21 09:34 |  |  |  | Covington Substation | STUDY | WA | King | GI | 2029-12-31 | 2029-12-31 | 250 | 250 | NRIS | Energy Storage | Battery | 250 | [6 empty] | 250 | Transition Cluster |  | . | [5 empty] | FALSE
G1015 | 2023-11-21 09:34 |  |  |  | Lower Monumental-Hanford No 1 500kV line. | STUDY | WA | Benton | GI | 2029-12-31 | 2029-12-31 | 500 | 500 | NRIS | Photovoltaic | Solar | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G1013 | 2023-11-20 19:25 |  |  |  | Combine Hills II tap to Walla Walla-Pendleton No 1 69 kV line | STUDY | OR | Umatilla | GI | 2030-12-31 | 2030-12-31 | 250.1 | 250.1 | NRIS & ERIS | Wind Turbine | Wind Turbine | 250.1 | [6 empty] | 250.1 |  |  | . | [5 empty] | FALSE
G1012 | 2023-11-20 19:17 |  |  |  | Combine Hills II tap to Walla Walla-Pendleton No 1 69 kV line | STUDY | OR | Umatilla | GI | 2030-01-31 | 2030-01-31 | 67 | 67 | NRIS & ERIS | Wind Turbine | Wind Turbine | 67 | [6 empty] | 67 |  |  | . | [5 empty] | FALSE
G1011 | 2023-11-20 11:36 |  |  |  | TBD | WITHDRAWN | OR | Lake | GI | 2027-12-31 | 2027-12-31 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | Energy Storage | Battery | 100 |  |  |  | 200 |  |  | . | [5 empty] | FALSE
G1009 | 2023-11-20 09:36 |  |  |  | Alfalfa Substation at 230kV | STUDY | WA | Yakima | GI | 2027-12-31 | 2027-12-31 | 600 | 600 | NRIS & ERIS | Energy Storage | Pumped-Storage Hydro | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G1010 | 2023-11-20 09:36 |  |  |  | Alfalfa Substation at 230kV | STUDY | WA | Yakima | GI | 2027-12-31 | 2027-12-31 | 70 | 70 | NRIS & ERIS | Photovoltaic | Solar | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G1008 | 2023-11-17 17:17 |  |  | 46 MW added to an existing 240 MW project (G0129). | Alcoa 115kV Substation | STUDY | WA | Clark | GI | 2024-06-15 | 2027-01-01 | 46 | 46 | NRIS | Combined Cycle | Natural Gas | 286 | [6 empty] | 286 |  |  | . |  |  |  |  | Available | FALSE
G1007 | 2023-11-17 11:47 |  |  |  | Paul Substation | STUDY | WA | Lewis | GI | 2030-10-30 | 2030-10-30 | 300 | 300 | NRIS & ERIS | Energy Storage | Battery | 300 | Wind Turbine | Wind Turbine | 300 |  |  |  | 600 | Transition Cluster |  | . | [5 empty] | FALSE
G1006 | 2023-11-17 11:13 |  |  |  | Cattle Creek Switching Station | WITHDRAWN | ID | Bonneville | GI | 2025-01-02 | 2027-01-01 | 43 | 43 | NRIS & ERIS | Wind Turbine | Wind Turbine | 43 | [6 empty] | 43 |  |  | . | [5 empty] | FALSE
G1005 | 2023-11-16 13:32 |  |  |  | McNary-John Day No 2 500kV line | WITHDRAWN | WA | Klickitat | GI | 2028-04-14 | 2028-04-15 | 225 | 225 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | Photovoltaic | Solar | 90 | Energy Storage | Battery | 90 | 380 |  |  | . | [5 empty] | FALSE
G1004 | 2023-11-16 11:02 |  |  |  | Connell Tap on the Benton-Scooteney line. | STUDY | WA | Franklin | GI | 2025-12-31 | 2027-01-01 | 10 | 10 | NRIS | Photovoltaic | Solar | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G1003 | 2023-11-16 11:00 |  |  |  | Hatton tap to Connell tap to Benton-Scooteney No 1 115kV line | STUDY | WA | Adams | GI | 2025-12-31 | 2027-01-01 | 3 | 3 | NRIS & ERIS | Photovoltaic | Solar | 3 | [6 empty] | 3 |  |  | . |  |  |  |  | Available | FALSE
G1001 | 2023-11-16 09:02 |  |  |  | Potholes - Grand Coulee No 1 230kV line. | STUDY | WA | Grant | GI | 2029-12-03 | 2029-12-01 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G1002 | 2023-11-16 09:02 |  |  |  | Ashe - Marion No 2 500kV line. | STUDY | OR | Sherman | GI | 2029-12-03 | 2029-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0586 | 2023-11-16 08:12 | Longhorn 230 kV Substation | Umatilla Electric Cooperative |  | Longhorn Substation | STUDY | OR | Linn | LL | 2025-01-31 | 2025-01-31 | 750 | 750 |  | Other | Other | 750 | [6 empty] | 750 |  |  | . | [5 empty] | FALSE
G1000 | 2023-11-15 14:07 |  |  |  | McNary Substation, or Longhorn Substation | STUDY | OR | Morrow | GI | 2029-12-31 | 2029-12-31 | 440 | 440 | NRIS & ERIS | Photovoltaic | Solar | 440 | Energy Storage | Battery | 220 |  |  |  | 660 |  |  | . | [5 empty] | FALSE
G0998 | 2023-11-15 10:55 |  |  |  | Ashe Substation at 230kV and 500 kV | STUDY | WA | Benton | GI | 2030-12-31 | 2030-12-31 | 1120 | 1120 | NRIS | Steam Turbine | Nuclear | 1120 | [6 empty] | 1120 |  |  | . | [5 empty] | FALSE
L0585 | 2023-11-08 15:37 | McNary 230 kV Substation | Umatilla Electric Cooperative |  | McNary Substation | STUDY | OR | Linn | LL | 2024-01-31 | 2024-01-31 | 1250 | 1250 |  | Other | Other | 1250 | [6 empty] | 1250 |  |  | . | [5 empty] | FALSE
G0997 | 2023-11-07 12:50 |  |  |  | Bandon – Rogue No 1 115 kV line | STUDY | OR | Curry | GI | 2028-09-01 | 2028-09-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0996 | 2023-11-06 16:55 |  |  |  | Grand Coulee-Schultz No 1 500kV line. | STUDY | OR | Douglas | GI | 2029-12-01 | 2029-12-01 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0994 | 2023-11-06 14:18 |  |  |  | Buckley Substation at 500 kV | STUDY | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 277 | 277 | NRIS & ERIS | Wind Turbine | Wind Turbine | 277 | [6 empty] | 277 |  |  | . | [5 empty] | FALSE
G0995 | 2023-11-06 14:18 |  |  |  | Buckley Substation at 500 kV | STUDY | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 400 | 400 | NRIS & ERIS | Wind Turbine | Wind Turbine | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0993 | 2023-11-06 12:23 |  |  |  | Grand Coulee-Bell | STUDY | WA | Spokane | GI | 2028-09-01 | 2028-09-01 | 300 | 300 | NRIS & ERIS | Energy Storage | Battery | 100 | Photovoltaic | Solar | 200 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G0992 | 2023-11-06 11:17 |  |  |  | Monroe-Custer No 1 500 kV line | STUDY | WA | Skagit | GI | 2028-09-01 | 2028-09-01 | 131 | 131 | NRIS & ERIS | Wind Turbine | Wind Turbine | 131 | [6 empty] | 131 |  |  | . | [5 empty] | FALSE
G0990 | 2023-11-06 10:35 |  |  |  | Fairview-Rouge No 1 230 kV line | STUDY | OR | Curry | GI | 2028-09-01 | 2028-09-01 | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0991 | 2023-11-06 10:35 |  |  |  | Fairview-Rouge No 1 230 kV line | STUDY | OR | Curry | GI | 2028-09-01 | 2028-09-01 | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0989 | 2023-11-06 08:52 |  |  |  | Buckley 230kV | STUDY | OR | Gilliam | GI | 2026-12-31 | 2027-12-31 | 275 | 275 | NRIS & ERIS | Photovoltaic | Solar | 275 | Energy Storage | Battery | 275 |  |  |  | 550 |  |  | . | [5 empty] | FALSE
G0987 | 2023-11-06 08:19 |  |  |  | Grand Coulee-Bell No 6 500 kV line | STUDY | WA | Spokane | GI | 2028-09-01 | 2028-09-01 | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0988 | 2023-11-06 08:19 |  |  |  | Grand Coulee-Bell No 6 500 kV line | STUDY | WA | Spokane | GI | 2028-09-01 | 2028-09-01 | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0986 | 2023-11-03 14:56 |  |  |  | Primary: Sedro-Woolley - Bellingham No 1 230kV line; Secondary: Murray - Custer No 1 230kV line. | STUDY | WA | Skagit | GI | 2029-12-30 | 2029-12-31 | 150 | 150 |  | Wind Turbine | Wind Turbine | 150 | Energy Storage | Battery | 150 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G0985 | 2023-11-03 14:00 |  |  |  | Creston Substation, Configuration: Loop into BPA station. Grand Coulee Creston No 1 115kV line Alternate: Wagner | STUDY | WA | Lincoln | GI | 2027-12-31 | 2027-12-31 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 150 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G0984 | 2023-11-03 13:50 |  |  |  | Hampton Substation | WITHDRAWN | OR | Deschutes | GI | 2028-12-31 | 2028-12-31 | 60 | 60 | NRIS & ERIS | Photovoltaic | Solar | 60 | Energy Storage | Battery | 60 |  |  |  | 120 |  |  | . | [5 empty] | FALSE
G0980 | 2023-11-03 11:36 |  |  |  | John Day Substation at 500 kV | STUDY | OR | Sherman | GI | 2028-09-01 | 2028-09-01 | 191 | 191 | NRIS & ERIS | Wind Turbine | Wind Turbine | 191 | [6 empty] | 191 |  |  | . | [5 empty] | FALSE
G0981 | 2023-11-03 11:36 |  |  |  | John Day Substation at 500 kV | STUDY | OR | Sherman | GI | 2028-09-01 | 2028-09-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0982 | 2023-11-03 11:36 |  |  |  | John Day Substation at 500 kV | STUDY | OR | Sherman | GI | 2028-09-01 | 2028-09-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0983 | 2023-11-03 11:36 |  |  |  | John Day Substation at 500 kV | STUDY | OR | Sherman | GI | 2028-09-01 | 2028-09-01 | 1200 | 1200 | NRIS & ERIS | Photovoltaic | Solar | 800 | Energy Storage | Battery | 400 |  |  |  | 1200 |  |  | . | [5 empty] | FALSE
G0979 | 2023-11-03 09:13 |  |  |  | Rock Creek Substation | STUDY | WA | Klickitat | GI | 2029-12-03 | 2029-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0978 | 2023-10-27 13:19 |  |  |  | Biglow Canyon – John Day No 1 230 kV line | STUDY | OR | Sherman | GI | 2026-01-02 | 2026-01-01 | 450 | 450 | ERIS | Photovoltaic | Solar | 250 | Energy Storage | Battery | 250 |  |  |  | 500 |  |  | . | [5 empty] | TRUE
G0977 | 2023-10-27 12:31 |  |  |  | Bonanza Substation | WITHDRAWN | OR | Crook | GI | 2030-01-07 | 2030-01-06 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0584 | 2023-10-24 16:43 | Coos Curry Tie | PacifiCorp |  | BPA's Gold Beach 115 kV Substation | STUDY | OR | Linn | LL | 2026-10-24 | 2034-12-31 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0976 | 2023-10-17 11:11 |  |  |  | Lexington 115kV | WITHDRAWN | WA | Cowlitz | GI | 2024-12-01 | 2025-06-01 | 9 | 9 | NRIS & ERIS | Reciprocating Engine | Biofuel | 8.8 | [6 empty] | 8.8 |  |  | . | [5 empty] | FALSE
G0975 | 2023-10-16 16:56 |  |  |  | Walla Walla-Pendleton 69kV line | STUDY | OR | Umatilla | GI | 2023-12-01 | 2027-01-01 | 19 | 19 | ERIS | Wind Turbine | Wind Turbine | 19 | [6 empty] | 19 |  |  | . | [5 empty] | TRUE
G0972 | 2023-10-14 07:42 |  |  |  | Fairview-Rogue No 1 230kV line. | STUDY | OR | Curry | GI | 2029-12-01 | 2029-12-01 | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0973 | 2023-10-14 07:42 |  |  |  | Olympia-Shelton No 3 230kV line. | STUDY | WA | Mason | GI | 2029-12-01 | 2029-12-01 | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 | Transition Cluster |  | . | [5 empty] | FALSE
G0974 | 2023-10-14 07:42 |  |  |  | Parkdale Substation | STUDY | OR | Wasco | GI | 2029-12-01 | 2029-12-01 | 250 | 250 | ERIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0969 | 2023-10-13 16:47 |  |  |  | Salem - Albany No 1 115kV line. | STUDY | OR | Linn or Marion | GI | 2028-12-01 | 2028-12-01 | 80 | 80 |  | Photovoltaic | Solar | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . | [5 empty] | FALSE
G0970 | 2023-10-13 16:47 |  |  | grid-charging BESS | Salem-Albany No 2 115kV line. | STUDY | OR | Polk or Benton | GI | 2028-12-01 |  | 80 | 80 | NRIS & ERIS | Reciprocating Engine | Biofuel | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . | [5 empty] | FALSE
G0971 | 2023-10-13 16:47 |  |  |  | Eugene-Alderwood No 1 115kV line. | STUDY | OR | Lane | GI | 2028-12-01 | 2028-12-01 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . | [5 empty] | FALSE
G0968 | 2023-10-13 14:36 |  |  | 799.2 kW request | Evans Substation | STUDY | WA | Clark | GI | 2023-12-01 | 2024-06-03 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0967 | 2023-10-13 10:22 |  |  |  | Swan Valley-Goshen No 1 161kV line. | WITHDRAWN | ID | Bonneville | GI | 2027-10-10 | 2027-10-10 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 150 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
L0583 | 2023-10-12 13:37 | Lochner Substation | Consumers Power, Inc. |  | Albany-Lebanon 115kV line | STUDY | OR | Linn | LL | 2026-10-13 | 2026-10-13 | 500 | 500 |  | Other | Other | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G0966 | 2023-10-11 12:50 |  |  |  | Stanfield Substation at 230 kV | STUDY | OR | Umatilla | GI | 2032-12-01 | 2032-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G0960 | 2023-10-11 12:49 |  |  |  | Longhorn Substation at 230 kV | STUDY | OR | Morrow | GI | 2026-12-01 | 2027-01-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G0961 | 2023-10-11 12:49 |  |  |  | McNary Substation at 230 kV | STUDY | OR | Umatilla | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0962 | 2023-10-11 12:49 |  |  |  | Longhorn Substation at 230 kV | STUDY | OR | Morrow | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G0963 | 2023-10-11 12:49 |  |  |  | Longhorn Substation at 230 kV | STUDY | OR | Morrow | GI | 2030-12-02 | 2030-12-02 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0964 | 2023-10-11 12:49 |  |  |  | Stanfield Substation at 230 kV | STUDY | OR | Umatilla | GI | 2030-12-02 | 2030-12-02 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G0965 | 2023-10-11 12:49 |  |  |  | Stanfield Substation at 230 kV | STUDY | OR | Umatilla | GI | 2032-12-01 | 2032-12-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0959 | 2023-10-11 12:48 |  |  |  | McNary Substation at 230 kV | STUDY | OR | Umatilla | GI | 2026-12-01 | 2027-01-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0955 | 2023-10-06 16:29 |  |  |  | TBD | STUDY | WA | Lincoln | GI | 2026-09-01 | 2027-01-01 | 350 | 350 | NRIS & ERIS | Wind Turbine | Wind Turbine | 350 | [6 empty] | 350 |  |  | . | [5 empty] | FALSE
G0956 | 2023-10-06 16:29 |  |  |  | TBD | STUDY | ID | Benewah | GI | 2026-09-01 | 2027-01-01 | 400 | 400 | ERIS | Wind Turbine | Wind Turbine | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0958 | 2023-10-06 14:08 |  |  |  | John Day - Marion No 1 500kV line | STUDY | OR | Wasco | GI | 2027-06-01 | 2027-06-01 | 400 | 400 | NRIS & ERIS | Wind Turbine | Wind Turbine | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0957 | 2023-10-06 05:13 |  |  |  | Benton-White Bluffs No 1 line or White Bluffs-Richland No 1 line | STUDY | WA | Benton | GI | 2027-07-01 | 2027-07-01 | 10 | 10 | ERIS | Steam Turbine | Solar | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0954 | 2023-10-05 16:25 |  |  |  | TBD | STUDY | WA | Lincoln | GI | 2026-09-01 | 2027-01-01 | 350 | 350 | NRIS & ERIS | Wind Turbine | Wind Turbine | 350 | [6 empty] | 350 |  |  | . | [5 empty] | FALSE
G0953 | 2023-10-05 16:22 |  |  |  | TBD | STUDY | WA | Lincoln | GI | 2026-09-01 | 2027-01-01 | 600 | 600 | ERIS | Wind Turbine | Wind Turbine | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0952 | 2023-10-05 13:26 |  |  |  | John Day Substation at 500 kV | STUDY | OR | Gilliam | GI | 2029-06-01 | 2029-06-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0951 | 2023-10-05 13:25 |  |  |  | John Day Substation at 500 kV | STUDY | OR | Gilliam | GI | 2029-06-01 | 2029-06-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0950 | 2023-10-05 13:24 |  |  |  | John Day Substation at 500 kV | STUDY | OR | Gilliam | GI | 2029-06-01 | 2029-06-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0949 | 2023-10-05 13:23 |  |  | Grid-Charged BESS | John Day Substation at 500 kV | STUDY | OR | Gilliam | GI | 2029-06-01 | 2029-06-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0948 | 2023-10-05 13:22 |  |  |  | John Day 500kV substation | STUDY | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0947 | 2023-10-05 13:21 |  |  |  | John Day 500kV substation | STUDY | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0946 | 2023-10-05 13:20 |  |  |  | John Day 500kV substation | STUDY | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0945 | 2023-10-04 06:23 |  |  |  | Goshen-Drummond No 1 161kV line | STUDY | ID | Fremont | GI | 2026-06-01 | 2027-01-01 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 52 |  |  |  | 202 |  |  | . | [5 empty] | FALSE
G0944 | 2023-10-03 09:28 |  |  |  | Six Mile Substation; Secondary: Boardman-Alkali No 1 115kV line | STUDY | OR | Morrow | GI | 2026-09-01 | 2027-01-01 | 261 | 261 | NRIS & ERIS | Photovoltaic | Solar | 261 | [6 empty] | 261 | Transition Cluster |  | . | [5 empty] | FALSE
L0582 | 2023-10-02 08:35 | CGS Distribution Substation | Energy Northwest (CGS) |  | Benton-White Bluffs No 2 115 kV line | STUDY | WA | Benton | LL | 2028-07-07 | 2026-10-02 | 70 | 70 |  | Other | Other | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G0943 | 2023-10-02 08:12 |  |  |  | Snohomish | STUDY | WA | Snohomish | GI | 2024-09-30 | 2024-09-30 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0942 | 2023-09-29 14:57 |  |  |  | Olympia Substation | STUDY | WA | Thurston | GI | 2026-12-31 | 2026-12-31 | 20 | 20 | ERIS | Energy Storage | Battery | 20 | [6 empty] | 20 |  |  | . | Available |  |  |  |  | FALSE
G0941 | 2023-09-27 07:55 |  |  |  | Ashe – Marion No 2 500 kV line | STUDY | OR | Gilliam | GI | 2028-12-28 | 2028-12-28 | 488 | 488 | NRIS & ERIS | Energy Storage | Battery | 488 | [6 empty] | 488 |  |  | . | [5 empty] | FALSE
G0940 | 2023-09-22 18:52 |  |  |  | Ashe-Marion No 2 500kV line. | WITHDRAWN | OR | Gilliam | GI | 2027-12-15 | 2027-12-15 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 150 |  |  |  | 450 |  |  | . | [5 empty] | FALSE
G0939 | 2023-09-22 18:47 |  |  |  | Ashe-Marion No 2 500kV line. | WITHDRAWN | OR | Gilliam | GI | 2027-12-15 | 2027-12-15 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 200 |  |  |  | 600 |  |  | . | [5 empty] | FALSE
G0938 | 2023-09-22 10:01 |  |  |  | Webber Canyon Substation | STUDY | WA | Benton | GI | 2027-01-06 | 2027-01-06 | 300 | 300 | NRIS & ERIS | Energy Storage | Battery | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0937 | 2023-09-18 12:06 |  |  |  | Chemoweth Substation; Alternates: Quenett Creek Substation & Chenoweth-Goldendale No 1 115kV line. | STUDY | OR | Wasco | GI | 2025-10-01 | 2027-01-01 | 117 | 117 | ERIS | Photovoltaic | Solar | 117 | [6 empty] | 117 |  |  | . | [5 empty] | FALSE
G0936 | 2023-09-18 07:52 |  |  |  | Rock Creek Substation | STUDY | WA | Klickitat | GI | 2025-09-01 | 2027-01-01 | 150 | 150 |  | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . |  |  |  |  | Available | FALSE | TRUE
G0935 | 2023-09-13 15:17 |  |  |  | Central Ferry-Lower Monumental No 1 500 kV Line | STUDY | WA | Walla Walla | GI | 2027-09-15 | 2027-09-15 | 225 | 225 | NRIS & ERIS | Photovoltaic | Solar | 225 | [6 empty] | 225 |  |  | . | [5 empty] | FALSE
G0934 | 2023-09-08 09:12 |  |  |  | Hat Rock 115kV | STUDY | OR | Umatilla | GI | 2025-06-02 | 2027-01-01 | 75 | 75 | ERIS | Photovoltaic | Solar | 75 | Energy Storage | Battery | 75 |  |  |  | 150 |  |  | . | [5 empty] | FALSE
L0581 | 2023-09-08 08:06 | New Midway Substation | Fall River Rural Electric Cooperative, Inc. |  | Targhee tap to Swan Valley-Teton No 1 115kV line | STUDY | ID | Teton | LL | 2026-09-11 | 2026-09-11 | 14.2 | 14.2 |  | Other | Other | 14.2 | [6 empty] | 14.2 |  |  | . | [5 empty] | FALSE
G0933 | 2023-09-07 14:03 |  |  |  | McNary-John Day No 2 500kV line | STUDY | WA | Benton | GI | 2029-12-31 | 2029-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | [5 empty] | FALSE
G0932 | 2023-09-07 14:02 |  |  |  | McNary-John Day No 2 500kV line | STUDY | WA | Benton | GI | 2029-12-31 | 2029-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | [5 empty] | FALSE
G0931 | 2023-09-07 11:03 |  |  |  | Buckley Substation | STUDY | OR | Sherman | GI | 2028-12-01 |  | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . | [5 empty] | FALSE
G0930 | 2023-09-07 10:03 |  |  |  | Ashe Substation | WITHDRAWN | WA | Benton | GI | 2030-09-01 | 2030-09-01 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 150 |  |  |  | 650 |  |  | . | [5 empty] | FALSE
G0929 | 2023-09-07 10:02 |  |  |  | Boyd Ridge Substation. Configuration: through a new 230 kV bay for the developer's generation tie line. | WITHDRAWN | OR | Deschutes | GI | 2026-06-01 | 2027-01-01 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 150 |  |  |  | 300 |  |  | . | [5 empty] | FALSE
G0928 | 2023-09-07 10:00 |  |  |  | Ashe Substation | WITHDRAWN | WA | Benton | GI | 2030-09-01 | 2030-09-01 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 250 |  |  |  | 750 |  |  | . | [5 empty] | FALSE
G0927 | 2023-09-07 09:58 |  |  |  | Ashe Substation | WITHDRAWN | WA | Benton | GI | 2030-09-01 | 2030-09-01 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 250 |  |  |  | 750 |  |  | . | [5 empty] | FALSE
G0926 | 2023-09-07 09:56 |  |  |  | Ashe Substation | WITHDRAWN | WA | Benton | GI | 2030-09-01 | 2030-09-01 | 500 | 500 |  | Photovoltaic | Solar | 500 | Energy Storage | Battery | 250 |  |  |  | 750 |  |  | . | [5 empty] | FALSE
G0925 | 2023-09-05 12:03 |  |  |  | Lower Monumental – Little Goose No 1 500 kV line. Alternates: Lower Monumental – Little Goose No 2 500 kV line; Little Goose – Central Ferry No 2 500 kV line | STUDY | WA | Walla Walla | GI | 2027-09-15 | 2027-09-15 | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | Photovoltaic | Solar | 100 | Energy Storage | Battery | 100 | 300 | Transition Cluster |  | . | [5 empty] | FALSE
G0924 | 2023-09-05 11:44 |  |  |  | Lower Monumental – Little Goose No 1 500 kV line. Alternates: Lower Monumental – Little Goose No 2 500 kV line; Little Goose – Central Ferry No 2 500 kV line | STUDY | WA | Walla Walla | GI | 2027-09-15 | 2027-09-15 | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | Photovoltaic | Solar | 100 | Energy Storage | Battery | 100 | 300 |  |  | . | [5 empty] | FALSE
G0923 | 2023-09-05 11:37 |  |  |  | Lower Monumental – Little Goose No 1 500 kV line. Alternates: Lower Monumental – Little Goose No 2 500 kV line; Little Goose – Central Ferry No 2 500 kV line | STUDY | WA | Walla Walla | GI | 2027-09-15 | 2027-09-15 | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | Photovoltaic | Solar | 100 | Energy Storage | Battery | 100 | 300 | Transition Cluster |  | . | [5 empty] | FALSE
G0922 | 2023-09-05 08:55 |  |  |  | Longview Substation at 230kV | STUDY | WA | Cowlitz | GI | 2026-12-01 | 2026-12-01 | 100 | 100 | NRIS & ERIS | Energy Storage | Battery | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0921 | 2023-09-01 11:23 |  |  |  | Chehalis - Covington No 1 230kV line. | STUDY | WA | Thurston | GI | 2030-10-30 | 2030-10-30 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | Available |  |  |  |  | FALSE
L0580 | 2023-08-30 06:52 | Junction City Substation | Blachly-Lane Electric Cooperative |  | Albany-Eugene No 115 kV line | ENERGIZED | OR | Linn | LL | 2026-08-31 |  | 2 | 2 |  | Other | Other | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0920 | 2023-08-28 12:32 |  |  |  | Ashe-Slatt No 1 500kV line | STUDY | WA | Benton | GI | 2027-01-06 | 2027-01-06 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 300 |  |  |  | 800 |  |  | . | [5 empty] | FALSE
G0919 | 2023-08-24 09:40 |  |  |  | Ashe 500 kV Substation | STUDY | WA | Benton | GI | 2031-06-02 | 2031-06-02 | 270 | 270 | NRIS | Steam Turbine | Nuclear | 270 | [6 empty] | 270 |  |  | . | [5 empty] | FALSE
G0918 | 2023-08-24 07:44 |  |  |  | Santiam-Alvey 1&2 No 1 230kV line | STUDY | OR | Lane | GI | 2029-10-31 | 2029-10-31 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0579 | 2023-08-24 07:34 | Tower Road Project | Umatilla Electric Cooperative |  | Boardman-Alkali No. 1 115kV line | STUDY | OR | Morrow | LL | 2025-01-31 | 2026-08-24 | 20 | 20 |  | Other | Other | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0578 | 2023-08-22 12:54 | PNW Metal Recycling | Public Utility District No. 1 of Cowlitz County |  | Cowlitz Substation | ENERGIZED | WA | Cowlitz | LL | 2024-04-01 | 2023-09-11 | 6.8 | 6.8 |  | Other | Other | 6.8 | [6 empty] | 6.8 |  |  | . | [5 empty] | FALSE
L0574 | 2023-08-11 11:06 | Ft Churchill-Captain Jack 525 kV line | Sierra Pacific Power Company dba NV Energy |  | Captain Jack Substation | STUDY | OR | Morrow | LL | 2031-01-02 | 2026-08-14 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0573 | 2023-08-10 17:22 | Parker Substation | Blachly-Lane Electric Cooperative |  | Eugene-Alderwood 115kV line | ENERGIZED | OR | Morrow | LL | 2024-12-31 | 2024-12-31 | 13.2 | 13.2 |  | Other | Other | 13.2 | [6 empty] | 13.2 |  |  | . | [5 empty] | FALSE
L0575 | 2023-08-04 11:43 | Forest Grove Substation | City of Forest Grove |  | Keeler-Forest Grove No 1 115kV line Keeler-Forest Grove No 2 115kV line | ENERGIZED | OR | Morrow | LL | 2026-08-22 | 2026-08-22 | 5 | 5 |  | Other | Other | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
L0576 | 2023-08-04 11:43 | Filbert Substation | City of Forest Grove |  | Forest Grove-McMinnville No 1 115kV line | ENERGIZED | OR | Morrow | LL | 2026-08-22 | 2026-08-22 | 5 | 5 |  | Other | Other | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
L0577 | 2023-08-04 11:43 | Thatcher Junction Substation | City of Forest Grove |  | Forest Grove-McMinnville No 1 115kV line | ENERGIZED | OR | Morrow | LL | 2026-08-22 |  | 2 | 2 |  | Other | Other | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0917 | 2023-08-02 15:55 |  |  |  | Jones Canyon Substation | STUDY | OR | Gilliam | GI | 2025-09-02 | 2027-01-01 | 91 | 91 | NRIS & ERIS | Wind Turbine | Wind Turbine | 90.3 | [6 empty] | 90.3 |  |  | . | [5 empty] | FALSE | TRUE
L0572 | 2023-07-27 12:36 | GLP Data Center | Benton Rural Electric Association |  | McNary-John Day No 2 500kV line | STUDY | WA | Benton | LL | 2026-02-28 | 2026-02-28 | 600 | 600 |  | Other | Other | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0915 | 2023-07-24 10:24 |  |  |  | Grand Coulee 500 kV Switchyard | STUDY | WA | Douglas | GI | 2028-12-01 | 2028-12-01 | 500 | 500 | NRIS & ERIS | Energy Storage | Battery | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G0916 | 2023-07-24 10:24 |  |  |  | Grand Coulee 500 kV Switchyard | STUDY | WA | Douglas | GI | 2028-12-01 | 2028-12-01 | 500 | 500 | NRIS & ERIS | Energy Storage | Battery | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G0914 | 2023-07-24 10:23 |  |  |  | Grand Coulee 500 kV Switchyard | STUDY | WA | Douglas | GI | 2028-12-01 | 2028-12-01 | 1000 | 1000 | NRIS & ERIS | Energy Storage | Battery | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
G0910 | 2023-07-18 14:32 |  |  | Grid-Charged BESS | LaPine Substation | STUDY | OR | Deschutes | GI | 2030-11-01 | 2030-11-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0909 | 2023-07-18 14:31 |  |  | Grid-Charged BESS | LaPine Substation | STUDY | OR | Deschutes | GI | 2028-11-01 | 2028-11-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0911 | 2023-07-18 14:30 |  |  | Grid-Charged BESS | LaPine 230kV Substation | STUDY | OR | Deschutes, Klamath or Lake | GI | 2032-12-01 | 2032-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0912 | 2023-07-18 14:30 |  |  | Grid-Charged BESS | LaPine 230kV Substation | STUDY | OR | Deschutes, Klamath or Lake | GI | 2033-11-01 | 2033-11-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0913 | 2023-07-18 14:30 |  |  | Grid-Charged BESS | LaPine 230kV Substation | STUDY | OR | Deschutes, Klamath or Lake | GI | 2034-11-01 | 2034-11-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0908 | 2023-07-17 17:53 |  |  |  | Longhorn Substation | STUDY | OR | Umatilla | GI | 2025-12-31 | 2027-01-01 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 200 |  |  |  | 500 |  |  | . | [5 empty] | FALSE
L0571 | 2023-07-17 10:07 | Forest Grove Substation Transmission Tie Switch Addition | City of Forest Grove |  | Forest Grove Substation | WITHDRAWN | OR | Washington | LL | 2026-07-17 | 2026-07-17 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0570 | 2023-07-14 07:51 | Boyer Ring Bus | PacifiCorp |  | BPA’s Grand Ronde-Boyer No 1 115kV line | STUDY | OR | Washington | LL | 2026-07-15 | 2026-07-15 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0569 | 2023-07-12 13:36 | Gardiner Substation 13.8 kV to 12.47 kV | Central Lincoln People's Utility District |  | Gardiner Substation | STUDY | OR | Washington | LL | 2026-07-13 | 2026-07-13 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0568 | 2023-07-10 08:51 | Fortescue | Public Utility District No. 1 of Lewis County |  | Chehalis-Covington No. 1 230 kV line | STUDY | WA | Lewis | LL | 2026-07-10 | 2028-09-30 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0905 | 2023-06-30 16:54 |  |  |  | Santiam-Chemawa No 1 230kV line. | STUDY | OR | Linn or Marion | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Reciprocating Engine | Biofuel | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0906 | 2023-06-30 16:54 |  |  |  | Albany-Burnt Woods No 1 115kV line. | STUDY | OR | Linn | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0907 | 2023-06-30 16:54 |  |  |  | Santiam-Toledo No 1 230kV line | STUDY | OR | Linn | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0902 | 2023-06-30 16:53 |  |  |  | Carlton Substation 115kV | STUDY | OR | Linn or Lane | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0903 | 2023-06-30 16:53 |  |  |  | Carlton Substation 115kV | STUDY | OR | Linn or Lane | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0904 | 2023-06-30 16:53 |  |  | Grid-Charged BESS | Santiam-Chemawa No 1 230kV line | STUDY | OR | Linn or Marion | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Reciprocating Engine | Biofuel | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0896 | 2023-06-30 16:52 |  |  |  | Santiam-Alvey 1&2 No 2 230 kV line | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0897 | 2023-06-30 16:52 |  |  |  | Santiam-Alvey 1&2 No 2 230 kV line | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0898 | 2023-06-30 16:52 |  |  |  | Santiam-Albany No 1 230kV line. | STUDY | OR | Linn | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0899 | 2023-06-30 16:52 |  |  |  | Santiam-Albany No. 1 230kV line. | STUDY | OR | Linn | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0900 | 2023-06-30 16:52 |  |  |  | Santiam-Alvey 1&2 No 2 230kV line; Secondary: Santiam-Alvey 1&2 No 1 230kV line | STUDY | OR | Linn or Lane | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0901 | 2023-06-30 16:52 |  |  |  | Santiam-Alvey 1&2 No 2 230kV line; Secondary: Santiam-Alvey 1&2 No 1 230kV line | STUDY | OR | Linn or Lane | GI | 2030-12-01 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0893 | 2023-06-30 16:51 |  |  |  | Santiam 230kV Substation | STUDY | OR | Linn | GI | 2030-12-02 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0894 | 2023-06-30 16:51 |  |  |  | Santiam 230kV Substation | STUDY | OR | Linn | GI | 2030-12-02 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0895 | 2023-06-30 16:51 |  |  |  | Santiam 230kV Substation | STUDY | OR | Linn | GI | 2030-12-02 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0892 | 2023-06-30 16:50 |  |  |  | Santiam 230kV Substation | STUDY | OR | Linn | GI | 2030-12-02 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0890 | 2023-06-30 16:49 |  |  |  | Lane Substation at 230 kV | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-02 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0891 | 2023-06-30 16:49 |  |  |  | Lane Substation at 230 kV | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-02 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0889 | 2023-06-30 16:34 |  |  |  | Lane Substation at 230 kV | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-02 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0888 | 2023-06-30 16:19 |  |  |  | Alvey-Fairview No 1 230kV line | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0887 | 2023-06-30 16:16 |  |  |  | Alvey-Fairview No 1 230kV line | STUDY | OR | Douglas or Lane | GI | 2030-12-02 | 2030-12-02 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0886 | 2023-06-30 16:13 |  |  | Grid-Charged BESS | Forest Grove-McMinnville No 1 115kV line. | STUDY | OR | Linn or Lane | GI | 2030-12-02 | 2030-12-02 | 80 | 80 | NRIS & ERIS | Reciprocating Engine | Biofuel | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . | [5 empty] | FALSE
G0885 | 2023-06-30 16:10 |  |  |  | Oregon City-Chemawa No 2 115kV line. | STUDY | OR | Linn or Lane | GI | 2029-12-03 | 2029-12-03 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0883 | 2023-06-30 15:59 |  |  |  | Mt. Vernon Tap to Lookout Point-Alvey No. 2 | STUDY | OR | Lane | GI | 2029-12-03 | 2029-12-03 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0882 | 2023-06-30 15:56 |  |  |  | Lookout Point-Alvey No. 1 115kV line | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-02 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0881 | 2023-06-30 15:54 |  |  |  | Lookout Point-Alvey No. 1 115kV line | STUDY | OR | Lane | GI | 2029-12-03 | 2029-12-03 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0880 | 2023-06-30 15:50 |  |  |  | Lookout Point-Alvey No. 2 115kV line | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-02 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0879 | 2023-06-30 15:43 |  |  |  | Lookout Point-Alvey No. 2 115kV line | STUDY | OR | Lane | GI | 2029-12-03 | 2029-12-03 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0878 | 2023-06-30 15:40 |  |  | Grid-charged BESS | Albany-Lebanon No. 1 115kV line | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-02 | 80 | 80 | NRIS & ERIS | Reciprocating Engine | Biofuel | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . | [5 empty] | FALSE
G0877 | 2023-06-30 15:37 |  |  |  | Albany-Lebanon No. 1 115kV line | STUDY | OR | Lane | GI | 2029-12-03 | 2029-12-03 | 80 | 80 | NRIS & ERIS | Reciprocating Engine | Biofuel | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0876 | 2023-06-30 08:05 |  |  |  | Knight Substation | WITHDRAWN | WA | Klickitat | GI | 2029-11-30 | 2029-11-30 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G0875 | 2023-06-30 07:35 |  |  |  | LaPine Substation | WITHDRAWN | OR | Lake | GI | 2029-11-30 | 2029-11-30 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . | [5 empty] | FALSE
G0874 | 2023-06-30 07:15 |  |  |  | Buckley Substation | WITHDRAWN | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . | Available |  |  |  |  | FALSE
G0873 | 2023-06-30 07:13 |  |  |  | Lower Monumental Substation | WITHDRAWN | WA | Walla Walla | GI | 2029-12-01 | 2029-12-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0872 | 2023-06-30 07:08 |  |  |  | Lower Granite Substation | STUDY | WA | Garfield | GI | 2028-12-01 | 2028-12-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0871 | 2023-06-30 07:04 |  |  |  | Captain Jack Substation | STUDY | OR | Lake | GI | 2028-12-01 | 2028-12-01 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . | Available |  |  |  |  | FALSE
G0870 | 2023-06-30 07:02 |  |  |  | Captain Jack Substation | STUDY | OR | Lake | GI | 2028-12-01 | 2028-12-01 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . | Available |  |  |  |  | FALSE
G0884 | 2023-06-30 04:03 |  |  |  | Mt. Vernon Tap to Lookout Point-Alvey No. 2 | STUDY | OR | Lane | GI | 2030-12-02 | 2030-12-02 | 80 | 80 | NRIS & ERIS | Energy Storage | Battery | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
L0567 | 2023-06-21 16:42 | CPI-EPUD Tie | Consumers Power, Inc. |  | Harrisburg Substation | RECEIVED | OR | Washington | LL | 2026-06-22 | 2026-06-22 | 6 | 6 |  | Other | Other | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
L0566 | 2023-06-15 07:57 | Waste Management RNG Facilities | Columbia Basin Electric Cooperative, Inc. |  | Boardman Substation | STUDY | OR | Morrow | LL | 2024-03-31 | 2026-06-16 | 14 | 14 |  | Other | Other | 14 | [6 empty] | 14 |  |  | . | [5 empty] | FALSE
G0869 | 2023-06-15 07:52 |  |  |  | Ashe Substation at 500 kV | WITHDRAWN | WA | Benton | GI | 2030-12-31 | 2030-12-31 | 2200 | 2200 | NRIS | Steam Turbine | Nuclear | 2200 | [6 empty] | 2200 |  |  | . | [5 empty] | FALSE
G0868 | 2023-06-13 13:50 |  |  |  | TBD | WITHDRAWN | CA | Modoc | GI | 2026-12-31 | 2026-12-31 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
G0867 | 2023-06-02 11:45 |  |  |  | TBD | STUDY | OR | Sherman | GI | 2027-12-01 | 2027-12-01 | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | Available |  |  |  |  | FALSE
G0865 | 2023-06-02 11:44 |  |  |  | Buckley Substation | STUDY | OR | Sherman | GI | 2027-09-01 | 2027-09-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 100 |  |  |  | 300 |  |  | . | Available |  |  |  |  | FALSE
G0866 | 2023-06-02 11:44 |  |  |  | Buckley Substation | STUDY | OR | Sherman | GI | 2027-09-01 | 2027-09-01 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | [6 empty] | 300 |  |  | . | Available |  |  |  |  | FALSE
L0564 | 2023-05-22 10:52 | Alfalfa Substation -230 kV Load | Yakama Power |  | Alfalfa Substation | STUDY | WA | Yakima | LL | 2026-05-22 | 2026-05-22 | 80.7 | 80.7 |  | Other | Other | 80.7 | [6 empty] | 80.7 |  |  | . | [5 empty] | FALSE
L0563 | 2023-05-18 14:23 | Archaea RNG Plant | Columbia Basin Electric Cooperative, Inc. |  | Boardman Substation | ENERGIZED | OR | Morrow | LL | 2026-05-22 | 2026-05-22 | 4 | 4 |  | Other | Other | 4 | [6 empty] | 4 |  |  | . | [5 empty] | FALSE
L0560 | 2023-05-12 08:49 | West Hillsboro Data Center Project (Phase 1) | Portland General Electric Company |  | Keeler-Forest Grove No. 1 & No. 2 115kV Lines | STUDY | OR | Washington | LL | 2026-05-22 | 2026-05-22 | 1400 | 1400 |  | Other | Other | 1400 | [6 empty] | 1400 |  |  | . | [5 empty] | FALSE
L0561 | 2023-05-12 08:49 | NW Hillsboro-North Plains Semiconductor Plants Project (Phase 2) | Portland General Electric Company |  | Keeler-Forest Grove No. 1 & No. 2 115kV Lines | STUDY | OR | Washington | LL | 2026-05-22 | 2026-05-22 | 1800 | 1800 |  | Other | Other | 1800 | [6 empty] | 1800 |  |  | . | [5 empty] | FALSE
L0562 | 2023-05-12 08:49 | Keeler Horizon #1 & #2 Terminal Upgrades | Portland General Electric Company |  | Keeler-Forest Grove No. 1 & No. 2 115kV Lines | RECEIVED | OR | Morrow | LL | 2026-05-22 | 2026-05-22 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0862 | 2023-05-11 13:35 |  |  |  | John Day-Marion No 1 500kV line. | STUDY | OR | Sherman | GI | 2027-05-03 | 2027-05-01 | 400 | 400 | NRIS & ERIS | Energy Storage | Battery | 400 | [6 empty] | 400 | Transition Cluster |  | . | [5 empty] | FALSE
G0863 | 2023-05-11 13:35 |  |  |  | John Day-Marion No 1 500kV line. | STUDY | OR | Sherman | GI | 2027-05-03 | 2027-05-01 | 500 | 500 | NRIS & ERIS | Energy Storage | Battery | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G0864 | 2023-05-11 13:35 |  |  |  | Ashe-Marion No 2 500kV line. | STUDY | OR | Sherman | GI | 2027-05-03 | 2027-05-01 | 500 | 500 | NRIS & ERIS | Energy Storage | Battery | 500 | Wind Turbine | Wind Turbine | 304 |  |  |  | 804 |  |  | . | [5 empty] | FALSE
L0565 | 2023-05-11 13:23 | AC Management | Public Utility District No. 1 of Cowlitz County |  | Lexington Substation | STUDY | WA | Cowlitz | LL | 2025-03-31 | 2023-09-21 | 5 | 5 |  | Other | Other | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
L0559 | 2023-05-09 09:24 | Substation FG Rebuild | USN Bremerton |  | Station X-Station H No 1 115kV line | RECEIVED | WA | Kitsap | LL | 2026-05-11 | 2028-07-01 | 70 | 70 |  | Other | Other | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
L0558 | 2023-04-27 08:48 | Stearns Lane | Douglas Electric Cooperative, Inc. |  | BPA's Green Valley Substation | STUDY | OR | Washington | LL | 2025-12-01 | 2026-04-27 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0861 | 2023-04-25 16:36 |  |  |  | Grizzly-Summer Lake No 1 500kV line | STUDY | OR | Deschutes | GI | 2027-12-31 | 2027-12-31 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . | Available |  |  |  |  | FALSE
G0860 | 2023-04-25 07:10 |  |  |  | Grand Coulee-Bell No 5 230kV line | STUDY | WA | Lincoln | GI | 2027-12-31 | 2027-12-31 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0859 | 2023-04-20 11:53 |  |  |  | Central Electric Cooperative's (CEC) 12.5kV distribution line served via CEC's Knott Substation. | WITHDRAWN | OR | Deschutes | GI | 2025-08-01 | 2025-08-01 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0858 | 2023-04-14 09:33 |  |  |  | Columbia Substation @ 230kV | STUDY | WA | Douglas | GI | 2026-12-31 | 2026-12-31 | 130 | 130 | NRIS & ERIS | Energy Storage | Battery | 130 | [6 empty] | 130 |  |  | . | Available |  |  |  |  | FALSE
L0557 | 2023-04-13 16:21 | Drax | Public Utility District No. 1 of Cowlitz County |  | BPA's Cowlitz Substation. | ENERGIZED | WA | Cowlitz | LL | 2026-04-13 | 2024-02-05 | 16.3 | 16.3 |  | Other | Other | 16.3 | [6 empty] | 16.3 |  |  | . | [5 empty] | FALSE
G0857 | 2023-04-13 14:05 |  |  |  | Garrison Substation | WITHDRAWN | MT | Powell | GI | 2026-07-01 | 2027-01-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0856 | 2023-04-13 14:02 |  |  |  | Garrison Substation | WITHDRAWN | MT | Powell | GI | 2026-07-01 | 2027-01-01 | 220 | 220 | NRIS & ERIS | Energy Storage | Battery | 220 | [6 empty] | 220 |  |  | . | [5 empty] | FALSE
G0855 | 2023-04-13 10:02 |  |  |  | Lower Monumental-McNary No 1 500 kV line through a direct connection to a new 500 kV substation | STUDY | OR | Umatilla | GI | 2027-12-01 | 2027-12-01 | 450 | 450 | NRIS & ERIS | Photovoltaic | Solar | 175 | Energy Storage | Battery | 100 | Wind Turbine | Wind Turbine | 175 | 450 |  |  | . | [5 empty] | FALSE
L0556 | 2023-04-11 16:39 | Trammel Crow Mid I-5 | Public Utility District No. 1 of Cowlitz County |  | Cowlitz PUD’s South Kelso substation, fed from BPA’s Cardwell Substation. | STUDY COMPLETED | WA | Cowlitz | LL | 2026-04-08 | 2023-09-11 | 5.3 | 5.3 |  | Other | Other | 5.3 | [6 empty] | 5.3 |  |  | . | [5 empty] | FALSE
G0854 | 2023-04-11 10:05 |  |  |  | McNary-Quarry Switchyard No 1 230 kV line | STUDY | OR | Umatilla | GI | 2025-12-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | Photovoltaic | Solar | 300 |  |  |  | 600 |  |  | . | [5 empty] | FALSE
L0555 | 2023-03-28 13:42 | CAC Green H2 Facility | Columbia River People's Utility District |  | Allston Substation or St Johns Substation | WITHDRAWN | WA | Columbia | LL | 2030-01-02 |  | 1600 | 1600 |  | Other | Other | 1600 | [6 empty] | 1600 |  |  | . | [5 empty] | FALSE
L0554 | 2023-03-28 10:15 | West Burley Loads | City of Burley |  | West Burley-Heyburn No 1 138kV line | STUDY | ID | Teton | LL | 2026-03-24 | 2026-03-24 | 5.2 | 5.2 |  | Other | Other | 5.2 | [6 empty] | 5.2 |  |  | . | [5 empty] | FALSE
L0553 | 2023-03-28 09:52 | Burley Loads | City of Burley |  | West Burley-Heyburn No 1 138kV line | STUDY | ID | Teton | LL | 2026-03-23 | 2026-03-23 | 5.2 | 5.2 |  | Other | Other | 5.2 | [6 empty] | 5.2 |  |  | . | [5 empty] | FALSE
G0853 | 2023-03-24 09:10 |  |  |  | Chief Joseph-Sickler No 1 500kV line | STUDY | WA | Douglas | GI | 2027-12-31 | 2027-12-31 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | Available |  |  |  |  | FALSE
G0852 | 2023-03-22 18:15 |  |  |  | 1) 16 miles south of Marion - Buckley 500kV line 2) 16 miles south of Ashe - Marion 500kV line 3) 5.61 miles south of Jones Canyon - Santiam 230kV line Note that it is proposed to build a double circuit 500kV line for all 3 POIs to loop into cust sub.. | WITHDRAWN | OR | Wasco | GI | 2027-12-01 | 2027-12-01 | 750 | 750 | NRIS & ERIS | Photovoltaic | Solar | 750 | Energy Storage | Battery | 750 |  |  |  | 1500 |  |  | . | [5 empty] | FALSE
G0851 | 2023-03-22 11:16 |  |  |  | Primary: Buckley-Grizzly No 1 500 kV line; Secondary: Maupin 230 kV Substation. | WITHDRAWN | OR | Sherman | GI | 2027-12-31 | 2027-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | [5 empty] | FALSE
G0850 | 2023-03-22 11:13 |  |  |  | Primary: Buckley-Grizzly No 1 500 kV line; Secondary: Buckley Substation | STUDY | OR | Sherman | GI | 2027-12-31 | 2027-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | Available |  |  |  |  | FALSE
G0849 | 2023-03-22 11:12 |  |  |  | Primary: Buckley-Grizzly No 1 500kV line; Secondary: Buckley Substation | STUDY | OR | Sherman | GI | 2027-12-31 | 2027-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | Available |  |  |  |  | FALSE
G0848 | 2023-03-06 07:02 |  |  |  | Fairview Substation | WITHDRAWN | OR | Coos | GI | 2033-06-01 | 2033-06-01 | 1000 | 1000 | NRIS & ERIS | Wind Turbine | Wind Turbine | 1000 | [6 empty] | 1000 |  |  | . | Available |  |  |  |  | FALSE
G0847 | 2023-02-24 11:44 |  |  |  | PSE's Phalen Gulch 230kV Substation | STUDY | WA | Columbia | GI | 2024-12-30 | 2027-04-27 | 150 | 150 | ERIS | Photovoltaic | Solar | 150 | [6 empty] | 150 |  |  | . | [5 empty] | TRUE
G0846 | 2023-02-22 14:41 |  |  |  | Knight Substation | WITHDRAWN | WA | Klickitat | GI | 2026-06-15 | 2027-01-01 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . | [5 empty] | FALSE
G0842 | 2023-02-22 02:41 |  |  |  | Brasada 115 kV Substation | WITHDRAWN | OR | Crook | GI | 2026-06-15 | 2026-06-15 | 90 | 90 | NRIS & ERIS | Photovoltaic | Solar | 90 | Energy Storage | Battery | 45 |  |  |  | 135 |  |  | . | [5 empty] | FALSE
G0843 | 2023-02-22 02:41 |  |  |  | Horse Heaven - Harvalum No 1 230kV line | STUDY | WA | Klickitat | GI | 2026-06-15 | 2027-01-01 | 120 | 120 | NRIS & ERIS | Photovoltaic | Solar | 120 | Energy Storage | Battery | 60 |  |  |  | 180 |  |  | . | Available |  |  |  |  | FALSE
G0844 | 2023-02-22 02:41 |  |  |  | Horse Heaven-Harvalum No 1 230kV line. | STUDY | WA | Klickitat | GI | 2026-06-15 | 2027-01-01 | 280 | 280 | NRIS & ERIS | Photovoltaic | Solar | 280 | Energy Storage | Battery | 140 |  |  |  | 420 | Transition Cluster |  | . | Available |  |  |  |  | FALSE
G0845 | 2023-02-22 02:41 |  |  |  | Rocky Ford 115 kV Substation | WITHDRAWN | WA | Grant | GI | 2026-06-15 | 2026-06-15 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 75 |  |  |  | 225 |  |  | . | [5 empty] | FALSE
G0841 | 2023-02-15 07:42 |  |  | BESS is grid-charging | Grizzly-Summer Lake #1 or Grizzly-Captain Jack #1 500 kV lines. | STUDY | OR | Lake | GI | 2028-12-01 | 2028-12-01 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 200 |  |  |  | 600 |  |  | . | Available |  |  |  |  | FALSE
G0840 | 2023-02-07 12:28 |  |  |  | Chief Joseph-Sickler No 1 500kV line | STUDY | WA | Douglas | GI | 2027-12-31 | 2027-12-31 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | Available |  |  |  |  | FALSE
G0839 | 2023-02-03 07:47 |  |  |  | Jones Canyon-Santiam No 1 230kV line | STUDY | OR | Jefferson | GI | 2027-12-31 | 2027-12-31 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 150 |  |  |  | 300 |  |  | . | Available |  |  |  |  | FALSE
G0838 | 2023-02-03 07:46 |  |  |  | McNary-Santiam No 1 230kV line | STUDY | OR | Jefferson | GI | 2027-04-01 | 2027-04-01 | 150 | 150 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 150 |  |  |  | 300 |  |  | . | Available |  |  |  |  | FALSE
G0837 | 2023-02-02 15:16 |  |  | 24.3 MW Request | Boardman 115kV | WITHDRAWN | OR | Morrow | GI | 2023-12-15 | 2025-08-01 | 25 | 25 | NRIS | Gas Turbine | Natural Gas | 24.3 | [6 empty] | 24.3 |  |  | . |  |  | Available |  |  | FALSE
L0552 | 2023-02-02 09:10 | NW Pipeline | Public Utility District No. 1 of Cowlitz County |  | BPA's Lexington 115 kV Substation | ENERGIZED | WA | Cowlitz | LL | 2026-02-02 | 2026-02-02 | 4.7 | 4.7 |  | Other | Other | 4.7 | [6 empty] | 4.7 |  |  | . | [5 empty] | FALSE
L0551 | 2023-01-10 14:54 | CREA-Central Ferry | Columbia Rural Electric Association |  | Central Ferry Substation | STUDY | WA | Garfield | LL | 2026-01-09 | 2026-01-09 | 100 | 100 |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0836 | 2023-01-05 09:54 |  |  |  | Snohomish | WITHDRAWN | WA | Snohomish | GI | 2024-01-01 | 2024-01-01 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0835 | 2022-12-30 11:20 |  |  |  | Harney Substation | WITHDRAWN | OR | Harney | GI | 2027-12-01 | 2027-12-01 | 120 | 120 | NRIS & ERIS | Photovoltaic | Solar | 115 | [6 empty] | 115 |  |  | . | [5 empty] | FALSE
G0833 | 2022-12-30 11:19 |  |  | 203.5 MW Request | Primary: Scooteney Substation; Alternate: Benton-Scooteney 115 kV line. | WITHDRAWN | WA | Adams | GI | 2027-12-01 | 2027-12-01 | 204 | 204 | NRIS & ERIS | Photovoltaic | Solar | 203.5 | [6 empty] | 203.5 |  |  | . | Available |  |  |  |  | FALSE
G0834 | 2022-12-30 11:19 |  |  |  | Lower Monumental-McNary No 1 500 kV line through a direct connection to a new 500 kV substation | STUDY | OR | Umatilla | GI | 2027-12-01 | 2027-12-01 | 450 | 450 | NRIS & ERIS | Photovoltaic | Solar | 175 | Energy Storage | Battery | 100 | Wind Turbine | Wind Turbine | 175 | 450 |  |  | . | [5 empty] | FALSE
L0550 | 2022-12-29 16:37 | Roza | Public Utility District No. 1 of Kittitas County |  | BPA's Moxee Substation | STUDY | WA | Kittitas | LL | 2025-12-26 | 2027-12-31 | 1 | 1 |  | Other | Other | 630 | [6 empty] | 630 |  |  | . | [5 empty] | FALSE
G0832 | 2022-12-22 09:45 |  |  |  | Murray: Snohomish Co PUD 115 kV Feeder 1 | STUDY | WA | Snohomish | GI | 2025-10-31 | 2025-11-01 | 25 | 25 | ERIS | Energy Storage | Battery | 25 | [6 empty] | 25 |  |  | . |  |  | Available |  | Available | FALSE
L0549 | 2022-12-19 13:53 | Lookingglass Substation | Douglas Electric Cooperative, Inc. |  | Reston Substation | STUDY | OR | Douglas | LL | 2025-12-18 | 2027-12-18 | 20.3 | 20.3 |  | Other | Other | 20.3 | [6 empty] | 20.3 |  |  | . | [5 empty] | FALSE
L0548 | 2022-12-19 09:38 | Project Osprey | Clark Public Utilities |  | Sifton Substation | WITHDRAWN | WA | Clark | LL | 2025-12-15 | 2025-10-01 | 100 | 100 |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0831 | 2022-12-14 12:59 |  |  |  | 45°33'53.11"N, 120°22'21.49"W | WITHDRAWN | OR | Gilliam | GI | 2027-08-02 | 2027-08-02 | 175 | 175 | NRIS & ERIS | Photovoltaic | Solar | 175 | Energy Storage | Battery | 175 |  |  |  | 350 |  |  | . | [5 empty] | FALSE
G0830 | 2022-12-14 11:14 |  |  |  | Olympia Substation | STUDY | WA | Thurston | GI | 2026-12-31 | 2026-12-31 | 20 | 20 | ERIS | Energy Storage | Battery | 20 | [6 empty] | 20 |  |  | . | Available |  |  |  |  | FALSE
L0546 | 2022-12-12 08:30 | Four Mile Drive (Kalispell West) | Flathead Electric Cooperative, Inc. |  | Hot Springs Substation or Libby Substationi | STUDY | MT | Lincoln | LL | 2025-12-08 | 2025-12-08 | 35 | 35 |  | Other | Other | 35 | [6 empty] | 35 |  |  | . | [5 empty] | FALSE
L0547 | 2022-12-12 08:30 | Whitefish Stage Road_HWY 40 | Flathead Electric Cooperative, Inc. |  | TBD | WITHDRAWN | MT | Flathead | LL | 2025-12-08 | 2025-12-08 | 35 | 35 |  | Other | Other | 35 | [6 empty] | 35 |  |  | . | [5 empty] | FALSE
G0829 | 2022-12-09 13:36 |  |  |  | Columbia Substation @230kV | STUDY | WA | Douglas | GI | 2026-12-31 | 2026-12-31 | 20 | 20 | ERIS | Energy Storage | Battery | 20 | [6 empty] | 20 |  |  | . | Available |  |  |  |  | FALSE
G0828 | 2022-12-08 15:04 |  |  |  | Vantage Substation @ 230kV | STUDY | WA | Grant | GI | 2026-12-31 | 2026-12-31 | 100 | 100 | NRIS & ERIS | Energy Storage | Battery | 100 | [6 empty] | 100 |  |  | . | Available |  |  |  |  | FALSE
L0545 | 2022-12-07 10:22 | Stack IPI Data Center | Public Utility District No. 1 of Klickitat County |  | RKCR-JDAY-1 or MCNY-ROSS-2 near Harvalum Substation | STUDY | WA | Klickitat | LL | 2025-12-05 | 2025-12-05 | 958 | 958 |  | Other | Other | 958 | [6 empty] | 958 |  |  | . | [5 empty] | FALSE
L0544 | 2022-12-05 08:39 | Grant Rocky Ford Station | Public Utility District No. 2 of Grant County, Washington |  | Potholes-Grand Coulee No 1 230kV line Grand Coulee-Hanford No 1 500kV line | STUDY | WA | Grant | LL | 2027-06-01 | 2027-12-31 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0827 | 2022-12-02 13:32 |  |  |  | John Day – Klondike Schoolhouse 230 kV No 1 Line | STUDY | OR | Sherman | GI | 2024-12-16 | 2024-12-16 | 25 | 25 | NRIS & ERIS | Wind Turbine | Wind Turbine | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE | TRUE
L0543 | 2022-12-02 12:12 | Bonanza | Central Electric Cooperative, Inc. |  | Ponderosa Substation | STUDY | OR | Crook | LL | 2025-12-02 | 2026-01-01 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0826 | 2022-11-20 16:07 |  |  |  | Primary: Grizzly - Summer Lake No 1 500 kV line. Secondary: Grizzly - Captain Jack No 1 500 kV line. | STUDY | OR | Klamath | GI | 2027-12-31 | 2027-12-31 | 280 | 280 | NRIS & ERIS | Photovoltaic | Solar | 280 | Energy Storage | Battery | 280 |  |  |  | 560 |  |  | . | Available |  |  |  |  | FALSE
G0825 | 2022-11-20 15:26 |  |  |  | Primary: Buckley - Grizzly No 1 500 kV line; Secondary: Buckley 500 kV Substation | STUDY | OR | Sherman | GI | 2027-12-31 | 2027-12-31 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 400 |  |  |  | 800 |  |  | . | Available |  |  |  |  | FALSE
G0824 | 2022-11-18 08:09 |  |  |  | Central Ferry Substation at 500 kV | WITHDRAWN | WA | Garfield | GI | 2024-12-31 | 2024-12-31 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 303 | Energy Storage | Battery | 152 |  |  |  | 455 |  |  | . | [5 empty] | FALSE
G0823 | 2022-11-16 21:04 |  |  |  | McNary Substation: Umatilla E Coop 230kV Feeder 1 | WITHDRAWN | OR | Morrow | GI | 2026-09-01 | 2026-09-01 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0822 | 2022-11-14 14:18 |  |  | Total injection not to exceed 2000 MW at the POI. | Ashe Substation, or Ashe - Marion No 2 500 kV line, or Ashe - Slatt No 1 500 kV line. | STUDY | WA | Benton | GI | 2026-12-01 | 2026-12-01 | 2000 | 2000 | NRIS & ERIS | Photovoltaic | Solar | 2000 | Energy Storage | Battery | 2000 |  |  |  | 4000 |  |  | . | [5 empty] | FALSE
G0821 | 2022-11-14 09:32 |  |  |  | BPA 138KV BRIDGE SUBSTATION | STUDY | ID | Cassia | GI | 2025-12-01 | 2027-01-01 | 10 | 10 | ERIS | Steam Turbine | Geothermal | 10 | [6 empty] | 10 |  |  | . |  |  |  |  | Available | FALSE
L0542 | 2022-11-08 07:44 | Pacific Corrugated (PCPC) | Public Utility District No. 1 of Cowlitz County |  | BPA's Longview Substation | ENERGIZED | WA | Cowlitz | LL | 2024-11-05 |  | 1.9 | 1.9 |  | Other | Other | 1.9 | [6 empty] | 1.9 |  |  | . | [5 empty] | FALSE
G0819 | 2022-11-02 14:19 |  |  |  | Columbia-Grand Coulee No 1 230kV line | STUDY | WA | Douglas | GI | 2027-12-01 | 2027-12-01 | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
G0820 | 2022-11-02 14:19 |  |  |  | Columbia-Grand Coulee No 1 230kV line | STUDY | WA | Douglas | GI | 2027-12-01 | 2027-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
L0541 | 2022-10-20 17:09 | Divert | Public Utility District No. 1 of Cowlitz County | 2.6 MW Request | BPA's Longview 115kV Substation | ENERGIZED | WA | Cowlitz | LL | 2023-10-21 | 2023-10-21 | 2.6 | 2.6 |  | Other | Other | 2.6 | [6 empty] | 2.6 |  |  | . | [5 empty] | FALSE
G0818 | 2022-10-20 15:57 |  |  | 2.99 MW Request | Maupin-Tygh Valley #1 69 kV line | STUDY | OR | Wasco | GI | 2025-12-31 | 2027-01-01 | 3 | 3 | ERIS | Photovoltaic | Solar | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
L0540 | 2022-10-20 06:37 | Manzanita Substation | Public Utility District No. 1 of Mason County |  | Shelton - Fairmont #2 115kV line. | STUDY COMPLETED | WA | Mason | LL | 2024-05-01 | 2025-04-01 | 6.7 | 6.7 |  | Other | Other | 6.7 | [6 empty] | 6.7 |  |  | . | [5 empty] | FALSE
L0539 | 2022-10-05 13:47 | Gardiner Hydrogen Production Facility | Central Lincoln People's Utility District |  | Gardiner Substation | WITHDRAWN | OR | Douglas | LL | 2027-06-30 | 2027-06-30 | 100 | 100 |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0817 | 2022-10-03 08:17 |  |  |  | Spring Creek-Wine Country #1 between Spring Creek and Mabton Substation. | STUDY | WA | Yakima | GI | 2025-12-31 | 2027-01-01 | 215 | 215 | NRIS & ERIS | Photovoltaic | Solar | 215 | Energy Storage | Battery | 110 |  |  |  | 325 |  |  | . | [5 empty] | FALSE
G0814 | 2022-10-03 07:57 |  |  |  | Intalco Substation at 230 kV or alternate is Custer Substation at 500 kV | WITHDRAWN | WA | Grays Harbor | GI | 2030-05-30 | 2030-05-30 | 1000 | 1000 | NRIS & ERIS | Wind Turbine | Wind Turbine | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
G0815 | 2022-10-03 07:57 |  |  |  | Tacoma Substation at 500 kV | WITHDRAWN | WA | Grays Harbor | GI | 2030-05-30 | 2030-05-30 | 1000 | 1000 | NRIS & ERIS | Wind Turbine | Wind Turbine | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
G0816 | 2022-10-03 07:57 |  |  |  | Tacoma Substation at 500 kV | WITHDRAWN | WA | Grays Harbor | GI | 2030-05-30 | 2030-05-30 | 1000 | 1000 | NRIS & ERIS | Wind Turbine | Wind Turbine | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
G0813 | 2022-09-23 13:27 |  |  |  | 6.6 Miles southwest of McNary looped into McNary - Hermiston 230kV. | WITHDRAWN | OR | Umatilla | GI | 2026-12-31 | 2026-12-31 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | [5 empty] | FALSE
L0538 | 2022-09-22 17:57 | Brother's Tap | Midstate Electric Cooperative, Inc. |  | MEC's Brother's Tap on BPA's Brasada-Harney No 1 115kV line | STUDY | OR | Deschutes | LL | 2024-09-24 | 2026-10-01 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0537 | 2022-09-16 16:22 | Mixed Use Load | Pend Oreille County PUD No. 1 |  | Usk Substation | WITHDRAWN | WA | Spokane | LL | 2022-11-01 | 2026-12-31 | 170 | 170 |  | Other | Other | 170 | [6 empty] | 170 |  |  | . | [5 empty] | FALSE
G0812 | 2022-09-16 13:50 |  |  |  | Primary: Wendson 230 kV; Alternate: Takenitch 230 kV | STUDY | OR | Lane | GI | 2030-12-10 | 2030-12-10 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0811 | 2022-09-16 13:48 |  |  |  | Primary: Wendson 230 kV; Alternate: Takenitch 230 kV | STUDY | OR | Lane | GI | 2030-12-10 | 2030-12-10 | 600 | 600 | NRIS & ERIS | Reciprocating Engine | Biofuel | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0810 | 2022-09-16 13:47 |  |  |  | Primary: Wendson 230 kV; Alternate: Takenitch 230 kV | STUDY | OR | Lane | GI | 2030-12-10 | 2030-12-10 | 200 | 200 | NRIS & ERIS | Reciprocating Engine | Biofuel | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
G0809 | 2022-09-16 13:46 |  |  |  | BPA's Gardiner 230 kV Substation or Tahkenitch 230 kV Substation. | STUDY | OR | Douglas | GI | 2030-12-10 | 2030-12-10 | 600 | 600 | NRIS & ERIS | Energy Storage | Pumped-Storage Hydro | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0808 | 2022-09-16 13:45 |  |  |  | BPA's Gardiner 115 kV substation or Tahkenitch 230 kV substation | STUDY | OR | Douglas | GI | 2030-12-10 | 2030-12-10 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0806 | 2022-09-16 13:44 |  |  |  | BPA's Gardiner 115 kV Substation or Tahkenitch 115 kV Substation. | STUDY | OR | Douglas | GI | 2028-12-08 | 2028-12-08 | 600 | 600 | NRIS & ERIS | Reciprocating Engine | Biofuel | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0807 | 2022-09-16 13:44 |  |  |  | BPA's Gardiner 230 kV or Tahkenitch 230 kV Substation. | STUDY | OR | Douglas | GI | 2030-12-10 | 2030-12-10 | 600 | 600 | NRIS & ERIS | Energy Storage | Pumped-Storage Hydro | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0805 | 2022-09-16 13:42 |  |  |  | BPA's Gardiner 230 kV Substation or Tahkenitch 230 kV Substation | STUDY | OR | Douglas | GI | 2028-12-08 | 2028-12-08 | 200 | 200 | NRIS & ERIS | Reciprocating Engine | Biofuel | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
G0804 | 2022-09-16 13:41 |  |  |  | BPA's Gardiner 115 kV Substation or Tahkenitch 115 kV Substation. | STUDY | OR | Douglas | GI | 2028-12-08 | 2028-12-08 | 200 | 200 | NRIS & ERIS | Reciprocating Engine | Biofuel | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
G0803 | 2022-09-16 13:39 |  |  |  | Primary: Gardiner Substation; Alternate: Wendson Substation | STUDY | OR | Lane | GI | 2028-12-08 | 2028-12-08 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
G0802 | 2022-09-16 13:38 |  |  |  | Primary: Wendson 115 kV; Alternate: Takenitch 115 kV | STUDY | OR | Lane | GI | 2028-12-08 | 2028-12-08 | 80 | 80 | NRIS & ERIS | Reciprocating Engine | Biofuel | 80 | [6 empty] | 80 |  |  | . | Available |  |  |  |  | FALSE
G0800 | 2022-09-16 13:37 |  |  |  | BPA's Gardiner Substation or Central Lincoln PUD's Gardiner Substation | STUDY | OR | Douglas | GI | 2028-12-08 | 2028-12-08 | 80 | 80 | NRIS & ERIS | Reciprocating Engine | Biofuel | 80 | [6 empty] | 80 |  |  | . | Available |  |  |  |  | FALSE
G0801 | 2022-09-16 13:37 |  |  |  | BPA's Gardiner Substation or Central Lincoln PUD's Gardiner Substation | STUDY | OR | Douglas | GI | 2028-12-08 | 2028-12-08 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
L0536 | 2022-09-02 15:59 | Lake Street Data Center | City of Forest Grove |  | Keeler-Forest Grove No 2 115kV line | WITHDRAWN | OR | Washington | LL | 2025-09-19 | 2025-09-19 | 108 | 108 |  | Other | Other | 108 | [6 empty] | 108 |  |  | . | [5 empty] | FALSE
G0799 | 2022-08-18 15:01 |  |  |  | Wine Country-Midway No 1 230 kV line. | WITHDRAWN | WA | Benton | GI | 2026-06-01 | 2027-01-01 | 315 | 315 | NRIS & ERIS | Energy Storage | Battery | 315 | [6 empty] | 315 |  |  | . | [5 empty] | FALSE
G0797 | 2022-08-18 14:53 |  |  | Grid-Charging BESS | BPA 500 KV John Day-Marion transmission line. | STUDY | OR | Wasco | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G0798 | 2022-08-18 14:53 |  |  |  | BPA 500 KV John Day-Marion transmission line. | STUDY | OR | Wasco | GI | 2029-01-02 | 2029-01-02 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0796 | 2022-08-18 11:06 |  |  |  | BPA 500 KV John Day-Big Eddy 1/2 transmission lines. | STUDY | OR | Sherman | GI | 2029-01-02 | 2029-01-02 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0795 | 2022-08-18 11:05 |  |  |  | BPA 500 KV John Day-Big Eddy 1/2 transmission line. | STUDY | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0794 | 2022-08-18 11:04 |  |  | Grid-charging BESS | BPA 115KV Albany-Eugene transmission line. | STUDY | OR | Linn | GI | 2028-12-01 | 2028-12-01 | 80 | 80 | NRIS & ERIS | Reciprocating Engine | Biofuel | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . | Available |  |  |  |  | FALSE
G0793 | 2022-08-18 11:02 |  |  | grid-charging BESS | BPA 115KV Albany-Eugene transmission line. | STUDY | OR | Linn | GI | 2028-12-01 | 2028-12-01 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . | Available |  |  |  |  | FALSE
G0792 | 2022-08-18 11:00 |  |  |  | BPA 500 KV John Day-Big Eddy 1/2 transmission lines. | STUDY | OR | Sherman | GI | 2029-01-02 | 2029-01-02 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0791 | 2022-08-18 10:59 |  |  | Grid-Charged BESS | BPA 500 KV John Day-Big Eddy 1/2 transmission line. | STUDY | OR | Sherman | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G0790 | 2022-08-18 09:58 |  |  |  | BPA 230KV Big Eddy-Redmond transmission line. | WITHDRAWN | OR | Wasco | GI | 2029-01-02 | 2029-01-02 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0789 | 2022-08-18 09:57 |  |  |  | BPA 230KV Big Eddy-Redmond transmission line. | WITHDRAWN | OR | Wasco | GI | 2028-12-01 | 2028-12-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0788 | 2022-08-18 |  |  |  | Big Eddy-Ostrander 500 kV | STUDY | OR | Wasco | GI | 2028-12-01 | 2028-12-01 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0787 | 2022-08-17 23:58 |  |  | Grid-charged BESS | Big Eddy-Ostrander No 1 500 kV | STUDY | OR | Wasco | GI | 2028-12-01 | 2028-12-01 | 600 | 600 | NRIS & ERIS | Energy Storage | Pumped-Storage Hydro | 600 | Energy Storage | Battery | 600 |  |  |  | 1200 |  |  | . | [5 empty] | FALSE
G0786 | 2022-08-17 23:57 |  |  |  | New substation approximately 2-15 miles West of BPA 230 KV Longhorn Substation. | STUDY | OR | Morrow | GI | 2029-01-02 | 2029-01-02 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | Available |  |  |  |  | FALSE
G0785 | 2022-08-17 23:56 |  |  |  | New substation approximately 2-15 miles West of BPA 230 KV Longhorn Substation. | STUDY | OR | Morrow | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | [6 empty] | 650 |  |  | . | Available |  |  |  |  | FALSE
G0784 | 2022-08-17 23:54 |  |  |  | BPA 230 KV Big Eddy-McLoughlin transmission line. | WITHDRAWN | OR | Wasco | GI | 2029-01-02 |  | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0783 | 2022-08-17 23:53 |  |  |  | 230KV Big Eddy-McLoughlin transmission line. | WITHDRAWN | OR | Wasco | GI | 2028-12-01 | 2028-12-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0782 | 2022-08-17 23:51 |  |  |  | New substation approximately 2-15 miles West of BPA 230 KV Longhorn Substation. | STUDY | OR | Morrow | GI | 2029-01-02 | 2029-01-02 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | Available |  |  |  |  | FALSE
G0781 | 2022-08-17 23:50 |  |  | Grid-charged BESS | Roughly 2-15 miles West of BPA Longhorn 230kV substation | STUDY | OR | Morrow | GI | 2028-12-04 | 2028-12-04 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | Available |  |  |  |  | FALSE
G0779 | 2022-08-17 23:48 |  |  |  | Big Eddy-Troutdale 230 kV line. Alternative POI on Big Eddy-McLoughlin or Big Eddy-Chemawa 230 kV lines. | WITHDRAWN | OR | Wasco | GI | 2028-12-01 | 2028-12-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | Energy Storage | Battery | 600 |  |  |  | 1200 |  |  | . | [5 empty] | FALSE
G0780 | 2022-08-17 23:48 |  |  |  | BPA 230 KV Big Eddy-Troutdale transmission line. | WITHDRAWN | OR | Wasco | GI | 2029-01-02 |  | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0778 | 2022-08-17 23:46 |  |  |  | Stanfield Substation | STUDY | OR | Umatilla | GI | 2027-12-31 | 2027-12-01 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0777 | 2022-08-17 23:44 |  |  |  | Stanfield Substation | STUDY | OR | Umatilla | GI | 2027-12-01 | 2027-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
G0776 | 2022-08-17 23:42 |  |  |  | Big Eddy-Chemawa 230 kV line. Alternative POI at Big Eddy-Troutdale or Big Eddy-McLoughlin 230 kV line. | WITHDRAWN | OR | Wasco | GI | 2028-12-31 | 2028-12-31 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0775 | 2022-08-17 23:41 |  |  |  | Big Eddy-Chemawa 230 kV line. Alternative POI at Big Eddy-Troutdale or Big Eddy-McLoughlin 230 kV lines. | WITHDRAWN | OR | Wasco | GI | 2028-12-01 | 2028-12-31 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | Energy Storage | Battery | 600 |  |  |  | 1200 |  |  | . | [5 empty] | FALSE
G0774 | 2022-08-17 23:38 |  |  |  | John Day-Marion No 1 500 kV line. Alternative POI at Ashe-Marion 500 kV line. | STUDY | OR | Wasco | GI | 2028-12-31 | 2028-12-31 | 650 | 650 | NRIS & ERIS | Energy Storage | Battery | 650 | [6 empty] | 650 |  |  | . | [5 empty] | FALSE
G0773 | 2022-08-17 23:37 |  |  |  | John Day-Marion No 1 500 kV line. Alternative POI at Ashe-Marion 500 kV line. | STUDY | OR | Wasco | GI | 2028-12-01 | 2028-12-01 | 650 | 650 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 |  |  |  | 1300 |  |  | . | [5 empty] | FALSE
L0535 | 2022-08-17 16:14 | Lithium Nevada | Harney Electric Cooperative, Inc. |  | BPA's 115 kV breaker at NVE's Winnemucca Substation | STUDY | NV | Humboldt | LL | 2024-05-01 | 2025-10-01 | 142.7 | 142.7 |  | Other | Other | 142.7 | [6 empty] | 142.7 |  |  | . | [5 empty] | FALSE
L0533 | 2022-08-15 11:47 | Sunbreak | PacifiCorp |  | Ponderosa Substation | WITHDRAWN | OR | Crook | LL | 2025-03-31 | 2025-08-11 | 250 | 250 |  | Other | Other | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
L0534 | 2022-08-15 09:46 | Atlas Agro | City of Richland, Washington |  | Benton-White Bluffs No 1 line or White Bluffs-Richland No 1 line | STUDY | WA | Benton | LL | 2025-08-15 | 2025-08-15 | 350 | 350 |  | Other | Other | 350 | [6 empty] | 350 |  |  | . | [5 empty] | FALSE
G0770 | 2022-08-12 13:33 |  |  | 24.3 MW Request | Morrow Flat 115kV (POD 4458) | WITHDRAWN | OR | Morrow | GI | 2023-05-01 | 2025-08-01 | 25 | 25 | NRIS | Gas Turbine | Natural Gas | 24.3 | [6 empty] | 24.3 |  |  | . |  |  | Available |  |  | FALSE
G0771 | 2022-08-12 13:33 |  |  | 24.3 MW Request | Morrow Flat 230kV - UECA (POD 4432) | WITHDRAWN | OR | Morrow | GI | 2023-04-03 | 2025-08-01 | 25 | 25 | NRIS | Gas Turbine | Natural Gas | 24.3 | [6 empty] | 24.3 |  |  | . |  |  | Available |  |  | FALSE
G0769 | 2022-08-11 15:59 |  |  |  | Longview-Chehalis No 1 and No 3 230 kV line. | WITHDRAWN | WA | Lewis | GI | 2026-10-15 | 2026-10-15 | 170 | 170 | NRIS & ERIS | Wind Turbine | Wind Turbine | 170 | [6 empty] | 170 |  |  | . | [5 empty] | FALSE
G0768 | 2022-08-02 10:39 |  |  |  | John Day 500 kV Substation | STUDY | OR | Gilliam | GI | 2027-12-01 | 2027-12-01 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | Photovoltaic | Solar | 200 | Energy Storage | Battery | 100 | 600 |  |  | . | [5 empty] | FALSE
G0767 | 2022-08-01 13:25 |  |  |  | To be determined. | WITHDRAWN | WA | Grant | GI | 2026-01-02 | 2027-01-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | Available |  |  |  |  | FALSE
G0766 | 2022-07-25 10:39 |  |  |  | Wine Country – Midway No 1 230 kV line. | WITHDRAWN | WA | Benton | GI | 2026-06-01 |  | 315 | 315 | NRIS & ERIS | Energy Storage | Battery | 315 | [6 empty] | 315 |  |  | . | [5 empty] | FALSE
G0765 | 2022-07-15 14:28 |  |  |  | Coyote Springs Substation | STUDY | OR | Umatilla | GI | 2024-07-01 | 2025-06-01 | 277 | 290 | ERIS | Combined Cycle | Natural Gas | 13 | [6 empty] | 13 |  |  | . | [5 empty] | FALSE
G0764 | 2022-07-15 13:17 |  |  | Downsized from 40 MW to 5 MW on 2/13/2023. | La Grande 230 kV Substation. | STUDY | OR | Union | GI | 2026-12-31 | 2026-12-31 | 5 | 5 | ERIS | Photovoltaic | Solar | 5 | Energy Storage | Battery | 5 |  |  |  | 10 |  |  | . | Available |  | Available |  |  | FALSE
L0532 | 2022-07-14 08:16 | North Richland | City of Richland, Washington |  | White Bluffs-Stevens Drive No 2 115kV line | STUDY | WA | Benton | LL | 2025-07-11 | 2025-07-11 | 40 | 40 |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
G0772 | 2022-07-11 |  |  | 24.3 MW Request | TBD | WITHDRAWN | OR | Morrow | GI | 2023-04-03 | 2024-06-01 | 25 | 25 | NRIS | Gas Turbine | Natural Gas | 24.3 | [6 empty] | 24.3 |  |  | . | [5 empty] | FALSE
G0763 | 2022-06-28 14:48 |  |  |  | 45.24351258952271, -120.1840070265574 | WITHDRAWN | OR | Gilliam | GI | 2024-12-31 | 2024-12-31 | 3 | 3 | ERIS | Photovoltaic | Solar | 3 | [6 empty] | 3 |  |  | . | Available |  |  |  |  | FALSE
G0762 | 2022-06-28 14:46 |  |  |  | LaPine Substation | STUDY | OR | Lake | GI | 2024-12-31 | 2027-01-01 | 3 | 3 | ERIS | Photovoltaic | Solar | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
L0531 | 2022-06-28 08:25 | Bridgeport I5 Commercial/Industrial Project | City of Milton |  | BPA's Surprise Lake Substation | STUDY | WA | King | LL | 2025-06-25 | 2025-06-03 | 20.7 | 20.7 |  | Other | Other | 20.7 | [6 empty] | 20.7 |  |  | . | [5 empty] | FALSE
G0761 | 2022-06-23 11:47 |  |  |  | TBD | STUDY | WA | Grant | GI | 2026-06-30 | 2027-01-01 | 290 | 290 | NRIS & ERIS | Wind Turbine | Wind Turbine | 290 | [6 empty] | 290 |  |  | . | [5 empty] | FALSE
G0760 | 2022-06-16 17:03 |  |  |  | Vantage 500 kV Substation | STUDY | WA | Grant | GI | 2025-12-31 | 2027-01-01 | 590 | 590 | ERIS | Energy Storage | Battery | 590 | Combustion Turbine | Natural Gas | 400 |  |  |  | 990 |  |  | . | Available |  |  |  |  | FALSE
G0759 | 2022-06-16 11:25 |  |  |  | 5-mile 500kV Gen Tie to Buckley 500 kV Substation | WITHDRAWN | OR | Sherman | GI | 2025-12-31 | 2025-12-31 | 1650 | 1650 | ERIS | Photovoltaic | Solar | 1650 | Energy Storage | Battery | 1650 | Combustion Turbine | Natural Gas | 500 | 3800 |  |  | . | [5 empty] | FALSE
G0758 | 2022-06-16 11:21 |  |  |  | 5-mile 500kV Gen Tie to Grizzly 500 kV Substation | STUDY | OR | Jefferson | GI | 2025-12-31 | 2027-01-01 | 600 | 600 | ERIS | Photovoltaic | Solar | 365 | Energy Storage | Battery | 600 | Combustion Turbine | Natural Gas | 400 | 1365 |  |  | . | Available |  |  |  |  | FALSE
G0757 | 2022-06-16 11:17 |  |  |  | Allston Substation 500 kV | WITHDRAWN | OR | Columbia | GI | 2025-12-31 | 2025-12-31 | 1650 | 1650 | ERIS | Photovoltaic | Solar | 1650 | Energy Storage | Battery | 1650 | Combustion Turbine | Natural Gas | 500 | 3800 |  |  | . | [5 empty] | FALSE
G0756 | 2022-06-16 11:14 |  |  |  | Summer Lake Substation | WITHDRAWN | OR | Lake | GI | 2025-12-31 |  | 1650 | 1650 | ERIS | Photovoltaic | Solar | 1650 | Energy Storage | Battery | 1650 | Combustion Turbine | Natural Gas | 500 | 3800 |  |  | . | [5 empty] | FALSE
G0755 | 2022-06-15 21:04 |  |  |  | Malin 230 kV Substation | WITHDRAWN | OR | Klamath | GI | 2025-12-31 |  | 300 | 300 | ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | [5 empty] | FALSE
G0754 | 2022-06-15 21:00 |  |  |  | Marion 500 kV Substation | WITHDRAWN | OR | Marion | GI | 2025-12-31 | 2025-12-31 | 1650 | 1650 | ERIS | Photovoltaic | Solar | 1650 | Energy Storage | Battery | 1650 | Combustion Turbine | Natural Gas | 500 | 3800 |  |  | . | [5 empty] | FALSE
G0753 | 2022-06-15 20:54 |  |  |  | 5-mile 230kV Gen Tie to Columbia 230 kV Substation | STUDY | WA | Douglas | GI | 2025-12-31 | 2027-01-01 | 300 | 300 | ERIS | Photovoltaic | Solar | 215 | Energy Storage | Battery | 300 |  |  |  | 515 |  |  | . | Available |  |  |  |  | FALSE
G0752 | 2022-06-15 20:49 |  |  |  | 5-mile 500kV Gen Tie to Longhorn 500 kV Substation | STUDY | OR | Morrow | GI | 2025-12-31 | 2027-01-01 | 340 | 340 | ERIS | Energy Storage | Battery | 330 | Combustion Turbine | Natural Gas | 340 |  |  |  | 670 |  |  | . | Available |  |  |  |  | FALSE
G0751 | 2022-06-15 16:24 |  |  |  | John Day 500 kV Substation | WITHDRAWN | OR | Sherman | GI | 2025-12-31 | 2027-01-01 | 412.5 | 412.5 | ERIS | Energy Storage | Battery | 412.5 | [6 empty] | 412.5 |  |  | . | [5 empty] | FALSE
G0750 | 2022-06-15 16:21 |  |  |  | Hot Springs 230 kV Substation | WITHDRAWN | MT | Sanders | GI | 2025-12-31 | 2025-12-31 | 300 | 300 | ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | Available |  |  |  |  | FALSE
G0749 | 2022-06-15 16:18 |  |  |  | Garrison 230 kV Substation | WITHDRAWN | MT | Powell | GI | 2025-12-31 | 2027-01-01 | 300 | 300 | ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | Available |  | Available |  |  | FALSE
G0748 | 2022-06-15 14:21 |  |  |  | Captain Jack 500 kV Substation | WITHDRAWN | OR | Klamath | GI | 2025-12-31 | 2027-01-01 | 1403 | 1403 | ERIS | Photovoltaic | Solar | 475 | Energy Storage | Battery | 1403 | Combustion Turbine | Natural Gas | 500 | 2378 |  |  | . | Available |  | Available |  |  | FALSE
L0530 | 2022-06-07 15:58 | Tillamook Substation Line Terminal Swap Project | Tillamook People's Utility District |  | Tillamook Substation | STUDY | OR | Tillamook | LL | 2025-06-03 | 2025-06-03 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0747 | 2022-06-01 18:07 |  |  |  | BPA’s LaPine-Chiloquin 230 kV line. | STUDY | OR | Klamath | GI | 2025-12-01 | 2027-01-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
L0529 | 2022-06-01 08:55 | Ellensburg Loop Project | Public Utility District No. 1 of Kittitas County |  | BPA's Columbia-Ellensburg No 1 115kV line | STUDY | WA | Kittitas | LL | 2025-05-28 | 2027-05-31 | 6.4 | 6.4 |  | Other | Other | 6.4 | [6 empty] | 6.4 |  |  | . | [5 empty] | FALSE
G0746 | 2022-05-25 14:49 |  |  |  | Primary POI: Franklin - Hedges No 1 115 kV line. Secondary POI: McNary-Berrian No 1 tap to McNary-Badger Canyon No 1 115 kV line | WITHDRAWN | WA | Benton | GI | 2025-12-31 | 2027-01-01 | 75 | 75 | NRIS & ERIS | Photovoltaic | Solar | 75 | Energy Storage | Battery | 75 |  |  |  | 150 |  |  | . | Available |  | Available |  |  | FALSE
G0745 | 2022-05-25 14:39 |  |  |  | Hatton tap to Connell tap | STUDY | WA | Adams | GI | 2026-12-31 | 2026-12-31 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | Energy Storage | Battery | 100 |  |  |  | 200 | Transition Cluster |  | . | Available |  |  |  |  | FALSE
G0744 | 2022-05-24 15:56 |  |  |  | 1. Vantage-Hanford #1 500 kV line 2. Corridor of the 230kV Midway- Rocky Ford and Midway-Potholes 230kV transmission lines | STUDY | WA | Grant | GI | 2026-12-30 | 2026-12-30 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | Available |  |  |  |  | FALSE
G0743 | 2022-05-24 13:06 |  |  |  | Wine Country-Midway #1 | WITHDRAWN | WA | Benton | GI | 2026-06-01 | 2027-01-01 | 315 | 315 | NRIS & ERIS | Photovoltaic | Solar | 315 | [6 empty] | 315 |  |  | . | [5 empty] | FALSE
G0742 | 2022-05-20 09:16 |  |  |  | Vantage - Hanford No 1 500 kV line; Midway - Rocky Ford No 1 230 kV line; Midway - Potholes No 1 230 kV line. | WITHDRAWN | WA | Grant | GI | 2026-06-30 | 2026-06-30 | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0528 | 2022-05-13 16:15 | Bellevue Substation | Big Bend Electric Cooperative, Inc. |  | BBEC's proposed LaPorte 115 kV line, north of Selph Landing Road and Bellevue Road in Pasco, WA | STUDY COMPLETED | WA | Franklin | LL | 2025-05-09 | 2025-05-09 | 7 | 7 |  | Other | Other | 7 | [6 empty] | 7 |  |  | . | [5 empty] | FALSE
L0527 | 2022-05-11 09:33 | Bull Road Data Center | City of Ellensburg |  | Ellensburg-Moxee No 1 115kV line | WITHDRAWN | WA | Kittitas | LL | 2025-05-07 | 2025-05-07 | 250 | 250 |  | Other | Other | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0741 | 2022-05-05 07:55 |  |  |  | E. E. Clouse Substation 230 kV | WITHDRAWN | WA | Klickitat | GI | 2024-11-29 | 2027-01-01 | 125 | 125 | NRIS & ERIS | Photovoltaic | Solar | 250 | Energy Storage | Battery | 150 |  |  |  | 400 |  |  | . | Available |  | Available |  |  | FALSE
L0526 | 2022-05-04 09:03 | Cascade Steel Load Transfer | The City of McMinnville, a municipal corporation of the State of Oregon, acting by and through its Water and Light Commission |  | Cascade 230 kV Substation | WITHDRAWN | OR | Yamhill | LL | 2025-04-30 | 2025-04-30 | 2 | 2 |  | Other | Other | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
G0740 | 2022-04-28 09:31 |  |  |  | TBD | WITHDRAWN | WA | Grant | GI | 2026-01-01 |  | 200 | 200 | ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0739 | 2022-04-26 15:35 |  |  |  | BPA's Kerr Substation | WITHDRAWN | MT | Lake | GI | 2024-04-28 | 2024-04-28 | 212 | 212 | NRIS & ERIS | Hydro | Water | 212 | [6 empty] | 212 |  |  | . | [5 empty] | FALSE
G0738 | 2022-04-26 10:10 |  |  | Related to G0362. | BPA’s Morrow Flat 230 kV | STUDY | OR | Umatilla | GI | 2025-12-01 | 2027-01-01 | 0 | 0 | ERIS | Photovoltaic | Solar | 60 | Energy Storage | Battery | 25 |  |  |  | 85 |  |  | . | [5 empty] | TRUE
G0737 | 2022-04-26 10:05 |  |  |  | Keeler - Forest Grove No 1 115 kV transmission line. | WITHDRAWN | OR | Washington | GI | 2026-12-31 | 2026-12-31 | 150 | 150 | NRIS & ERIS | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | Available |  |  |  |  | FALSE
L0525 | 2022-04-04 07:03 | Elmore County SFBRD | Idaho Power Company |  | Anderson Ranch-Mountain Home #1 115 kV line | STUDY | ID | Idaho | LL | 2025-03-31 | 2026-03-31 | 27 | 27 |  | Other | Other | 27 | [6 empty] | 27 |  |  | . | [5 empty] | FALSE
L0524 | 2022-03-22 12:18 | Starrh Transformer Replacement | United Electric Co-op, Inc. |  |  | WITHDRAWN | ID | Cassia | LL | 2025-03-18 | 2022-09-09 | 21 | 21 |  | Other | Other | 21 | [6 empty] | 21 |  |  | . | [5 empty] | FALSE
L0523 | 2022-03-22 12:11 | Clallam New MIll | Public Utility District No. 1 of Clallam County |  | Sappho Substation | BPA COMPLETED | WA | Clallam | LL | 2024-03-20 | 2024-03-20 | 4.3 | 4.3 |  | Other | Other | 4.3 | [6 empty] | 4.3 |  |  | . | [5 empty] | FALSE
L0522 | 2022-03-22 08:47 | Vineyard Substation | Big Bend Electric Cooperative, Inc. |  | Benton-Franklin #1 or #2 115 kV transmission line | STUDY | WA | Franklin | LL | 2025-03-18 | 2025-03-18 | 14 | 14 |  | Other | Other | 14 | [6 empty] | 14 |  |  | . | [5 empty] | FALSE
G0736 | 2022-03-21 08:43 |  |  | Generating output at POI limited to 300 MW. | Tucannon River - North Lewiston No 1 115 kV line. | WITHDRAWN | WA | Asotin | GI | 2025-12-01 | 2022-05-23 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 300 |  |  |  | 600 |  |  | . | [5 empty] | FALSE
G0735 | 2022-03-18 12:38 |  |  |  | Aberdeen Substation 230 kV; Alternatives: Satsop-Aberdeen No 2 230 kV line and Satsop-Aberdeen No 3 230 kV line | WITHDRAWN | WA | Grays Harbor | GI | 2030-05-30 | 2030-05-30 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . | Available |  |  |  |  | FALSE
L0521 | 2022-03-18 11:11 | Sixmile Canyon 500kV Substation | PacifiCorp |  | BPA's proposed Longhorn Substation | STUDY | OR | Umatilla | LL | 2026-01-02 | 2026-01-02 | 1050 | 1050 |  | Other | Other | 1050 | [6 empty] | 1050 |  |  | . | [5 empty] | FALSE
L0520 | 2022-03-18 10:55 | Dalreed Substation | PacifiCorp |  | the BPA Morrow Flat - Jones Canyon #1 230 kV line. | STUDY | OR | Morrow | LL | 2024-01-02 | 2024-01-02 | 71.5 | 71.5 |  | Other | Other | 71.5 | [6 empty] | 71.5 |  |  | . | [5 empty] | FALSE
G0733 | 2022-03-15 15:43 |  |  |  | TBD | STUDY | WA | Benton | GI | 2025-10-31 | 2027-12-31 | 30 | 30 | ERIS | Energy Storage | Battery | 30 | [6 empty] | 30 |  |  | . |  |  | Available |  |  | FALSE
G0734 | 2022-03-15 15:19 |  |  |  | New 230 kV Substation that will tap the Franklin-McNary 230kV Transmission Line. | STUDY | WA | Benton | GI | 2024-11-15 | 2026-04-30 | 20 | 20 | ERIS | Energy Storage | Battery | 20 | [6 empty] | 20 |  |  | . |  |  | Available |  |  | FALSE
G0732 | 2022-03-11 10:04 |  |  |  | Wautoma 500 kV | STUDY | WA | Benton | GI | 2027-04-15 | 2028-04-15 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | [5 empty] | FALSE
L0519 | 2022-03-11 09:23 | L0519 Mt. Solo Industrial Project | Public Utility District No. 1 of Cowlitz County |  | BPA's Longview Substation 230 kV | WITHDRAWN | WA | Cowlitz | LL | 2025-03-07 | 2025-03-07 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0518 | 2022-03-11 07:54 | L0518 Pacific Substation Transformer | United Electric Co-op, Inc. |  | Unity-West Burley No 1 138 kV, Pacific Tap POD 4313 | WITHDRAWN | ID | Cassia | LL | 2025-03-07 | 2022-09-09 | 21 | 21 |  | Other | Other | 21 | [6 empty] | 21 |  |  | . | [5 empty] | FALSE
L0517 | 2022-03-07 07:52 | L0517 Midway Substation | Avista Corporation |  | Addy-Bell 115kV Transmission Line (between existing Colbert and Mead Substations) | STUDY | WA | Spokane | LL | 2024-12-31 | 2025-03-03 | 9.2 | 9.2 |  | Other | Other | 9.2 | [6 empty] | 9.2 |  |  | . | [5 empty] | FALSE
L0516 | 2022-03-01 08:13 | Boardman-Ion 69kV Line Relocation & New 230kV Step Down Sub | Idaho Power Company |  | BPA's Planned Longhorn Substation | E&P EXECUTED | OR | Umatilla | LL | 2025-02-19 | 2025-07-19 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0515 | 2022-02-23 07:58 | Boardman to Hemingway Project | Idaho Power Company |  | BPA's Planned Longhorn Substation | CONST AGRMT EXE | OR | Umatilla | LL | 2026-05-29 | 2027-06-30 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0731 | 2022-02-18 16:05 |  |  |  | Northern Lights 12.47 KV distribution near Samuels Substation. | WITHDRAWN | ID | Bonner | GI | 2024-05-01 | 2027-01-01 | 10 | 10 | ERIS | Other | Other | 10 | [6 empty] | 10 |  |  | . | Available |  | Available |  | Available | FALSE
G0728 | 2022-02-04 10:46 |  |  | 500 MW max output at POI. | Jones Canyon to Tumble Creek section of Jones Canyon-Santiam No 1 230 kV line; Ashe to Marian No 2 500 kV line; or Slatt to Buckley No 1 500 kV line. | STUDY | OR | Sherman | GI | 2026-12-01 | 2027-01-01 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | Energy Storage | Battery | 250 |  |  |  | 750 |  |  | . | Available |  |  |  |  | FALSE
G0729 | 2022-02-04 10:46 |  |  | 300 MW max output at POI. | Grand Coulee - Chief Joseph No 1 230 kV line; Grand Coulee - Chief Joseph No 2 230 kV line; or Grand Coulee - Chief Joseph No 3 500 kV line | WITHDRAWN | WA | Douglas | GI | 2025-12-01 | 2027-01-01 | 450 | 450 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 150 |  |  |  | 450 |  |  | . | Available |  |  |  |  | FALSE
G0730 | 2022-02-04 10:46 |  |  | 750 MW max output at POI. | Central Ferry Substation | WITHDRAWN | WA | Garfield | GI | 2025-12-01 | 2028-01-01 | 1125 | 1125 | NRIS & ERIS | Wind Turbine | Wind Turbine | 600 | Photovoltaic | Solar | 150 | Energy Storage | Battery | 375 | 1125 |  |  | . | Available |  | Available |  |  | FALSE
G0727 | 2022-02-01 09:17 |  |  |  | Central Ferry Substation 230 kV Alternate POI: Tucannon River POI 115 kV | WITHDRAWN | WA | Garfield | GI | 2026-12-31 | 2026-12-31 | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | TRUE
L0514 | 2022-01-27 13:22 | Quantum Loophole | Public Utility District No. 1 of Cowlitz County |  | BPA's Longview Substation | WITHDRAWN | WA | Cowlitz | LL | 2025-01-31 | 2025-01-31 | 400 | 400 |  | Other | Other | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0726 | 2022-01-26 11:44 |  |  |  | Redmond 69 KV Substation | WITHDRAWN | OR | Jefferson | GI | 2022-12-31 | 2022-12-31 | 20 | 20 | NRIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . |  |  | Available |  |  | FALSE
G0723 | 2022-01-26 11:11 |  |  |  | Bandon-Rogue No 1 115 kV line. | STUDY | OR | Coos & Curry | GI | 2026-12-01 | 2026-12-01 | 200 | 200 | NRIS & ERIS | Energy Storage | Battery | 200 | [6 empty] | 200 |  |  | . | Available |  | Available |  |  | FALSE
G0724 | 2022-01-26 11:11 |  |  |  | Fairview-Rogue No 1 230 KV line. | STUDY | OR | Curry | GI | 2026-12-10 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | Available |  | Available |  |  | FALSE
G0725 | 2022-01-26 11:11 |  |  |  | Fairview 230 kV Substation | STUDY | OR | Coos & Curry | GI | 2027-12-10 | 2027-12-10 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | Available |  | Available |  |  | FALSE
G0722 | 2022-01-24 10:34 |  |  |  | BPA's Harney - Brasada 115 kV line. | STUDY | OR | Harney | GI | 2024-06-30 | 2027-01-01 | 15 | 15 | ERIS | Photovoltaic | Solar | 15 | [6 empty] | 15 |  |  | . | [5 empty] | FALSE
L0512 | 2022-01-06 07:50 | Mint Farm - AE Inc | Public Utility District No. 1 of Cowlitz County |  | CCPUD's Mint Farm Substation | BPA COMPLETED | WA | Cowlitz | LL | 2024-01-04 | 2024-01-04 | 54 | 54 |  | Other | Other | 54 | [6 empty] | 54 |  |  | . | [5 empty] | FALSE
L0511 | 2022-01-04 17:21 | Ponderay Renewable Fiber and Blockchain Center Expansion | Pend Oreille County PUD No. 1 |  | BPA's Usk Substation | WITHDRAWN | WA | Pend Oreille | LL | 2024-01-02 | 2024-01-02 | 600 | 600 |  | Other | Other | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0721 | 2021-12-22 07:58 |  |  |  | Franklin - McNary 230 kV line, at the new Bofer Canyon Substation | STUDY COMPLETED | WA | Benton | GI | 2024-11-15 | 2026-03-31 | 0 | 0 | ERIS | Wind Turbine | Wind Turbine | 13.6 | [6 empty] | 13.6 |  |  | . |  |  | Available |  |  | FALSE
G0720 | 2021-12-17 19:13 |  |  |  | Garrison 230 kV Substation | WITHDRAWN | MT | Powell | GI | 2024-12-31 | 2027-01-01 | 120 | 120 | ERIS | Energy Storage | Battery | 120 | [6 empty] | 120 |  |  | . | Available |  | Available |  |  | FALSE
L0513 | 2021-12-16 09:00 | TC Energy 230 kV Intertie at Diamond Lake Junction | Midstate Electric Cooperative, Inc. |  | BPA's LaPine Substation | RECEIVED | OR | Lake | LL | 2023-12-15 | 2025-12-15 | 24 | 24 |  | Other | Other | 12 | [6 empty] | 12 |  |  | . | [5 empty] | FALSE
G0719 | 2021-12-08 07:16 |  |  |  | TBD | WITHDRAWN | OR | Sherman | GI | 2025-12-31 |  | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0718 | 2021-12-07 08:46 |  |  |  | Primary: Pe Ell Substation Alternate: Tap to Chehalis 230 kV | WITHDRAWN | WA | Lewis | GI | 2027-03-31 | 2026-10-15 | 160 | 160 | NRIS & ERIS | Wind Turbine | Wind Turbine | 170 | [6 empty] | 170 |  |  | . | Available |  | Available |  |  | FALSE
G0717 | 2021-12-07 08:00 |  |  |  | Rock Creek Substation | STUDY COMPLETED | WA | Klickitat | GI | 2024-09-01 | 2024-09-01 | 75 | 75 | NRIS & ERIS | Energy Storage | Battery | 75 | [6 empty] | 75 |  |  | . |  |  | Available |  | Available | TRUE
G0716 | 2021-12-02 16:02 |  |  | Gridstack Battery Energy Storage Systems (BESS) rated for 2.63 MW each, for a total of 50 MW of BESS. The plant controller will modulate output of both plants to ensure output at the POI does not exceed 100 MW. | New 115 kV substation adjacent to the new Webber Canyon substation. | STUDY | WA | Benton | GI | 2025-10-31 | 2027-12-31 | 100 | 100 | ERIS | Photovoltaic | Solar | 100 | Energy Storage | Battery | 50 |  |  |  | 150 |  |  | . |  |  | Available |  |  | FALSE
G0715 | 2021-12-02 15:48 |  |  |  | Buckley 500 kV Substation | STUDY | OR | Sherman | GI | 2025-12-01 | 2028-01-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | Available |  | Available |  |  | FALSE
G0714 | 2021-12-02 15:45 |  |  |  | Buckley 500 kV Substation | STUDY | OR | Sherman | GI | 2025-12-01 | 2028-01-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | Available |  | Available |  |  | FALSE
L0510 | 2021-12-02 06:35 | Six Mile Canyon Substation | Umatilla Electric Cooperative |  | BPA's Ashe - Slatt No.1 500 kV line | E&P EXECUTED | OR | Umatilla | LL | 2024-12-07 | 2027-08-30 | 1000 | 1000 |  | Other | Other | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
G0713 | 2021-11-29 08:04 |  |  |  | BPA's Slatt Substation | STUDY | OR | Morrow | GI | 2026-12-31 | 2026-12-31 | 100 | 100 | ERIS | Photovoltaic | Solar | 100 | [6 empty] | 100 |  |  | . |  |  | Available |  | Available | FALSE
G0711 | 2021-11-23 09:12 |  |  |  | 45.67752437675481, -120.7374771 - Wasco Sherman County OR | STUDY | OR | Sherman | GI | 2025-12-31 | 2027-01-01 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | [6 empty] | 300 |  |  | . | Available |  |  |  |  | FALSE
G0712 | 2021-11-23 09:12 |  |  |  | 45.67752437675481, -120.7374771 - Wasco Sherman County OR | STUDY | OR | Sherman | GI | 2025-12-31 | 2027-01-01 | 448 | 448 | NRIS & ERIS | Photovoltaic | Solar | 448 | [6 empty] | 448 |  |  | . | Available |  |  |  |  | FALSE
L0509 | 2021-11-22 07:17 | BBEC - Camp Sub | Big Bend Electric Cooperative, Inc. |  | Scooteney Substation | STUDY | WA | Franklin | LL | 2025-03-28 | 2024-12-01 | 11 | 11 |  | Other | Other | 11 | [6 empty] | 11 |  |  | . | [5 empty] | FALSE
L0508 | 2021-11-05 08:03 | Meadowlark | City of Forest Grove |  | Forest Grove-McMinnville No. 1 115 kV Line | STUDY | OR | Washington | LL | 2025-01-31 | 2025-06-01 | 36 | 36 |  | Other | Other | 36 | [6 empty] | 36 |  |  | . | [5 empty] | FALSE
G0710 | 2021-11-02 10:58 |  |  | An increase of 1.6 MW of capacity to an existing Flathead Electric generation facility. | Flathead Substation | STUDY | MT | Flathead | GI | 2022-09-01 | 2025-12-31 | 2 | 2 | ERIS | Reciprocating Engine | Biofuel | 1.6 | [6 empty] | 1.6 |  |  | . |  |  |  |  | Available | FALSE
L0507 | 2021-10-27 16:17 | Liberty Gold | Raft River Rural Electric Cooperative, Inc. |  | BPA's Bridge Substation | STUDY | ID | Cassia | LL | 2024-10-23 | 2024-10-23 | 9.5 | 9.5 |  | Other | Other | 9.5 | [6 empty] | 9.5 |  |  | . | [5 empty] | FALSE
G0709 | 2021-10-26 11:49 |  |  |  | BPA's Slatt 230 kV Substation | STUDY | OR | Gilliam | GI | 2023-12-01 | 2025-12-01 | 41 | 41 | NRIS & ERIS | Energy Storage | Battery | 41 | [6 empty] | 41 |  |  | . |  |  | Available |  | Available | TRUE
L0506 | 2021-10-26 09:55 | Webber Canyon to Prosser Transmission Line | Public Utility District No. 1 of Benton County |  | BPA's proposed Webber Canyon Substation | STUDY | WA | Benton | LL | 2025-01-02 | 2025-01-02 | 44.6 | 44.6 |  | Other | Other | 44.6 | [6 empty] | 44.6 |  |  | . | [5 empty] | FALSE
G0707 | 2021-10-26 07:33 |  |  |  | BPA’s Boardman – Alkali 115 kV transmission line. | STUDY COMPLETED | OR | Morrow | GI | 2023-12-01 | 2025-05-31 | 60 | 60 | NRIS & ERIS | Energy Storage | Battery | 60 | [6 empty] | 60 |  |  | . |  |  | Available |  | Available | FALSE
G0708 | 2021-10-26 07:33 |  |  |  | BPA’s Boardman – Alkali 115 kV transmission line. | STUDY | OR | Morrow | GI | 2023-12-01 | 2028-12-01 | 60 | 60 | NRIS & ERIS | Energy Storage | Battery | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
L0505 | 2021-10-21 17:25 | Drummond-Macks Inn 46 kV to 115 kV Conversion | Fall River Rural Electric Cooperative, Inc. |  | Drummond Substation | STUDY | ID | Fremont | LL | 2026-12-31 | 2026-12-30 | 8.3 | 8.3 |  | Other | Other | 8.3 | [6 empty] | 8.3 |  |  | . | [5 empty] | FALSE
G0706 | 2021-10-20 13:10 |  |  |  | Slatt Substation | STUDY | OR | Morrow | GI | 2024-12-31 | 2025-12-01 | 100 | 100 | ERIS | Photovoltaic | Solar | 100 | [6 empty] | 100 |  |  | . |  |  | Available |  | Available | FALSE
L0504 | 2021-09-29 13:12 | Belfair Substation | Public Utility District No. 3 of Mason County |  | BPA's Shelton-Kitsap #2 115 kV line | STUDY | WA | Mason | LL | 2023-09-27 | 2026-04-30 | 38.3 | 38.3 |  | Other | Other | 38.3 | [6 empty] | 38.3 |  |  | . | [5 empty] | FALSE
L0503 | 2021-09-28 15:13 | L0503 Toledo-Wendson 230 kV | Central Lincoln People's Utility District |  | BPA's Toledo - Wendson 230 kV transmission line | STUDY | OR | Lincoln | LL | 2023-09-26 | 2032-09-26 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0705 | 2021-09-24 11:25 |  |  |  | Plymouth Tap 115 kV | STUDY | WA | Benton | GI | 2024-12-31 | 2027-01-01 | 60 | 60 | NRIS | Photovoltaic | Solar | 60 | [6 empty] | 60 |  |  | . | Available |  | Available |  | Available | FALSE
G0704 | 2021-09-23 16:28 |  |  | 200 MW total output at POI | Hatton 115 kV Substation | WITHDRAWN | WA | Adams | GI | 2025-09-01 | 2022-06-03 | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | Available |  |  |  |  | FALSE
G0695 | 2021-09-22 16:05 |  |  | 1200 MW grid-charging | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2028-12-01 | 2027-01-01 | 1200 | 1200 | NRIS & ERIS | Photovoltaic | Solar | 1300 | Energy Storage | Battery | 1300 | Reciprocating Engine | Biofuel | 1300 | 3900 |  |  | . | Available |  |  |  |  | FALSE
G0696 | 2021-09-22 16:05 |  |  |  | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2030-12-02 | 2027-01-01 | 1200 | 1200 | NRIS & ERIS | Photovoltaic | Solar | 1300 | Energy Storage | Battery | 1300 |  |  |  | 2600 |  |  | . | Available |  |  |  |  | FALSE
G0697 | 2021-09-22 16:05 |  |  |  | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2032-12-01 | 2027-01-01 | 1200 | 1200 | NRIS & ERIS | Photovoltaic | Solar | 650 | Energy Storage | Battery | 650 | Energy Storage | Pumped-Storage Hydro | 650 | 1950 |  |  | . | Available |  |  |  |  | FALSE
G0698 | 2021-09-22 16:05 |  |  |  | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | Energy Storage | Battery | 600 | Energy Storage | Pumped-Storage Hydro | 600 | 1800 |  |  | . | Available |  |  |  |  | FALSE
G0699 | 2021-09-22 16:05 |  |  | 595 MW when grid charging | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0700 | 2021-09-22 16:05 |  |  |  | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | Energy Storage | Battery | 600 |  |  |  | 1200 |  |  | . | Available |  |  |  |  | FALSE
G0701 | 2021-09-22 16:05 |  |  |  | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | Energy Storage | Battery | 600 |  |  |  | 1200 |  |  | . | Available |  |  |  |  | FALSE
G0702 | 2021-09-22 16:05 |  |  | grid-charged BESS | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | Energy Storage | Battery | 600 |  |  |  | 1200 |  |  | . | Available |  |  |  |  | FALSE
G0693 | 2021-09-22 16:04 |  |  |  | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | Energy Storage | Battery | 100 |  |  |  | 200 |  |  | . | Available |  |  |  |  | FALSE
G0694 | 2021-09-22 16:04 |  |  |  | Ponderosa Substation 500 kV | STUDY | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | Energy Storage | Battery | 100 |  |  |  | 200 |  |  | . | Available |  |  |  |  | FALSE
G0692 | 2021-09-17 16:41 |  |  |  | Benton 115 kV Substation | WITHDRAWN | WA | Adams | GI | 2023-12-31 | 2024-12-31 | 20 | 20 | NRIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0502 | 2021-09-16 07:06 | Swift-Troutdale Line | PacifiCorp |  | BPA Sifton Substation | STUDY | WA | Clark | LL | 2025-01-01 | 2026-07-01 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0691 | 2021-09-13 12:04 |  |  |  | Bofer Substation | STUDY COMPLETED | WA | Benton | GI | 2023-10-23 | 2026-03-31 | 100 | 100 | ERIS | Photovoltaic | Solar | 100 | Energy Storage | Battery | 30 |  |  |  | 130 |  |  | . |  |  | Available |  |  | FALSE
G0690 | 2021-09-09 11:56 |  |  |  | CEC Prineville Junction-Madras 69 kV line | WITHDRAWN | OR | Jefferson | GI | 2022-12-31 | 2022-12-31 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0689 | 2021-09-07 15:48 |  |  |  | Connell Tap on the Benton-Scooteney line. | STUDY | WA | Franklin | GI | 2023-12-31 | 2027-01-01 | 10 | 10 | NRIS & ERIS | Photovoltaic | Solar | 13.3 | [6 empty] | 13.3 |  |  | . | Available |  | Available |  | Available | FALSE
G0688 | 2021-08-26 08:57 |  |  |  | Midway Substation 230 kV, directly into a new 230 kV bay. | STUDY | WA | Benton | GI | 2025-12-31 | 2027-12-31 | 500 | 500 | NRIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . | Available |  |  |  |  | FALSE
G0687 | 2021-08-25 12:24 |  |  |  | 45.371967, -120.707373 - Grass valley Sherman County OR | STUDY | OR | Sherman | GI | 2024-12-31 | 2027-01-01 | 900 | 900 | NRIS & ERIS | Photovoltaic | Solar | 900 | [6 empty] | 900 |  |  | . | Available |  | Available |  | Available | FALSE
L0501 | 2021-08-25 08:48 | Chemawa-Waconda 115 kV Line Project | Portland General Electric Company |  | Chemawa Substation | STUDY | OR | Marion | LL | 2023-08-23 | 2026-06-30 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0500 | 2021-08-17 08:39 | East Low 79.2 Pump Project | USBR Columbia Basin |  | Scooteney Substation | BPA COMPLETED | WA | Franklin | LL | 2024-08-13 | 2022-02-14 | 4.5 | 4.5 |  | Other | Other | 4.5 | [6 empty] | 4.5 |  |  | . | [5 empty] | FALSE
L0499 | 2021-08-13 12:40 | Project Pivot and Specialized | PacifiCorp |  | McNary Substation | STUDY | OR | Umatilla | LL | 2024-08-09 | 2026-12-01 | 484 | 484 |  | Other | Other | 484 | [6 empty] | 484 |  |  | . | [5 empty] | FALSE
G0686 | 2021-08-13 09:56 |  |  |  | Benton No 2 115 kV line. | STUDY | WA | Benton | GI | 2028-07-03 | 2027-01-01 | 128 | 128 | NRIS & ERIS | Photovoltaic | Solar | 127.5 | [6 empty] | 127.5 |  |  | . | Available |  | Available |  |  | FALSE
L0498 | 2021-08-13 09:47 | Project Litespeed | PacifiCorp |  | BPA's Boardman - Alkali No.1 115 kV line | STUDY | OR | Gilliam | LL | 2024-01-01 | 2024-01-01 | 185 | 185 |  | Other | Other | 242 | [6 empty] | 242 |  |  | . | [5 empty] | FALSE
L0497 | 2021-07-29 09:26 | Energizer Data Center Expanded Capacity | Public Utility District No. 1 of Klickitat County |  | KPUD Energizer Substation | STUDY COMPLETED | WA | Klickitat | LL | 2023-07-27 | 2023-07-27 | 200 | 200 |  | Other | Other | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0496 | 2021-07-26 14:44 | Birch Data Center | City of Forest Grove |  | Keeler/Forest Grove 115 #1 & 2 | WITHDRAWN | OR | Yamhill | LL | 2023-03-31 | 2024-07-22 | 150 | 150 |  | Other | Other | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G0684 | 2021-07-23 11:07 |  |  | Maximum instantaneous injection of the project (generation + storage) will not exceed 470 MW at POI | Wautoma 500 kV Substation | STUDY | WA | Benton | GI | 2024-10-01 | 2027-01-01 | 470 | 470 | ERIS | Photovoltaic | Solar | 470 | Energy Storage | Battery | 235 |  |  |  | 705 |  |  | . | Available |  | Available |  |  | FALSE
G0683 | 2021-07-19 10:12 |  |  |  | Wautoma 500 kV | STUDY | WA | Benton | GI | 2026-12-31 | 2027-12-31 | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 233 | [6 empty] | 233 |  |  | . | Available |  | Available |  | Available | FALSE
G0682 | 2021-07-13 12:09 |  |  | Interconnection Capacity is for 300 MW max at the POI. | Big Eddy - Spring Creek No 1 230 kV line, approximately 28 miles NE of the Big Eddy Substation | WITHDRAWN | WA | Klickitat | GI | 2025-12-31 | 2025-12-31 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 305 | Energy Storage | Battery | 154 |  |  |  | 459 |  |  | . | Available |  | Available |  |  | FALSE
L0495 | 2021-07-12 18:12 | Latham Substation Reliability Project | Emerald People's Utility District |  | BPA-owned 2.92 miles section of Alvey-Martin Creek No. 1 Line between Drain Tap and Martin Creek | STUDY | OR | Lane | LL | 2023-07-10 | 2027-11-30 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0494 | 2021-07-12 09:16 | Ponderary Renewable Fiber and Blockchain Project | Pend Oreille County PUD No. 1 |  | Usk Substation | ENERGIZED | WA | Pend Oreille | LL | 2021-09-01 | 2021-12-15 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0681 | 2021-07-07 08:18 |  |  |  | Buckley - Marion No 1 500 kV line | STUDY | OR | Marion | GI | 2026-12-31 | 2027-12-31 | 1000 | 1000 | NRIS & ERIS | Photovoltaic | Solar | 1000 | Energy Storage | Battery | 1000 |  |  |  | 2000 |  |  | . | Available |  | Available |  |  | FALSE
G0680 | 2021-07-02 15:38 |  |  | Co-located with a 200 MW solar project. | Sickler Substation | WITHDRAWN | WA | Adams | GI | 2023-08-01 | 2027-01-01 | 300 | 300 | ERIS | Energy Storage | Battery | 300 | [6 empty] | 300 |  |  | . | Available |  | Available |  |  | FALSE
G0679 | 2021-07-02 15:04 |  |  | Co-located with a 300 MW Battery Project | Sickler Substation | WITHDRAWN | WA | Adams | GI | 2023-08-01 | 2027-01-01 | 200 | 200 | ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | Available |  | Available |  |  | FALSE
L0493 | 2021-06-29 14:18 | Energizer Data Center | Public Utility District No. 1 of Klickitat County |  | KPUD Energizer Substation | STUDY COMPLETED | WA | Klickitat | LL | 2024-06-25 | 2024-06-25 | 77.5 | 77.5 |  | Other | Other | 77.5 | [6 empty] | 77.5 |  |  | . | [5 empty] | FALSE
L0492 | 2021-06-29 11:01 | East Low 47.5 Pump Project | USBR Columbia Basin | Joint request with ECBID | BBEC's Schrag Substation | RECEIVED | WA | Adams | LL | 2024-06-25 | 2024-06-25 | 5.2 | 5.2 |  | Other | Other | 5.2 | [6 empty] | 5.2 |  |  | . | [5 empty] | FALSE
G0678 | 2021-06-17 14:25 |  |  | Includes AC coupled battery storage system. | Longhorn substation 230 kV | STUDY | OR | Morrow | GI | 2024-12-31 | 2027-01-01 | 1200 | 1200 | NRIS & ERIS | Photovoltaic | Solar | 1200 | [6 empty] | 1200 |  |  | . | Available |  | Available |  |  | FALSE
L0491 | 2021-06-17 09:40 | Cascade Renewable Transmission Project - HVDC | New Customer Pending | Max Capacity of HVDC line = 1100 MW | Big Eddy Substation | STUDY | OR | Wasco | LL | 2024-06-17 | 2027-06-01 | 0 | 0 |  | Other | Other | 1130 | [6 empty] | 1130 |  |  | . | [5 empty] | FALSE
L0490 | 2021-05-29 23:20 | Upriver McKenzie Reliability Improvement Project | Eugene Water & Electric Board | Joint Request with Lane Electric Cooperative | BPA Cougar-Holden Creek No 1 115 kV line; BPA Hills Creek-Oakridge Section of Hills Creek-Lookout Point No 1 115 kV line. | STUDY | WA | Thurston | LL | 2025-09-02 | 2026-12-31 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0489 | 2021-04-27 17:08 | Aberdeen Biodiesel | Public Utility District No. 1 of Grays Harbor County Washington |  | Aberdeen Substation 230 kV | WITHDRAWN | WA | Grays Harbor | LL | 2025-01-02 | 2025-01-01 | 275 | 275 |  | Other | Other | 275 | [6 empty] | 275 |  |  | . | [5 empty] | FALSE
G0677 | 2021-04-02 10:59 |  |  |  | Slatt 500 kV Substation | WITHDRAWN | OR | Gilliam | GI | 2023-12-29 | 2028-12-29 | 400 | 400 | ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . |  |  | Available |  |  | FALSE
L0488 | 2021-03-31 | Railroad Avenue Project | Public Utility District No. 1 of Franklin County |  | Tap on the Benton-Franklin No 1 line | STUDY | WA | Franklin | LL | 2024-03-31 | 2025-06-01 | 1 | 1 |  | Other | Other | 59 | [6 empty] | 59 |  |  | . | [5 empty] | FALSE
G0676 | 2021-03-29 17:51 |  |  |  | Spring Creek Substation 230 kV | STUDY | WA | Klickitat | GI | 2024-09-01 | 2027-01-01 | 125 | 125 | NRIS & ERIS | Photovoltaic | Solar | 125 | Energy Storage | Battery | 125 |  |  |  | 250 |  |  | . | Available |  | Available |  | Available | FALSE
G0674 | 2021-03-09 14:30 |  |  |  | Ponderosa 500 kV | STUDY | OR | Crook | GI | 2030-04-03 | 2030-04-03 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0675 | 2021-03-09 14:30 |  |  |  | Ponderosa 500 kV | STUDY | OR | Crook | GI | 2029-04-03 | 2029-04-03 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0673 | 2021-03-09 14:28 |  |  |  | Ponderosa 500 kV | STUDY | OR | Crook | GI | 2028-04-03 | 2028-04-03 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0672 | 2021-03-05 06:47 |  |  |  | Midway - Grandview 115 kV | WITHDRAWN | WA | Benton | GI | 2024-10-01 | 2024-10-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 200 |  |  |  | 400 |  |  | . | Available |  |  |  |  | FALSE
G0671 | 2021-02-25 15:46 |  |  |  | Franklin - Walla Walla No 1 115kV line | STUDY | WA | Walla Walla | GI | 2025-12-01 | 2027-12-01 | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | Available |  | Available |  |  | FALSE
G0670 | 2021-02-22 14:28 |  |  | System Capacity is 500 MW. | Wautoma Substation | STUDY | WA | Benton | GI | 2025-12-31 | 2027-12-31 | 500 | 500 | NRIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . |  |  | Available |  | Available | FALSE
G0669 | 2021-02-18 12:12 |  |  |  | Ponderosa Substation 230 kV | STUDY | OR | Crook | GI | 2027-04-01 | 2027-04-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . | Available |  | Available |  |  | FALSE
L0487 | 2021-01-27 14:11 | New Camas Substation | Clark Public Utilities |  | Sifton-North Camas 115kV BES Line | WITHDRAWN | WA | Clark | LL | 2024-02-01 | 2024-02-01 | 25 | 25 |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G0668 | 2021-01-26 11:08 |  |  |  | BPA's Rocky Ford - Grand Coulee No 1 230 kV line. | STUDY | WA | Grant | GI | 2025-12-01 | 2028-01-01 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 100 |  |  |  | 500 |  |  | . | Available |  | Available |  |  | FALSE
G0667 | 2021-01-20 08:55 |  |  | Project will generate at (or less than) 100 MW at POI. | Midway - Moxee No 1 115 kV line. | WITHDRAWN | WA | Yakima | GI | 2024-10-01 | 2024-10-01 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 104 | Energy Storage | Battery | 52 |  |  |  | 156 |  |  | . | [5 empty] | FALSE
G0666 | 2021-01-13 10:06 |  |  | An increase of 3.2 MW to the existing nameplate capacity of 4.8 MW, at Finley Butte Landfill, for a total of 8 MW. | Boardman 115 kV Substation | WITHDRAWN | OR | Morrow | GI | 2021-06-30 | 2023-06-01 | 4 | 4 | ERIS | Cogeneration | Biofuel | 4 | [6 empty] | 4 |  |  | . | [5 empty] | FALSE
G0665 | 2020-12-22 16:41 |  |  | Wind 600 MW / Solar 150 MW / 375 MW Battery | Lower Granite 500kV or Central Ferry 500kV or Central Ferry 230kV | WITHDRAWN | WA | Garfield | GI | 2025-12-01 | 2028-01-01 | 750 | 750 | NRIS & ERIS | Wind Turbine | Wind Turbine | 600 | Photovoltaic | Solar | 150 | Energy Storage | Battery | 375 | 1125 |  |  | . | Available |  | Available |  |  | FALSE
G0662 | 2020-12-21 13:17 |  |  | 400 MW Solar / 200 MW Battery | Pilot Butte to Redmond 230kV or Pilot Butte to Ponderosa 230kV | STUDY | OR | Deschutes | GI | 2025-12-01 | 2027-01-01 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | Energy Storage | Battery | 200 |  |  |  | 600 |  |  | . | Available |  |  |  |  | FALSE
G0663 | 2020-12-21 13:17 |  |  | 1000 MW Solar / 500 MW Battery | Ponderosa (Grizzly) and Sand Springs 500kV tap on ckt 1 or 2 | WITHDRAWN | OR | Crook | GI | 2025-12-01 | 2027-01-01 | 700 | 700 | NRIS & ERIS | Photovoltaic | Solar | 700 | Energy Storage | Battery | 350 |  |  |  | 1050 |  |  | . | Available |  | Available |  |  | FALSE
G0664 | 2020-12-21 13:17 |  |  | 700 MW Solar / 350 MW Battery | Sand Springs to Fort Rock 500kV tap on ckt 1 or 2 | WITHDRAWN | OR | Lake | GI | 2025-12-01 | 2028-01-01 | 700 | 700 | NRIS & ERIS | Photovoltaic | Solar | 700 | Energy Storage | Battery | 350 |  |  |  | 1050 |  |  | . | Available |  | Available |  |  | FALSE
G0661 | 2020-12-15 21:24 |  |  | Total output at POI not to exceed 300 MW. | Bofer Canyon Substation | WITHDRAWN | WA | Benton | GI | 2023-10-10 | 2023-10-10 | 300 | 300 | NRIS & ERIS | Energy Storage | Battery | 150 | Photovoltaic | Solar | 300 |  |  |  | 450 |  |  | . |  |  | Available |  |  | FALSE
L0486 | 2020-12-10 | SW Highland Ave | Central Electric Cooperative, Inc. |  | CEC's 69kV transmission system | WITHDRAWN | OR | Crook | LL | 2023-06-30 | 2024-06-30 | 40 | 40 |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
L0485 | 2020-11-11 10:35 | Garden Springs | Avista Corporation |  | Bell-Coulee No. 5 230kV Txm Line | STUDY | WA | Spokane | LL | 2023-12-31 | 2023-12-31 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0660 | 2020-11-05 11:21 |  |  |  | POI 1: Grand Coulee - Rocky Ford 230 kV POI 2: Grand Coulee - Potholes 230 kV | STUDY | WA | Grant | GI | 2024-10-01 | 2028-12-29 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 100 |  |  |  | 300 |  |  | . | Available |  | Available |  | Available | FALSE
L0484 | 2020-10-07 16:11 | Spearfish Data Center | Public Utility District No. 1 of Klickitat County |  | Klickitat PUD's Spearfish Substation | WITHDRAWN | WA | Klickitat | LL | 2021-10-01 | 2022-02-14 | 100 | 100 |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0659 | 2020-10-07 15:42 | Qualco Project | Public Utility District No. 1 of Snohomish County | Installing an additional 1600 kW to an existing 450 kW generator for a total of 2.05 MW | 12.47 kV Snohomish distribution (Woods Creek Substation)/115 kV BPA-Snohomish Substation | ENERGIZED | WA | Snohomish | GI | 2021-06-01 | 2022-07-31 | 3 | 3 | ERIS | Reciprocating Engine | Biofuel | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
G0658 | 2020-10-02 15:44 |  |  | 238.5 MW request | A new 230 kV interconnection facility adjacent to BPA's Malin - Hilltop 230 kV line, south of Malin Substation | WITHDRAWN | OR | Klamath | GI | 2025-12-31 | 2025-12-31 | 239 | 239 | NRIS & ERIS | Wind Turbine | Wind Turbine | 239 | [6 empty] | 239 |  |  | . | Available |  |  |  |  | FALSE
L0482 | 2020-09-22 10:13 | Morrow Flat_Longhorn | Umatilla Electric Cooperative |  | Morrow Flat 230kV Substation | CONST AGRMT EXE | OR | Umatilla | LL | 2022-08-31 | 2025-05-01 | 500 | 500 |  | Other | Other | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
L0481 | 2020-09-22 10:07 | McNary 230kV | Umatilla Electric Cooperative |  | McNary 230kV, Bay 28 | CONST AGRMT EXE | OR | Umatilla | LL | 2022-08-31 | 2025-04-30 | 450 | 450 |  | Other | Other | 450 | [6 empty] | 450 |  |  | . | [5 empty] | FALSE
G0657 | 2020-09-16 11:36 |  |  | This is a (500 MW PV + 500 MW BESS) project, limiting the injection capability to 500 MW at the POI. | La Pine - Chiloquin No 1 line. | STUDY | OR | Klamath | GI | 2023-12-01 | 2027-01-01 | 1000 | 1000 | NRIS & ERIS | Photovoltaic | Solar | 500 | Energy Storage | Battery | 500 |  |  |  | 1000 |  |  | . | Available |  | Available |  |  | FALSE
G0656 | 2020-09-16 09:42 |  |  |  | BPA's Vantage 230 kV Substation | STUDY | WA | Grant | GI | 2023-11-30 | 2027-01-01 | 500 | 500 | NRIS & ERIS | Energy Storage | Battery | 500 | [6 empty] | 500 |  |  | . |  |  | Available |  | Available | FALSE
L0480 | 2020-09-09 16:05 | 115 kV Loop | Public Utility District No. 1 of Klickitat County |  | Rock Creek-Horseheaven | WITHDRAWN | WA | Klickitat | LL | 2023-09-09 | 2023-09-09 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0654 | 2020-08-31 14:53 |  |  | Request reduced from 200 MW to 170 MW on 6/26/2023. | La Pine - Fort Rock No 1 115 kV line. | STUDY | OR | Lake | GI | 2027-01-01 | 2027-01-01 | 170 | 170 | NRIS & ERIS | Photovoltaic | Solar | 170 | [6 empty] | 170 |  |  | . | Available |  | Available |  |  | FALSE
G0655 | 2020-08-31 14:53 |  |  |  | La Pine - Fort Rock No 1 115 kV line. | STUDY | OR | Lake | GI | 2027-01-01 | 2027-01-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | Available |  | Available |  |  | FALSE
L0478 | 2020-08-13 14:09 | East Hills Substation | South Side Electric, Inc. |  | East Hills Substation | CONST AGRMT EXE | ID | Cassia | LL | 2023-08-11 | 2025-08-01 | 6.8 | 6.8 |  | Other | Other | 6.8 | [6 empty] | 6.8 |  |  | . | [5 empty] | FALSE
L0483 | 2020-08-13 07:21 | Diesel Refinery | Clatskanie People's Utility District |  | Allston-Driscoll 115kV | STUDY | OR | Columbia | LL | 2023-08-13 | 2026-08-01 | 43 | 43 |  | Other | Other | 43 | [6 empty] | 43 |  |  | . | [5 empty] | FALSE
L0479 | 2020-08-12 10:03 | Bridge Substation | Raft River Rural Electric Cooperative, Inc. |  | Bridge Substation | CONST AGRMT EXE | ID | Cassia | LL | 2023-08-12 | 2025-12-31 | 9.8 | 9.8 |  | Other | Other | 9.8 | [6 empty] | 9.8 |  |  | . | [5 empty] | FALSE
G0653 | 2020-07-10 14:36 |  |  |  | A new 230 kV interconnection point onto BPA's existing 230 kV Allston - Clatsop transmission line at BPA pole #7102-23-1 or a new 230 kV interconnection point onto BPA's existing 230 kV system at BPA's Driscoll substation. | WITHDRAWN | OR | Clatsop | GI | 2024-12-31 | 2024-12-31 | 117 | 117 | NRIS & ERIS | Wind Turbine | Wind Turbine | 117 | [6 empty] | 117 |  |  | . | Available |  | Available |  |  | FALSE
G0652 | 2020-07-10 13:36 |  |  |  | BPA's proposed Stanfield Substation | STUDY | OR | Umatilla | GI | 2025-12-01 | 2027-01-01 | 250 | 250 | NRIS & ERIS | Photovoltaic | Solar | 150 | Energy Storage | Battery | 100 |  |  |  | 250 |  |  | . |  |  | Available |  | Available | FALSE
G0651 | 2020-07-08 15:38 |  |  |  | Grizzly-Summer Lake No 1 500 kV line | STUDY | OR | Lake | GI | 2023-09-30 | 2027-01-01 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | [6 empty] | 400 |  |  | . | Available |  | Available |  | Available | FALSE
G0650 | 2020-07-06 08:02 |  |  |  | 500 kV Substation, approximately 21 miles from G0650 Generation Station. | WITHDRAWN | MT | Silver Bow | GI | 2025-12-31 | 2025-12-31 | 542 | 576 | NRIS & ERIS | Steam Turbine | Natural Gas | 576 | [6 empty] | 576 |  |  | . | Available |  | Available |  |  | FALSE
L0477 | 2020-07-03 13:37 | Cherry Point Load | Public Utility District No. 1 of Whatcom County |  | Either Custer 230 kV or Intalco 230 kV | WITHDRAWN | WA | Whatcom | LL | 2024-07-06 | 2024-07-01 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0649 | 2020-06-29 09:50 |  |  |  | Loop into Jones Canyon - Santiam 230 kV line, .1 mile East of Hwy 26 | WITHDRAWN | OR | Wasco | GI | 2023-06-01 |  | 641 | 641 | NRIS & ERIS | Photovoltaic | Solar | 641 | [6 empty] | 641 |  |  | . | [5 empty] | FALSE
G0648 | 2020-05-29 14:59 |  |  | 1100 Battery with 300 MW Solar charging the battery, with 1100 total AC/DC Inverter. | Captain Jack 500 kV Substation | STUDY COMPLETED | OR | Klamath | GI | 2026-12-31 | 2024-11-01 | 1100 | 1100 | NRIS & ERIS | Energy Storage | Battery | 1100 | Photovoltaic | Solar | 300 |  |  |  | 1400 |  |  | . | Available |  | Available |  | Available | FALSE
G0647 | 2020-05-18 15:46 |  |  | 360 MW Solar/200 MW Energy Storage | Wautoma 500 kV Switchyard | WITHDRAWN | WA | Benton | GI | 2023-12-31 | 2023-12-31 | 560 | 560 | ERIS | Photovoltaic | Solar | 360 | Energy Storage | Battery | 200 |  |  |  | 560 |  |  | . | Available |  |  |  |  | FALSE
L0476 | 2020-05-11 14:24 | Conser 115kV | PacifiCorp |  | BPA Salem-Albany 115kV | STUDY | OR | Marion | LL | 2022-05-01 | 2025-06-30 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0475 | 2020-05-11 14:03 | Lyons Loop | PacifiCorp |  | BPA Santiam 69kV Tap Line | STUDY | OR | Marion | LL | 2023-05-01 | 2025-05-01 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0474 | 2020-04-21 10:02 | St. Johns Substation | PacifiCorp |  | BPA's St. Johns Substation | STUDY | OR | Multnomah | LL | 2023-04-28 | 2025-04-28 | 0 | 0 | [10 empty] | 0 |  |  | . | [5 empty] | FALSE
G0646 | 2020-04-01 13:18 |  |  | 50 MW Solar | Oregon Trail Electric Coop 69kV transmission line | WITHDRAWN | OR | Union | GI | 2023-12-31 | 2023-12-31 | 50 | 50 | ERIS | Solar Thermal | Solar | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0644 | 2020-03-23 10:15 |  |  | 100 MW Storage | McNary - John Day 500 kV line. | WITHDRAWN | WA | Klickitat | GI | 2023-12-21 | 2023-12-21 | 100 | 100 | NRIS & ERIS | Energy Storage | Battery | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0645 | 2020-03-23 10:15 |  |  | Solar | McNary-John Day 500kV Tap (BPA's "G0585 Substation") | STUDY COMPLETED | WA | Klickitat | GI | 2026-01-31 | 2026-12-21 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . |  |  | Available |  | Available | FALSE
G0642 | 2020-02-24 14:42 |  |  | 600 MW Battery Storage | Ponderosa 230 kV | STUDY | OR | Crook | GI | 2025-06-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . |  |  | Available |  |  | FALSE
G0643 | 2020-02-24 14:34 |  |  |  | Ponderosa 230 kV | STUDY | OR | Crook | GI | 2024-06-01 | 2027-01-01 | 600 | 600 | NRIS & ERIS | Energy Storage | Battery | 600 | [6 empty] | 600 |  |  | . |  |  | Available |  |  | FALSE
G0641 | 2020-02-20 10:43 |  |  |  | Sickler 500 kV Substation | WITHDRAWN | WA | Douglas | GI | 2026-12-01 | 2027-01-01 | 500 | 500 | NRIS & ERIS | Energy Storage | Pumped-Storage Hydro | 500 | [6 empty] | 500 |  |  | . | Available |  |  |  |  | FALSE
G0640 | 2020-02-10 10:23 |  |  | 238.5 MW Request | Option I: New 230 kV point onto BPA's existing 500 kV Captain Jack Substation; Option 2: New 230 kV point onto BPA's existing Malin Substation; Option 3: New 230 kV facility adjacent to BPA's Malin Hilltop 230 kV line, approx. adjacent to the Malin Substation | STUDY | OR | Klamath | GI | 2025-12-31 | 2028-01-01 | 239 | 239 | NRIS & ERIS | Wind Turbine | Wind Turbine | 239 | [6 empty] | 239 |  |  | . | Available |  | Available |  |  | FALSE
G0639 | 2020-02-03 10:01 |  |  | Solar / Battery Storage | BPA's Rocky Reach - Columbia 230 kV line. | STUDY | WA | Douglas | GI | 2023-08-01 | 2027-01-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | Available |  | Available |  |  | FALSE
G0638 | 2020-01-28 13:36 |  |  |  | Knight 500 kV Substation | WITHDRAWN | WA | Klickitat | GI | 2022-12-31 | 2022-12-31 | 190 | 190 | NRIS & ERIS | Energy Storage | Battery | 190 | [6 empty] | 190 |  |  | . | [5 empty] | FALSE
G0637 | 2020-01-28 13:35 |  |  |  | Knight 500 kV Substation | STUDY COMPLETED | WA | Klickitat | GI | 2022-12-31 | 2026-12-31 | 190 | 190 | NRIS & ERIS | Energy Storage | Battery | 190 | [6 empty] | 190 |  |  | . | Available |  | Available |  | Available | FALSE
G0636 | 2020-01-08 16:05 |  |  |  | Longhorn 230 kV Substation | WITHDRAWN | OR | Morrow | GI | 2023-11-15 | 2023-11-15 | 350 | 350 | NRIS & ERIS | Photovoltaic | Solar | 350 | [6 empty] | 350 |  |  | . | [5 empty] | FALSE
G0635 | 2020-01-07 15:12 |  |  |  | Franklin - McNary 230 KV transmission line. | STUDY COMPLETED | WA | Benton | GI | 2021-10-01 | 2026-03-31 | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | Available |  | Available |  | Available | FALSE
L0472 | 2019-12-20 17:17 | Project Bald Eagle | Clark Public Utilities |  | BPA Sifton Substation | WITHDRAWN | WA | Clark | LL | 2022-11-01 | 2022-09-01 | 230 | 230 |  | Other | Other | 230 | [6 empty] | 230 |  |  | . | [5 empty] | FALSE
L0473 | 2019-12-17 07:10 | Jordan Cove | PacifiCorp |  | CLPUD Glascow to Jordan Point 115 kV Line | WITHDRAWN | OR | Coos | LL | 2023-10-01 | 2023-10-01 | 26 | 26 |  | Other | Other | 26 | [6 empty] | 26 |  |  | . | [5 empty] | FALSE
L0471 | 2019-12-17 07:03 | Green Apple | Public Utility District No. 1 of Whatcom County |  | Bellingham Substation 115 kV | WITHDRAWN | WA | Whatcom | LL | 2023-01-01 | 2023-01-01 | 35 | 35 |  | Other | Other | 35 | [6 empty] | 35 |  |  | . | [5 empty] | FALSE
G0634 | 2019-12-13 13:12 |  |  | Solar PV modules with integrated DC storage. | Columbia - Ellensburg No 1 115 kV line | WITHDRAWN | WA | Kittitas | GI | 2021-12-01 | 2022-05-01 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | Available |  | Available |  |  | FALSE
G0633 | 2019-12-03 07:31 |  |  | A hybrid project that consists of Wind, Solar and Energy Storage. | Ashe - Marion No 2 500 kV transmission line, approximately 83 miles from Ashe Substation. | WITHDRAWN | OR | Gilliam | GI | 2023-10-01 | 2023-10-01 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . | Available |  |  |  |  | FALSE
L0470 | 2019-11-15 12:00 | New Rail Loop Load | Clark Public Utilities |  | TBD | WITHDRAWN | WA | Clark | LL | 2022-11-15 | 2022-11-15 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0632 | 2019-11-04 12:49 |  |  |  | BPA's Vantage 230 kV Substation | WITHDRAWN | WA | Grant | GI | 2022-11-30 | 2022-11-30 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | [6 empty] | 300 |  |  | . | Available |  |  |  |  | FALSE
G0631 | 2019-11-04 08:56 | Decatur Island Battery Storage | Orcas Power & Light Cooperative | Submitted as a 1.5 MW Request | Decatur Substation | ENERGIZED | WA | San Juan | GI | 2018-06-15 | 2021-03-01 | 2 | 2 | ERIS | Energy Storage | Battery | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
L0469 | 2019-10-31 07:53 | Clifton Ridge | Public Utility District No. 3 of Mason County |  | Shelton-Kitsap #2 115 kV Line | WITHDRAWN | WA | Mason | LL | 2022-11-01 | 2022-11-01 | 40 | 40 |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
G0630 | 2019-10-28 14:14 |  |  | 3/30/20: Request reduced from 350 MW to 300 MW | BPA's Anaconda Substation via 230 kV transmission line. | WITHDRAWN | MT | Deer Lodge | GI | 2022-12-15 | 2022-12-15 | 300 | 300 | NRIS & ERIS | Photovoltaic | Solar | 300 | [6 empty] | 300 |  |  | . | Available |  |  |  |  | FALSE
L0468 | 2019-10-09 10:18 | Rural Substation | United Electric Co-op, Inc. |  | BPA Heyburn-Adelaide Pole 6/2 or 6/3 | CONST AGRMT EXE | ID | Minidoka | LL | 2022-09-30 | 2024-08-30 | 7.1 | 7.1 |  | Other | Other | 7.1 | [6 empty] | 7.1 |  |  | . | [5 empty] | FALSE
L0467 | 2019-09-18 14:47 | Huard Road | Benton Rural Electric Association |  | Prosser Tap on the Grandview-Red Mountain 115 kV line | CONST AGRMT EXE | WA | Benton | LL | 2021-08-01 | 2023-09-30 | 10.2 | 10.2 |  | Other | Other | 10.2 | [6 empty] | 10.2 |  |  | . | [5 empty] | FALSE
G0629 | 2019-09-03 17:03 |  |  |  | Midway - Moxee 115 kV transmission line. | STUDY COMPLETED | WA | Benton | GI | 2024-10-31 | 2027-01-01 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | [6 empty] | 100 |  |  | . | Available |  | Available |  | Available | FALSE
G0628 | 2019-08-06 12:30 |  |  |  | Vantage - Schultz No 1 500 kV, or Bettas - Columbia No 1 230 kV | WITHDRAWN | WA | Kittitas | GI | 2022-12-31 | 2022-12-31 | 125 | 125 | NRIS & ERIS | Photovoltaic | Solar | 125 | [6 empty] | 125 |  |  | . | [5 empty] | FALSE
G0627 | 2019-07-29 16:01 |  |  |  | TBD | WITHDRAWN | WA | Klickitat | GI | 2021-12-31 | 2021-12-31 | 45 | 45 | NRIS & ERIS | Photovoltaic | Solar | 45 | [6 empty] | 45 |  |  | . | [5 empty] | FALSE
L0465 | 2019-07-19 14:00 | Port Angeles Substation | City of Port Angeles |  | BPA Port Angeles Substation | STUDY | WA | Clallam | LL | 2022-10-03 | 2022-10-03 | 50 | 50 |  | Other | Other | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
L0464 | 2019-07-18 16:00 | Duckabush | Public Utility District No. 1 of Mason County |  | Duckabush Substation | STUDY | WA | Mason | LL | 2022-10-03 | 2022-10-03 | 10 | 10 |  | Other | Other | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0466 | 2019-07-18 08:24 | T3ba'das Substation | Public Utility District No. 1 of Mason County |  | Olympia Potlatch 115 kV line | STUDY | WA | Mason | LL | 2022-10-03 | 2022-10-03 | 10 | 10 |  | Other | Other | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0463 | 2019-07-17 13:12 | Deer Island Substation | Columbia River People's Utility District |  | Alston-St. Helens 115 kV | CONST AGRMT EXE | OR | Columbia | LL | 2022-10-03 | 2024-09-30 | 25 | 25 |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
L0462 | 2019-07-02 10:16 | Gateway Substation | City of Richland, Washington | Project name changed from Kingsgate to Oscar per customer. 10/18/19 Customer changed the name of the substation from Oscar to Gateway 3/3/2020. | White Bluffs to Snyder Transmission Line | STUDY | WA | Benton | LL | 2021-10-01 | 2023-04-01 | 25 | 25 |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G0626 | 2019-06-27 15:33 |  |  |  | Vantage Substation 230 kV | STUDY COMPLETED | WA | Grant | GI | 2022-12-31 | 2027-10-01 | 90 | 90 | NRIS & ERIS | Photovoltaic | Solar | 90 | [6 empty] | 90 |  |  | . |  |  | Available |  | Available | FALSE
L0461 | 2019-06-22 08:55 | Alderwood Tap Line | Emerald People's Utility District | Joint project with Blachly Lane Electric Cooperative |  | STUDY | OR | Lane | LL | 2021-10-01 | 2026-01-01 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0625 | 2019-06-05 17:06 |  |  | Including a 100 MW battery energy storage system. Maximum generating capacity for solar and battery system combined would never exceed 200 MW, alternating current at the POI. | BPA's McNary Substation | STUDY | OR | Morrow | GI | 2020-12-31 | 2027-01-01 | 191 | 191 | NRIS & ERIS | Photovoltaic | Solar | 191 | [6 empty] | 191 |  |  | . | Available |  | Available |  | Available | FALSE
G0624 | 2019-05-31 11:15 |  |  | Maximum Total Output 1250 MW. Wind 1250 MW; Solar 750 MW; Battery Storage 563; Natural Gas 1250 MW. | Central Ferry Substation | WITHDRAWN | WA | Garfield | GI | 2023-10-31 | 2023-10-31 | 3813 | 3813 | NRIS & ERIS | Photovoltaic | Solar | 1250 | [6 empty] | 1250 |  |  | . | Available |  |  |  |  | FALSE
G0623 | 2019-05-01 12:24 |  |  |  | BPA's La Pine - Fort Rock 115 kV transmission line. | WITHDRAWN | OR | Lake | GI | 2021-10-01 | 2021-10-01 | 30 | 30 | NRIS | Photovoltaic | Solar | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
L0460 | 2019-04-29 13:01 | Carborundum Substation Upgrade | Clark Public Utilities | Withdrawn by customer | Ross-Carborundum No. 1 115 kV | WITHDRAWN | WA | Clark | LL | 2023-01-01 | 2023-01-01 | 120 | 120 |  | Other | Other | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
L0459 | 2019-04-29 12:54 | Thurston Switching Station | Eugene Water & Electric Board |  | SANT ALVY Lines 1 and 2 | STUDY | OR | Lane | LL | 2022-10-03 | 2025-04-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0622 | 2019-04-12 11:59 | Grays Harbor Project | Grays Harbor Energy LLC |  | Satsop 230 kV Substation | ENERGIZED | WA | Grays Harbor | GI | 2020-10-01 | 2021-05-31 | 39 | 9 | NRIS | Other | Other | 39 | [6 empty] | 39 | Transition Cluster |  | . |  |  | Available |  | Available | FALSE
L0458 | 2019-04-11 10:00 | Fusion | City of Richland, Washington |  | White Bluffs to Benton Switch | STUDY | WA | Benton | LL | 2022-10-01 | 2028-06-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0620 | 2019-04-11 09:30 |  |  |  | Coyote Springs Substation | STUDY | OR | Umatilla | GI | 2019-10-31 | 2025-12-31 | 27 | 27 | ERIS | Combined Cycle | Natural Gas | 27 | [6 empty] | 27 |  |  | . |  |  | Available |  | Available | FALSE
G0619 | 2019-04-10 17:53 |  |  |  | Primary: Slatt to John Day 500 kV transmission line. Alternate: Diamond Butte Substation | STUDY | OR | Wasco | GI | 2023-12-31 | 2027-12-27 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . | Available |  | Available |  | Available | FALSE
G0617 | 2019-03-22 16:13 |  |  | 200 MW solar facility with a 100/4hr battery, generating a max of 200 MW at POI. | John Day No 2 230 kV transmission line or Biglow Canyon Substation. | STUDY | OR | Sherman | GI | 2022-08-01 | 2026-11-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | Energy Storage | Battery | 100 |  |  |  | 300 |  |  | . |  |  | Available |  |  | FALSE
G0618 | 2019-03-22 16:13 | Klondike II Repower | Klondike Wind Power II, LLC | This is an incremental increase in nameplate capacity to G096, not an increase in the injected power as described in the LGIA. | BPA's John Day 230 kV | ENERGIZED | OR | Sherman | GI | 2020-12-31 | 2020-08-31 | 6 | 6 | ERIS | Wind Turbine | Wind Turbine | 6 | [6 empty] | 6 |  |  | . |  |  | Available |  |  | FALSE | TRUE
G0616 | 2019-02-22 12:10 | Coyote Springs 2 | Avista Corporation | Increase of 42 MW (from 280 MW to 322 MW) of available capacity to the existing Coyote Springs 2 project. | Coyote Springs Switchyard | ENERGIZED | OR | Morrow | GI | 2019-06-24 | 2020-08-18 | 42 | 42 | ERIS | Combined Cycle | Natural Gas | 42 | [6 empty] | 42 |  |  | . |  |  | Available |  |  | FALSE
G0615 | 2019-02-21 12:23 |  |  |  | Slatt - Buckley No 1 500 kV transmission line, approximately 10 miles from Buckley Substation. | STUDY COMPLETED | OR | Sherman | GI | 2021-12-31 | 2027-04-30 | 800 | 800 | NRIS & ERIS | Photovoltaic | Solar | 800 | Energy Storage | Battery | 400 |  |  |  | 1200 |  |  | . | Available |  | Available |  | Available | FALSE
L0457 | 2019-02-11 14:00 | Bridge Substation | Raft River Rural Electric Cooperative, Inc. |  | BPA Bridge Substation | WITHDRAWN | ID | Cassia | LL | 2022-03-01 | [13 empty] | 0 |  |  | . | [5 empty] | FALSE
L0456 | 2019-02-08 11:00 | Thatcher Substation | City of Forest Grove |  | Forest Grove's Filbert Substation | WITHDRAWN | OR | Washington | LL | 2022-03-01 | 2020-04-13 | 20 | 20 |  | Other | Other | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0455 | 2019-01-23 08:36 | LaPorte | Big Bend Electric Cooperative, Inc. |  | Benton-Franklin #1 115 kV Transmission Line | CONST AGRMT EXE | WA | Benton | LL | 2024-01-01 | 2024-01-15 | 7.2 | 7.2 |  | Other | Other | 7.2 | [6 empty] | 7.2 |  |  | . | [5 empty] | FALSE
G0614 | 2019-01-22 08:34 |  |  |  | McNary - John Day No 2 500 kV or Wautoma - Rock Creek No 1 500 kV transmission lines. | WITHDRAWN | WA | Klickitat | GI | 2021-12-31 | 2021-12-31 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . | Available |  |  |  |  | FALSE
G0613 | 2019-01-18 12:05 |  |  |  | BPA's 115 kV La Pine - Fort Rock transmission line. | WITHDRAWN | OR | Lake | GI | 2021-10-01 | 2021-10-01 | 10 | 10 | ERIS | Photovoltaic | Solar | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0612 | 2019-01-04 13:28 |  |  | Request reduced to 127 MW from 202.34 MW on 4/16/19. Request reduced, via material modification analysis, from 127 MW to 75 MW on 6/30/2020. | EE Clouse - Harvalum 230 kV transmission line. | WITHDRAWN | WA | Klickitat | GI | 2021-12-31 | 2021-12-31 | 75 | 75 | NRIS & ERIS | Photovoltaic | Solar | 75 | [6 empty] | 75 |  |  | . | Available |  | Available |  |  | FALSE
G0611 | 2019-01-04 13:23 |  |  | 312.5 MW request | KPUD's Harvest 230 kV Substation | WITHDRAWN | WA | Klickitat | GI | 2021-12-31 | 2021-12-31 | 313 | 313 | NRIS & ERIS | Wind Turbine | Wind Turbine | 313 | [6 empty] | 313 |  |  | . | [5 empty] | FALSE
G0610 | 2019-01-04 10:18 |  |  |  | John Day 500 kV Substation | WITHDRAWN | OR | Sherman | GI | 2021-12-31 | 2021-12-31 | 450 | 450 | NRIS & ERIS | Photovoltaic | Solar | 450 | [6 empty] | 450 |  |  | . | [5 empty] | FALSE
G0609 | 2018-12-21 14:00 |  |  |  | Troutdale 230kV Substation | STUDY COMPLETED | OR | Multnomah | GI | 2021-12-31 | 2026-06-01 | 400 | 400 | NRIS & ERIS | Energy Storage | Battery | 400 | [6 empty] | 400 |  |  | . |  |  | Available |  | Available | FALSE
G0608 | 2018-12-07 14:07 |  |  |  | BPA's John Day 500 kV Substation | STUDY | WA | Klickitat | GI | 2027-12-31 | 2027-12-31 | 1200 | 1200 | NRIS & ERIS | Energy Storage | Battery | 1200 | [6 empty] | 1200 |  |  | . | Available |  | Available |  |  | FALSE
G0607 | 2018-12-06 14:17 |  |  |  | BPA's Malin 500 kV Substation | WITHDRAWN | OR | Klamath | GI | 2025-12-21 | 2025-12-21 | 394 | 394 | NRIS & ERIS | Energy Storage | Battery | 394 | [6 empty] | 394 |  |  | . | Available |  | Available |  |  | FALSE
G0606 | 2018-12-02 11:47 | Rock Creek Hydro Project | Rock Creek Hydro LLC | Request seeks 390 kW. | Round Valley Substation | ENERGIZED | ID | Custer | GI | 2019-04-01 | 2019-09-01 | 1 | 1 | ERIS | Hydro | Water | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0454 | 2018-11-20 08:40 | Morrow Flat | Umatilla Electric Cooperative |  | BPA Morrow Flat Substation | BPA COMPLETED | OR | Morrow | LL | 2019-12-31 | 2022-04-29 | 120 | 120 |  | Other | Other | 120 | [6 empty] | 120 |  |  | . | [5 empty] | FALSE
G0605 | 2018-11-14 13:58 | Blueridge Solar/Battery Project | Wheatridge Solar Energy Center, LLC | Request to install additional 50 MW of solar and 30 MW of battery storage to the existing G0365 project. Total output will remain at 300 MW. | BPA's Morrow Flat 230 kV Bus | ENERGIZED | OR | Morrow | GI | 2020-12-31 | 2022-03-10 | 80 | 80 | NRIS | Photovoltaic | Solar | 50 | Energy Storage | Battery | 30 |  |  |  | 80 |  |  | . |  |  | Available |  |  | FALSE
G0604 | 2018-10-19 12:24 |  |  |  | TBD | WITHDRAWN | WA | Yakima | GI | 2022-12-15 |  | 115 | 115 | NRIS & ERIS | Photovoltaic | Solar | 115 | [6 empty] | 115 |  |  | . | [5 empty] | FALSE
G0603 | 2018-10-19 12:18 |  |  |  | Central Ferry Substation | WITHDRAWN | WA | Garfield | GI | 2022-12-15 | 2022-12-15 | 275 | 275 | NRIS & ERIS | Photovoltaic | Solar | 275 | [6 empty] | 275 |  |  | . | [5 empty] | FALSE
G0602 | 2018-10-17 14:52 |  |  | Request reduced to 170 MW. | Vantage Substation 230 kV | STUDY COMPLETED | WA | Grant | GI | 2022-12-31 | 2027-10-01 | 170 | 170 | NRIS & ERIS | Photovoltaic | Solar | 170 | [6 empty] | 170 |  |  | . | Available |  | Available |  | Available | FALSE
L0453 | 2018-10-03 09:32 | Midway 230 kV | Public Utility District No. 2 of Grant County, Washington | Withdrawn by customer. | BPA Midway 230 kV Substation | WITHDRAWN | WA | Benton | LL | 2021-10-03 | 2021-10-03 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0601 | 2018-09-26 10:52 |  |  |  | Boardman Substation and McNary 115 kV | WITHDRAWN | OR | Morrow | GI | 2019-12-31 | 2020-12-31 | 14 | 14 | ERIS | Photovoltaic | Solar | 14 | [6 empty] | 14 |  |  | . | Available |  |  |  |  | FALSE
L0452 | 2018-09-09 18:00 | Keeler Substation | Portland General Electric Company |  | BPA's Keeler Substation | CONST AGRMT EXE | OR | Washington | LL | 2021-09-09 | 2024-05-01 | 1000 | 1000 |  | Other | Other | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
L0451 | 2018-09-06 16:00 | McKinley Load | City of Port Angeles | Withdrawn by customer. | BPA Port Angeles Substation | WITHDRAWN | WA | Clallam | LL | 2021-09-06 | 2019-09-30 | 40 | 40 |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
L0450 | 2018-08-29 14:00 | Kinzua Substation | Columbia Basin Electric Cooperative, Inc. | Withdrawn by the customer | Boardman to Ione 69 kV Feeder | WITHDRAWN | OR | Morrow | LL | 2019-06-01 | 2025-01-01 | 60 | 60 |  | Other | Other | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
G0600 | 2018-08-14 11:00 |  |  | 80 MWac PV system with 28 MWac/112MWh battery storage |  | WITHDRAWN | WA | Grant | GI | 2021-12-31 | 2021-12-31 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | Energy Storage | Battery | 28 |  |  |  | 108 |  |  | . |  |  | Available |  |  | FALSE
G0599 | 2018-08-07 12:04 |  |  | 450 MW solar + 95MW/4h battery; 450 MW interconnection limit | BPA's Knight 500 kV Substation | WITHDRAWN | WA | Klickitat | GI | 2021-12-31 |  | 450 | 450 | NRIS & ERIS | Photovoltaic | Solar | 450 | Energy Storage | Battery | 95 |  |  |  | 545 |  |  | . | [5 empty] | FALSE
G0598 | 2018-08-01 11:17 |  |  |  | BPA's North Bonneville - Midway 230 kV line. | STUDY | WA | Klickitat | GI | 2021-12-31 | 2028-03-01 | 160 | 160 | NRIS & ERIS | Photovoltaic | Solar | 160 | Energy Storage | Battery | 63 |  |  |  | 223 |  |  | . | Available |  | Available |  | Available | FALSE
G0597 | 2018-08-01 11:11 |  |  |  | BPA's Columbia - Covington 230 kV line. | WITHDRAWN | WA | Kittitas | GI | 2021-12-31 | 2021-12-31 | 160 | 160 | NRIS & ERIS | Photovoltaic | Solar | 160 | Energy Storage | Battery | 63 |  |  |  | 223 |  |  | . | Available |  |  |  |  | FALSE
G0596 | 2018-07-31 11:25 |  |  | 80 MW solar + 32 MW/4h battery; 80 MW interconnection limit | BPA's Midway - Moxee 115 kV line | STUDY COMPLETED | WA | Yakima | GI | 2021-12-31 | 2026-12-29 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | Energy Storage | Battery | 32 |  |  |  | 112 |  |  | . |  |  | Available |  | Available | FALSE
G0595 | 2018-07-20 10:31 |  |  | 306.6 MW Request | BPA's Satsop 230 kV Substation | WITHDRAWN | WA | Lewis | GI | 2022-12-15 | 2022-12-15 | 307 | 307 | NRIS & ERIS | Wind Turbine | Wind Turbine | 307 | [6 empty] | 307 |  |  | . |  |  |  |  | Available | FALSE
G0594 | 2018-07-18 11:28 |  |  | Generator Nameplate Rating: 280 kW | EWEB's system. Exact location TBD. | STUDY | OR | Lane | GI | 2018-09-21 | 2022-12-30 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0449 | 2018-07-18 07:00 | Amnet | Flathead Electric Cooperative, Inc. | Withdrawn by customer | BPA's Conkelley Substation | WITHDRAWN | MT | Flathead | LL | 2018-10-01 | 2018-10-01 | 70 | 70 |  | Other | Other | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
L0448 | 2018-06-26 17:00 | Briones | PacifiCorp |  | PAC system downstream from BPA Ponderosa Substation | STUDY | OR | Crook | LL | 2021-06-01 | 2026-12-31 | 120 | 120 |  | Other | Other | 103 | [6 empty] | 103 |  |  | . | [5 empty] | FALSE
G0593 | 2018-06-26 10:12 | Arlington Microgrid | Public Utility District No. 1 of Snohomish County | 1.5 MW Request. 500 kW AC solar array; 1 MW battery storage. | BPA's Murray Substation | ENERGIZED | WA | Snohomish | GI | 2019-06-21 | 2021-09-01 | 2 | 2 | ERIS | Photovoltaic | Solar | 0 | Energy Storage | Battery | 1 |  |  |  | 1 |  |  | . | [5 empty] | FALSE
L0447 | 2018-06-21 15:45 | Oregon Mines | City of Cascade Locks | Withdrawn by customer | BPA Cascade Locks 115 kV | WITHDRAWN | OR | Hood River | LL | 2018-09-01 |  | 4 | 4 |  | Other | Other | 4 | [6 empty] | 4 |  |  | . | [5 empty] | FALSE
L0446 | 2018-06-14 08:00 | Rainbow Energy | Flathead Electric Cooperative, Inc. | Withdrawn by customer | Conkelley Substation | WITHDRAWN | MT | Flathead | LL | 2018-10-31 | 2021-06-14 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0591 | 2018-06-01 15:54 |  |  | 101.88 MW Request. Modified down to 50 on 1/7/22. Combined with Wheat Field Wind Power no increase in power injected into the transmission system. | Wheat Field Wind Power Project switchyard, 230 kV bus, interfacing with BPA's Jones Canyon Substation. | WITHDRAWN | OR | Gilliam | GI | 2021-10-31 | 2023-12-31 | 0 | 0 | ERIS | Photovoltaic | Solar | 50 | [6 empty] | 50 |  |  | . |  |  | Available |  | Available | FALSE
G0592 | 2018-06-01 15:54 |  |  |  | TBD | WITHDRAWN | OR | Harney | GI | 2021-10-31 | 2021-10-31 | 40 | 40 | NRIS & ERIS | Photovoltaic | Solar | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
G0590 | 2018-05-30 10:51 |  |  |  | Grizzly-Summer Lake 500 kV or Grizzly-Captain Jack 500 kV line. | WITHDRAWN | OR | Lake | GI | 2021-07-01 | 2021-07-01 | 600 | 600 | NRIS & ERIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0589 | 2018-05-25 06:59 |  |  | Submitted as a 380.16 MW solar project | Knight 500 kV Substation | STUDY COMPLETED | WA | Klickitat | GI | 2023-12-31 | 2026-12-31 | 381 | 381 | NRIS & ERIS | Photovoltaic | Solar | 381 | [6 empty] | 381 |  |  | . |  |  |  |  | Available | FALSE
G0588 | 2018-05-22 09:24 |  |  |  | 47.7228 Lat; -119.1377 Lon | WITHDRAWN | WA | Grant | GI | 2020-11-30 | 2020-11-30 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
L0445 | 2018-05-14 14:00 | Phillips Substation | Public Utility District No. 1 of Benton County |  | Benton PUD's 115 kV line which is connected to BPA's Franklin-Hedges #1 115kV line | WITHDRAWN | WA | Franklin | LL | 2021-10-01 | 2021-10-01 | 27.4 | 27.4 |  | Other | Other | 27.4 | [6 empty] | 27.4 |  |  | . | [5 empty] | FALSE
G0587 | 2018-04-11 08:37 | Decatur Island Solar | Orcas Power & Light Cooperative | Submitted as a 350 kW request | Decatur Substation | ENERGIZED | WA | San Juan | GI | 2018-06-15 | 2018-08-01 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0586 | 2018-04-06 12:06 |  |  |  | BPA's Spring Creek 230 kV Substation. | STUDY COMPLETED | WA | Klickitat | GI | 2022-06-15 | 2025-05-01 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | [6 empty] | 100 |  |  | . |  |  | Available |  | Available | FALSE
L0443 | 2018-04-05 11:19 | Chamberlain Road | Public Utility District No. 1 of Klickitat County | Withdrawn by customer | KPUD Energizer Substation | WITHDRAWN | WA | Klickitat | LL | 2021-10-01 | 2021-10-01 | 10 | 10 |  | Other | Other | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0444 | 2018-04-05 08:08 | Wilkins | Public Utility District No. 1 of Klickitat County | Withdrawn by customer | KPUD's Energizer Substation | WITHDRAWN | WA | Klickitat | LL | 2021-10-01 | 2021-10-01 | 20 | 20 |  | Other | Other | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0442 | 2018-03-22 15:22 | Herman Substation | Big Bend Electric Cooperative, Inc. |  | Hatton Tap 8/9 | WITHDRAWN | WA | Adams | LL | 2021-10-01 | 2021-10-01 | 38.7 | 38.7 |  | Other | Other | 38.7 | [6 empty] | 38.7 |  |  | . | [5 empty] | FALSE
L0441 | 2018-03-21 11:00 | United Electric Line Tap | United Electric Co-op, Inc. | Withdrawn by customer | Haymill-Adelaid Line at 7/2 | WITHDRAWN | ID | Cassia | LL | 2021-03-21 | 2021-03-21 | 8.1 | 8.1 |  | Other | Other | 8.1 | [6 empty] | 8.1 |  |  | . | [5 empty] | FALSE
G0585 | 2018-03-19 08:04 |  |  | 312.48 MW request | McNary-John Day 500kV Tap (BPA's "G0585 Substation") | STUDY | WA | KIickitat | GI | 2021-07-01 | 2027-12-30 | 313 | 313 | NRIS & ERIS | Wind Turbine | Wind Turbine | 313 | [6 empty] | 313 |  |  | . |  |  | Available |  | Available | FALSE
G0584 | 2018-03-19 08:01 |  |  |  | Horse Heaven - Harvalum 230 kV line | WITHDRAWN | WA | Klickitat | GI | 2021-07-01 | 2021-07-01 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | [6 empty] | 100 |  |  | . |  |  | Available |  |  | FALSE
L0440 | 2018-03-16 10:00 | Edison Substation | Public Utility District No. 1 of Benton County |  | Benton PUD's Franklin-Angus #1 115 kV Line | STUDY | WA | Franklin | LL | 2022-10-31 | 2024-10-31 | 28 | 28 |  | Other | Other | 28 | [6 empty] | 28 |  |  | . | [5 empty] | FALSE
L0439 | 2018-03-07 09:00 | Mint Farm Load Increase | Public Utility District No. 1 of Cowlitz County | Withdrawn by customer | Cowlitz PUD's Mint Farm Substation | WITHDRAWN | WA | Cowlitz | LL | 2021-03-07 | 2021-03-07 | 21 | 21 |  | Other | Other | 21 | [6 empty] | 21 |  |  | . | [5 empty] | FALSE
L0438 | 2018-03-06 09:00 | Dayton Substation | Columbia Rural Electric Association | Withdrawn by customer | Dayton Substation | WITHDRAWN | WA | Columbia | LL | 2021-03-06 | 2021-03-06 | 40 | 40 |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
L0437 | 2018-03-05 16:00 | White Creek | Public Utility District No. 1 of Klickitat County | Withdrawn by customer | KPUD's White Creek Substation | WITHDRAWN | WA | Klickitat | LL | 2021-03-06 | 2021-03-06 | 20 | 20 |  | Other | Other | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0583 | 2018-03-02 09:42 |  |  |  | Ashe - Marion 500 kV transmission line | WITHDRAWN | OR | Jefferson | GI | 2021-03-15 | 2021-03-15 | 1000 | 1000 | NRIS & ERIS | Photovoltaic | Solar | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
L0435 | 2018-02-23 13:00 | EE Clouse Substation | Public Utility District No. 1 of Klickitat County | Withdrawn by customer | KPUD EE Clouse 12.5kV Substation | WITHDRAWN | WA | Klickitat | LL | 2021-02-23 | 2021-02-23 | 25 | 25 |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
L0436 | 2018-02-23 13:00 | Harvalum | Public Utility District No. 1 of Klickitat County |  | Harvalum Substation | CONST AGRMT EXE | WA | Klickitat | LL | 2021-02-23 | 2024-12-31 | 160 | 160 |  | Other | Other | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
L0434 | 2018-02-23 13:00 | John Day | Public Utility District No. 1 of Klickitat County | Withdrawn by customer | KPUD's John Day 13.8 kV Substation | WITHDRAWN | OR | Wasco | LL | 2021-02-23 | 2021-02-23 | 8 | 8 |  | Other | Other | 8 | [6 empty] | 8 |  |  | . | [5 empty] | FALSE
G0582 | 2018-02-23 10:05 |  |  |  | Grand Coulee - Creston 115 kV line. | WITHDRAWN | WA | Lincoln | GI | 2020-06-15 | 2020-06-15 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0581 | 2018-02-22 12:55 |  |  | 400.6 MW Request | Morrow Flats 230 kV station | WITHDRAWN | OR | Morrow | GI | 2020-12-31 | 2023-12-31 | 401 | 401 | NRIS & ERIS | Wind Turbine | Wind Turbine | 401 | [6 empty] | 401 |  |  | . | [5 empty] | FALSE
G0580 | 2018-02-22 11:50 |  |  |  | Morrow Flats 115 kV station | WITHDRAWN | OR | Morrow | GI | 2020-12-31 | 2020-12-31 | 103 | 103 | NRIS & ERIS | Wind Turbine | Wind Turbine | 103 | [6 empty] | 103 |  |  | . | [5 empty] | FALSE
L0433 | 2018-02-12 17:00 | Network Load Expansion 4 Quenett Creek Substation | Northern Wasco County People's Utility District |  | Quenett Creek Substation | CONST AGRMT EXE | OR | Wasco | LL | 2021-02-12 | 2024-09-01 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0432 | 2018-02-05 16:00 | Junction City | Blachly-Lane Electric Cooperative | Withdrawn by Customer 3/27/2020 | Junction City Substation | WITHDRAWN | OR | Lane | LL | 2019-02-05 | 2021-01-25 |  |  |  | Other | Other | 90 | [6 empty] | 90 |  |  | . | [5 empty] | FALSE
L0431 | 2018-01-31 09:00 | Norway Substation | Coos-Curry Electric Cooperative, Inc. | Withdrawn by customer | Bandon to Fairview 115 kV line | WITHDRAWN | OR | Coos | LL | 2021-01-31 | 2021-01-25 | 19.2 | 19.2 |  | Other | Other | 19.2 | [6 empty] | 19.2 |  |  | . | [5 empty] | FALSE
L0430 | 2018-01-25 11:00 | Spearfish | Public Utility District No. 1 of Klickitat County |  | Spearfish Tap to Chenoweth-Goldendale #1 115kV | ENERGIZED | WA | Klickitat | LL | 2021-01-25 | 2019-10-17 | 10 | 10 |  | Other | Other | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0429 | 2017-12-20 15:02 | HiTest 2-Furnace Plant | Pend Oreille County PUD No. 1 |  | Pine Street Substation | WITHDRAWN | WA | Pend Oreille | LL | 2021-01-04 | 2021-12-31 | 210 | 210 |  | Other | Other | 210 | [6 empty] | 210 |  |  | . | [5 empty] | FALSE
L0428 | 2017-12-20 14:49 | HiTest 2-Furnace Plant | Pend Oreille County PUD No. 1 | This request has been withdrawn by the customer. | Pine Street Substation | WITHDRAWN | WA | Pend Oreille | LL | 2021-01-04 | 2021-01-04 | 105 | 105 |  | Other | Other | 105 | [6 empty] | 105 |  |  | . | [5 empty] | FALSE
L0427 | 2017-12-14 11:00 | Industrial Park | Kootenai Electric Cooperative, Inc. | Withdrawn by customer via email. | Bell-Taft 500kV #1, Mile 77 Tower 4 OR Lancaster 230kV Substation | WITHDRAWN | ID | Kootenai | LL | 2020-12-14 | 2019-12-16 | 120 | 120 |  | Other | Other | 120 | [6 empty] | 120 |  |  | . | [5 empty] | FALSE
G0579 | 2017-12-13 17:25 |  |  |  | Jones Canyon - Santiam line | WITHDRAWN | OR | Jefferson | GI | 2021-03-15 | 2021-03-15 | 250 | 250 | ERIS | Photovoltaic | Solar | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
L0426 | 2017-12-07 16:13 | Wallula 500kV | Columbia Rural Electric Association | Withdrawn by customer | Lower Monumental-McNary 500kV line | WITHDRAWN | WA | Walla Walla | LL | 2020-12-07 | 2020-12-07 |  |  |  | Other | Other | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
L0425 | 2017-11-28 13:00 | B Johnson Substation | Columbia River People's Utility District |  | St. Johns-St. Helens 115kV line | WITHDRAWN | OR | Multnomah | LL | 2020-11-30 | 2020-11-30 |  |  |  | Other | Other | 11 | [6 empty] | 11 |  |  | . | [5 empty] | FALSE
L0424 | 2017-11-27 07:06 | Grays Harbor Loads | Public Utility District No. 1 of Grays Harbor County Washington |  | Aberdeen or Satsop Substation | WITHDRAWN | WA | Walla Walla | LL | 2020-11-30 | 2024-09-30 | 40 | 40 |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
L0423 | 2017-11-17 16:00 | Gardiner Substation | Central Lincoln People's Utility District | Withdrawn by customer | Gardiner 115kV Substation | WITHDRAWN | OR | Douglas | LL | 2020-11-17 | 2020-11-17 |  |  |  | Other | Other | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
L0422 | 2017-11-09 17:00 | Project Vitesse 2 | PacifiCorp |  | Ponderosa 230kV Substataion | CONST AGRMT EXE | OR | Crook | LL | 2020-01-01 | 2024-11-15 | 220 | 220 |  | Other | Other | 220 | [6 empty] | 220 |  |  | . | [5 empty] | FALSE
L0421 | 2017-11-07 15:00 | Radar Hill Substation | Big Bend Electric Cooperative, Inc. |  | Scooteney Tap-Midway-Benton #1 115 kV | ENERGIZED | WA | Walla Walla | LL | 2020-11-07 | 2022-03-11 | 40 | 40 |  | Other | Other | 11.2 | [6 empty] | 11.2 |  |  | . | [5 empty] | FALSE
G0578 | 2017-11-02 14:36 |  |  | Solar / DC-coupled battery energy storage system (BESS). Maximum generating capacity for solar and battery system combined would never exceed 80 MW, alternating current at the POI | BPA's Midway - Moxee 115 kV transmission line. | STUDY COMPLETED | WA | Yakima | GI | 2022-11-01 | 2024-10-31 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | Energy Storage | Battery | 80 |  |  |  | 160 |  |  | . |  |  |  |  | Available | FALSE
L0420 | 2017-10-18 16:00 | Wallula Area Expansion | Columbia Rural Electric Association |  | Lower Monumental-McNary 500 kV line or Sacajawea Substation | STUDY COMPLETED | WA | Walla Walla | LL | 2019-10-18 | 2024-01-01 | 40 | 40 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0419 | 2017-10-13 14:00 | Grand Coulee #2 | Public Utility District No. 2 of Grant County, Washington | Withdrawn by customer via email. | Benton-451B #1 115kV Line | WITHDRAWN | WA | Grant | LL | 2018-03-01 | 2018-03-01 | 13.9 | 13.9 |  | Other | Other | 13.9 | [6 empty] | 13.9 |  |  | . | [5 empty] | FALSE
G0577 | 2017-10-05 15:14 |  |  |  | BPA's Ponderosa Substation | WITHDRAWN | OR | Crook | GI | 2020-10-30 | 2020-10-30 | 40 | 40 | Energy | Photovoltaic | Solar | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
G0576 | 2017-09-26 12:25 |  |  |  | McNary-Roundup No 1 230 kV transmission line. | WITHDRAWN | OR | Morrow | GI | 2020-12-31 | 2021-12-31 | 150 | 150 | NRIS | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G0575 | 2017-09-01 09:54 |  |  |  | Satsop 230 kV Substation | WITHDRAWN | WA | Grays Harbor | GI | 2018-05-01 |  | 51 | 51 | NRIS | Gas Turbine | Natural Gas | 51 | [6 empty] | 51 |  |  | . | [5 empty] | FALSE
L0418 | 2017-08-14 17:00 | Benton-CGS TRB 115 kV Line | Energy Northwest (CGS) |  | Benton-451B #1 115kV line | STUDY | WA | Benton | LL | 2023-05-01 | 2023-05-01 | 12.5 | 12.5 |  | Other | Other | 12.5 | [6 empty] | 12.5 |  |  | . | [5 empty] | FALSE
G0573 | 2017-08-07 15:58 |  |  |  | Big-Eddy - Redmond No 1 230 kV transmission line, near the city of Madras. | WITHDRAWN | OR | Jefferson | GI | 2020-06-01 | 2021-06-01 | 200 | 200 | NRIS & ERIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0574 | 2017-08-04 18:02 | McKenzie Reservoir Hydroelectric Facility | Three Sisters Irrigation District | 300 kW request | Holmes Road GPS 44 18'45.45"N, 121 25'25.38"W | ENERGIZED | OR | Deschutes | GI | 2018-09-01 | 2018-06-14 | 1 | 1 | ERIS | Hydro | Water | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0572 | 2017-07-31 12:05 |  |  |  | Midstate Electric's Fort Rock 115 kV Substation. | STUDY | OR | Lake | GI | 2019-06-01 | 2027-01-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0571 | 2017-07-31 12:04 |  |  |  | Tap off BPA's 115 kV line within 10 miles of Midstate Electric's Fort Rock 115 kV Substation. | STUDY | OR | Lake | GI | 2019-06-01 | 2027-01-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0570 | 2017-07-31 12:03 |  |  |  | Tap off BPA's 115 kV line within 10 miles of Midstate Electric's Fort Rock 115 kV Substation. | STUDY | OR | Lake | GI | 2019-06-01 | 2025-01-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . |  |  |  |  | Available | FALSE
L0417 | 2017-07-26 15:00 | Boundary Substation | Teck Metals, Ltd. |  | Boundary Substation | STUDY | WA | Pend Oreille | LL | 2020-07-26 | 2021-07-26 | 370 | 370 |  | Other | Other | 370 | [6 empty] | 370 |  |  | . | [5 empty] | FALSE
G0569 | 2017-07-19 10:29 | Ross MHQ Solar Project | BPA Corporate | Requestor is BPA Corporate, 300 kW |  | ENERGIZED | WA | Clark | GI | 2017-09-01 | 2017-10-27 | 1 | 1 |  | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0568 | 2017-06-21 12:47 |  |  | Customer reduced request from 300 to 294 before execution of the system impact study agreement. | Slatt Substation; Tap onto Slatt - Buckley 500 kV line; Tap onto McNary - Santiam 230 kV line. | WITHDRAWN | OR | Gilliam | GI | 2019-09-01 | 2021-09-01 | 294 | 294 | NRIS & ERIS | Wind Turbine | Wind Turbine | 294 | [6 empty] | 294 |  |  | . | [5 empty] | FALSE
G0567 | 2017-06-19 11:41 |  |  |  | Nilles Corner Substation | WITHDRAWN | WA | Douglas | GI | 2019-06-30 | 2019-06-30 | 5 | 5 | ERIS | Energy Storage | Battery | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
L0416 | 2017-06-08 16:00 | Baker Creek Substation | The City of McMinnville, a municipal corporation of the State of Oregon, acting by and through its Water and Light Commission | Withdrawn by customer. This project will be handled as non-tariff. | BPA's Walnut City Tap | WITHDRAWN | OR | Yamhill | LL | 2020-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0566 | 2017-06-05 10:05 |  |  |  |  | STUDY COMPLETED | MT | Lincoln | GI | 2022-09-30 | 2026-05-01 | 646 | 646 | NRIS | Hydro | Water | 646 | [6 empty] | 646 |  |  | . | [5 empty] | FALSE
L0415 | 2017-05-30 16:00 | Project Vitesse | PacifiCorp |  | BPA's Ponderosa Substation | ENERGIZED | OR | Crook | LL | 2019-12-01 | 2020-01-16 | 60 | 60 |  | Other | Other | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
L0414 | 2017-05-24 13:04 | Ruppert Road Substation | Benton Rural Electric Association |  | BPA's White Bluffs to Red Mountain 115kV Line | CONST AGRMT EXE | WA | Benton | LL | 2020-10-01 | 2023-10-31 | 13 | 13 |  | Other | Other | 13 | [6 empty] | 13 |  |  | . | [5 empty] | FALSE
G0564 | 2017-05-23 18:39 |  |  |  | A line tap on BPA's Hatton Tap - Hatton 115 kV transmission line. | WITHDRAWN | WA | Franklin | GI | 2019-06-30 | 2020-06-30 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0565 | 2017-05-23 18:39 |  |  |  | BPA's White Bluffs-Horn Rapids 115 kV transmission line. | WITHDRAWN | WA | Benton | GI | 2019-06-30 |  | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0562 | 2017-05-23 18:38 |  |  |  | BPA's Midway-Moxee 115 kV transmission line. | WITHDRAWN | WA | Yakima | GI | 2019-06-30 | 2020-06-30 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0563 | 2017-05-23 18:38 |  |  |  | BPA's Midway-Grandview 115 kV transmission line. | WITHDRAWN | WA | Yakima | GI | 2019-06-30 | 2020-06-30 | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0561 | 2017-05-03 15:50 |  |  |  | Badger Canyon Substation 115/230 kV. Alternates: Red Mountain Substation 115 kV; A tap on the Franklin-McNary 230 kV transmission line. | WITHDRAWN | WA | Benton | GI | 2020-10-06 | 2021-10-06 | 250 | 250 | NRIS & ERIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . |  |  |  |  | Available | FALSE
L0413 | 2017-05-01 17:00 | Lebanon Substation | PacifiCorp |  | BPA Lebanon Substation 115 kV | STUDY | OR | Linn | LL | 2020-09-15 | 2026-03-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0412 | 2017-03-23 13:00 | Saginaw Area | Emerald People's Utility District |  | Alvey-Fairview No. 1 230kV Line | STUDY | OR | Lane | LL | 2020-10-01 | 2020-10-01 | 12.1 | 12.1 |  | Other | Other | 12.1 | [6 empty] | 12.1 |  |  | . | [5 empty] | FALSE
L0411 | 2017-03-21 16:00 | Project Quantum | Clark Public Utilities | Customer's load opted for a different location. | BPA's Sifton Substation | WITHDRAWN | WA | Clark | LL | 2018-10-01 |  |  |  |  | Other | Other | 160 | [6 empty] | 160 |  |  | . | [5 empty] | FALSE
L0410 | 2017-03-20 08:00 | Airport Substation | Columbia Rural Electric Association |  | Walla Walla-Tucannon 115kV Line | STUDY | WA | Walla Walla | LL | 2020-10-01 | 2023-04-01 | 25 | 25 |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G0560 | 2017-03-06 09:20 |  |  |  | Grand Coulee 230 kV | WITHDRAWN | WA | Grant | GI | 2025-10-01 | 2025-10-01 | 500 | 500 | NRIS | Energy Storage | Pumped-Storage Hydro | 500 | [6 empty] | 500 |  |  | . |  |  |  |  | Available | FALSE
G0559 | 2017-03-01 10:04 |  |  |  | BPA's McNary-Franklin 230 kV | STUDY COMPLETED | WA | Benton | GI | 2019-12-01 | 2026-03-31 | 250 | 250 | NRIS & ERIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . |  |  |  |  | Available | FALSE
G0558 | 2017-02-21 16:50 |  |  |  | BPA's Ashe - Marion 500 kV, Mile 26, Tower 4; BPA's McNary - John Day 500 kV, Mile 4, Tower 1 | STUDY COMPLETED | WA | Benton | GI | 2019-12-01 | 2027-12-31 | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . |  |  |  |  | Available | FALSE
L0409 | 2017-01-25 09:00 | Sunset Rd to Dallas Rd | Public Utility District No. 1 of Benton County |  | Red Mountain Substation | CONST AGRMT EXE | WA | Benton | LL | 2017-12-31 | 2024-01-01 | 31 | 31 |  | Other | Other | 8 | [6 empty] | 8 |  |  | . | [5 empty] | FALSE
L0408 | 2017-01-20 16:00 | Badger Canyon-Reata | City of Richland, Washington |  | Benton PUD's Reata Substation | CONST AGRMT EXE | WA | Benton | LL | 2017-12-31 | 2024-12-30 | 31 | 31 |  | Other | Other | 8 | [6 empty] | 8 |  |  | . | [5 empty] | FALSE
L0407 | 2016-12-20 15:00 | Taylor Substation | Public Utility District No. 3 of Mason County |  | Existing BPA tap at Kamilche/Skookum on the Olympia-Shelton #2 115kV line | CONST AGRMT EXE | WA | Thurston | LL | 2020-01-01 | 2020-03-30 | 25 | 25 |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G0557 | 2016-12-20 10:55 |  |  |  | TBD | WITHDRAWN | OR | Lake | GI | 2019-12-01 |  | 80 | 80 | NRIS & ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0556 | 2016-12-16 14:34 |  |  |  | BPA's 230 KV Harvalum Substation | WITHDRAWN | WA | Klickitat | GI | 2026-12-31 |  | 1200 | 1200 | NRIS & ERIS | Energy Storage | Battery | 1200 | [6 empty] | 1200 |  |  | . | [5 empty] | FALSE
L0406 | 2016-12-09 10:25 | CTUC Interconnection | Colville Tribes | Withdrawn by the customer 9/26/19 | East Omak-Grand Coulee or Grand Coulee-Okanogan #2 | WITHDRAWN | WA | Grant | LL | 2019-10-01 | 2020-04-30 |  |  |  | Other | Other | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
L0405 | 2016-12-01 10:00 | McNary-Badger Canyon | Public Utility District No. 1 of Benton County |  | BPA's McNary Substation 115kV | CONST AGRMT EXE | OR | Umatilla | LL | 2020-10-01 | 2024-12-30 | 100 | 100 |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0404 | 2016-10-28 10:00 | Arc Furnace Load | Pend Oreille County PUD No. 1 | Withdrawn by customer | Usk Substation | WITHDRAWN | WA | Pend Oreille | LL | 2019-10-01 |  |  |  |  | Other | Other | 90 | [6 empty] | 90 |  |  | . | [5 empty] | FALSE
L0403 | 2016-10-25 12:00 | New Load | Central Electric Cooperative, Inc. | Withdrawn by Customer | Ponderosa or Redmond Substation | WITHDRAWN | OR | Crook | LL | 2018-11-01 |  |  |  |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
G0555 | 2016-10-07 13:42 |  |  |  | BPA's Raymond 115 kV bus | WITHDRAWN | WA | Pacific | GI | 2019-12-31 | 2021-12-31 | 107 | 107 | NRIS | Wind Turbine | Wind Turbine | 107 | [6 empty] | 107 |  |  | . | [5 empty] | FALSE
G0554 | 2016-10-07 13:39 |  |  |  | 1) BPA's Big Eddy-Troutdale 230 kV line, or 2) BPA's Big Eddy-McLoughlin 230 kV line | WITHDRAWN | OR | Hood River | GI | 2019-12-31 |  | 148 | 148 | NRIS | Wind Turbine | Wind Turbine | 148 | [6 empty] | 148 |  |  | . | [5 empty] | FALSE
L0402 | 2016-09-14 14:32 | Hood River Loads | Hood River Electric Cooperative |  | BPA Hood River Substation | STUDY | OR | Hood River | LL | 2019-10-01 | 2024-10-31 | 5 | 5 |  | Other | Other | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
G0552 | 2016-08-30 10:01 |  |  |  | Raymond 115 kV Substation | WITHDRAWN | WA | Pacific | GI | 2019-12-31 |  | 80 | 80 | NRIS & ERIS | Wind Turbine | Wind Turbine | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0553 | 2016-08-30 10:01 |  |  |  | Tap into Big Eddy-Troutdale 230 kV line. | WITHDRAWN | OR | Hood River | GI | 2019-12-31 |  | 70 | 70 | NRIS | Wind Turbine | Wind Turbine | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G0551 | 2016-08-04 10:58 |  |  | 100.5 MW Request | BPA's Ponderosa Substation. | WITHDRAWN | OR | Crook | GI | 2020-12-31 |  | 101 | 101 | NRIS & ERIS | Photovoltaic | Solar | 101 | [6 empty] | 101 |  |  | . | [5 empty] | FALSE
G0550 | 2016-07-08 15:27 |  |  |  | Morrow Flat 230 kV Substation. | WITHDRAWN | OR | Umatilla | GI | 2020-12-01 |  | 120 | 120 | ERIS | Photovoltaic | Solar | 120 | [6 empty] | 120 |  |  | . | [5 empty] | FALSE
G0549 | 2016-07-08 14:44 |  |  |  | TBD | WITHDRAWN | OR | Lake | GI | 2022-12-01 | 2022-12-01 | 400 | 400 | NRIS & ERIS | Photovoltaic | Solar | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
L0401 | 2016-07-07 12:00 | Rock Creek | Public Utility District No. 1 of Klickitat County | Withdrawn by customer. | Harvalum-Rock Creek 230 kV line. | WITHDRAWN | WA | Benton | LL | 2017-09-11 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0548 | 2016-06-20 12:29 |  |  |  | Boardman-Ione No. 1 69 kV line via a new tap or at substation | WITHDRAWN | OR | Morrow | GI | 2019-04-01 |  | 80 | 80 | NRIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0547 | 2016-06-20 12:25 |  |  |  | BPA Canby-Surprise Valley Electric Substation (SVE) 69 kV bus, via a tie line, or the SVE Co-op system. | WITHDRAWN | CA | Modoc | GI | 2019-04-01 | 2018-10-01 | 80 | 80 | NRIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0546 | 2016-06-20 12:20 |  |  |  | Walla Walla/Pendleton/Milton Freewater 69 kV system via line tap or at substation | WITHDRAWN | OR | Umatilla | GI | 2019-04-01 |  | 80 | 80 | NRIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0545 | 2016-06-20 12:16 |  |  |  | Malin-Hilltop No. 1 230 kV transmission line, at Malin Substation 230 kV bus. | WITHDRAWN | OR | Klamath | GI | 2019-10-01 | 2019-11-07 | 200 | 200 | NRIS | Photovoltaic | Solar | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0400 | 2016-06-13 07:01 | Detroit Substation | USACE Portland |  | Detroit Substation | WITHDRAWN | OR | Wheeler | LL | 2019-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0544 | 2016-06-09 12:08 |  |  |  | Tap the existing McNary to Morrow Flat 230 kV line | WITHDRAWN | OR | Umatilla | GI | 2018-12-31 |  | 80 | 80 | ERIS | Photovoltaic | Solar | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G0543 | 2016-06-06 08:40 |  |  |  | BPA's McNary 230 kV or the proposed Stanfield Substation at 230 kV | STUDY COMPLETED | OR | Umatilla | GI | 2019-12-31 | 2028-12-31 | 350 | 350 | NRIS | Wind Turbine | Wind Turbine | 350 | [6 empty] | 350 |  |  | . | [5 empty] | FALSE
G0540 | 2016-05-24 16:20 |  |  | Reduction in MW posted 8/23/2016. Reduction in MW posted 3/20/2017, per developer request. | BPA's Boardman - Ione 69 kV Transmission Line. | WITHDRAWN | OR | Morrow | GI | 2018-12-31 | 2020-08-31 | 10 | 10 | NRIS | Photovoltaic | Solar | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0541 | 2016-05-24 16:20 |  |  |  | BPA's Brasada - Harney 115 kV Transmission Line. | WITHDRAWN | OR | Deschutes | GI | 2018-12-31 |  | 64 | 64 | NRIS | Photovoltaic | Solar | 64 | [6 empty] | 64 |  |  | . | [5 empty] | FALSE
G0542 | 2016-05-24 16:20 |  |  |  | BPA's La Pine - Fort Rock 115 kV Transmission Line through an interconnection on MEC's Fort Rock 115 kV Substation. | WITHDRAWN | OR | Lake | GI | 2018-12-31 |  | 106 | 106 | NRIS | Photovoltaic | Solar | 106 | [6 empty] | 106 |  |  | . | [5 empty] | FALSE
G0539 | 2016-05-16 08:16 |  |  |  | BPA Ponderosa Substation or on the interconnecting systems tying into the Ponderosa Substation | E&P EXECUTED | OR | Crook | GI | 2022-03-31 | 2025-11-15 | 600 | 600 | NRIS | Photovoltaic | Solar | 600 | [6 empty] | 600 |  |  | . |  |  |  |  | Available | FALSE
G0538 | 2016-05-12 10:30 |  |  |  | BPA's Harney 115 kV Substation | WITHDRAWN | OR | Harney | GI | 2019-04-01 | 2022-12-31 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0537 | 2016-05-12 10:20 |  |  |  | Line tap into BPA Harney-Brasada 115 kV line | STUDY | OR | Harney | GI | 2019-04-01 | 2027-01-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0536 | 2016-05-12 10:10 |  |  |  | Line tap into BPA Harney-Brasada 115 kV line | WITHDRAWN | OR | Harney | GI | 2019-04-01 | 2027-01-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0535 | 2016-05-05 14:35 |  |  | Requestor is USACE |  | STUDY COMPLETED | WA | Walla Walla | GI | 2031-07-25 | 2033-01-31 | 210 | 210 | ERIS | Hydro | Water | 210 | [6 empty] | 210 |  |  | . | [5 empty] | FALSE
L0399 | 2016-04-16 05:00 | Snohomish North Snohomish County | Public Utility District No. 1 of Snohomish County |  | Snohomish-Murry #1 line | WITHDRAWN | WA | Snohomish | LL | 2019-10-01 | 2032-01-01 | 1.7 | 1.7 |  | Other | Other | 1.7 | [6 empty] | 1.7 |  |  | . | [5 empty] | FALSE
G0534 | 2016-04-13 12:38 |  |  |  | Wasco Tygh Valley Substation 69 kV bus | WITHDRAWN | OR | Wasco | GI | 2019-04-01 | 2023-01-01 | 120 | 120 | NRIS | Photovoltaic | Solar | 120 | [6 empty] | 120 |  |  | . | [5 empty] | FALSE
G0533 | 2016-04-13 12:34 |  |  |  | Tap or new substation within 2 miles of Wasco Electric's 69 KV Tygh Valley Substation. | WITHDRAWN | OR | Wasco | GI | 2019-06-01 |  | 20 | 20 | Energy | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0398 | 2016-03-21 16:02 | Bettas Road | Public Utility District No. 1 of Kittitas County |  |  | STUDY | WA | Kittitas | LL | 2019-10-01 | 2023-07-10 | 3.8 | 3.8 |  | Other | Other | 3.8 | [6 empty] | 3.8 |  |  | . | [5 empty] | FALSE
G0532 | 2016-03-18 18:14 |  |  | 99.52 MW Request | A 115 kV line tap proximate to Tower Road Switch Station. | STUDY COMPLETED | OR | Morrow | GI | 2017-06-30 | 2026-01-01 | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0397 | 2016-03-04 09:00 | L0397 Clatskanie PUD Allston | Clatskanie People's Utility District | Withdrawn by customer | BPA's Allston Substation | WITHDRAWN | OR | Columbia | LL | 2020-01-01 |  |  |  |  | Other | Other | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0530 | 2016-02-29 16:07 |  |  |  | BPA's Slatt Substation | WITHDRAWN | OR | Morrow | GI | 2021-01-01 | 2025-10-01 | 600 | 600 | NRIS & ERIS | Combined Cycle | Natural Gas | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0531 | 2016-02-29 16:07 |  |  |  | BPA's Slatt Substation | WITHDRAWN | OR | Morrow | GI | 2021-07-01 | 2020-10-01 | 400 | 400 | NRIS & ERIS | Gas Turbine | Natural Gas | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0529 | 2016-02-24 08:10 |  |  |  | BPA's Slatt Substation or PPW Dalreed Substation | WITHDRAWN | OR | Morrow | GI | 2017-12-31 | 2021-06-01 | 50 | 50 | NRIS & ERIS | Photovoltaic | Solar | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0528 | 2016-02-17 09:07 |  |  |  | Pearl 230 kV substation | WITHDRAWN | OR | Clackamas | GI | 2017-06-30 | 2020-10-01 | 150 | 150 | ERIS | Energy Storage | Battery | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G0527 | 2016-02-04 10:55 |  |  | Reduction request from 200 MW to 105 MW on 3/20/2017. | Fort Rock Substation | STUDY COMPLETED | OR | Lake | GI | 2019-04-01 | 2026-03-01 | 105 | 105 | NRIS & ERIS | Photovoltaic | Solar | 105 | [6 empty] | 105 |  |  | . |  |  |  |  | Available | FALSE
L0396 | 2016-02-03 09:00 | Industrial Load Phase 2 | Umatilla Electric Cooperative | Withdrawn by UEC on June 30, 2016. | BPA McNary and/or BPA Morrow Flat | WITHDRAWN | OR | Morrow | LL | 2018-01-01 |  |  |  |  | Other | Other | 1152 | [6 empty] | 1152 |  |  | . | [5 empty] | FALSE
G0526 | 2016-01-28 14:27 | Fort Rock II | Fort Rock Interconnection II LLC |  | Within 10 miles of Midstate Electric's Fort Rock 115 kV Substation | ENERGIZED | OR | Lake | GI | 2019-04-01 | 2020-06-18 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0525 | 2016-01-28 13:07 |  |  |  | BPA's Harney 115 kV Substation | WITHDRAWN | OR | Harney | GI | 2019-04-30 | 2022-11-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0395 | 2016-01-25 07:34 | Mabton Substation | Benton Rural Electric Association | Withdrawn by customer | Big Eddy-Midway #1 230kV transmission line | WITHDRAWN | OR | Wasco | LL | 2019-10-01 |  | 50.3 | 50.3 |  | Other | Other | 50.3 | [6 empty] | 50.3 |  |  | . | [5 empty] | FALSE
L0394 | 2016-01-22 07:07 | Salzer Valley Substation | City of Centralia |  | Chehalis-Centralia transmission line | STUDY | WA | Lewis | LL | 2018-10-01 | 2021-03-30 | 50 | 50 |  | Other | Other | 14 | [6 empty] | 14 |  |  | . | [5 empty] | FALSE
G0524 | 2016-01-07 10:35 |  |  |  | Within 2 miles of Wasco Electric Coop's 69 kV Tygh Valley Substation (Tap or new substation) | STUDY | OR | Wasco | GI | 2018-12-31 | 2022-11-08 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0523 | 2016-01-07 10:28 |  |  |  | BPA Maupin 69 kV Substation | STUDY | OR | Wasco | GI | 2018-12-31 | 2027-11-01 | 13 | 13 | ERIS | Photovoltaic | Solar | 13 | [6 empty] | 13 |  |  | . | [5 empty] | FALSE
G0522 | 2016-01-07 10:23 | NewSun Riley Project | Riley Interconnection LLC |  | BPA's Harney - Brasada line, 115 kV tap. 10 - 20 miles west of Harney Substation. | ENERGIZED | OR | Harney | GI | 2018-12-31 | 2020-07-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0521 | 2016-01-07 10:19 | NewSun Fort Rock Project | NewSun Energy Transmission Company LLC |  | Within 10 miles of Midstate Electric's Fort Rock 115 kV Substation. | ENERGIZED | OR | Lake | GI | 2019-01-31 | 2020-06-09 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0520 | 2016-01-06 17:02 | NewSun Starvation Solar Project | NewSun Energy Transmission Company LLC |  | BPA Harney 115 kV Substation or nearby 115 kV tap | ENERGIZED | OR | Harney | GI | 2018-06-01 | 2020-06-18 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0519 | 2015-12-17 10:00 |  |  |  | UEC 12.47 KV line adjacent to property | WITHDRAWN | OR | Umatilla | GI | 2016-09-01 | 2017-03-01 | 3 | 3 | ERIS | Photovoltaic | Solar | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
L0393 | 2015-12-17 10:00 | Finley Butte Substation | Midstate Electric Cooperative, Inc. |  | LaPine 115kV Bus | STUDY | OR | Deschutes | LL | 2018-10-01 | 2025-08-01 | 100 | 100 |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0392 | 2015-12-07 10:00 | Ponderosa Substation | PacifiCorp | Withdrawn by PacifiCorp | BPA's Ponderosa Substation | WITHDRAWN | OR | Crook | LL | 2018-12-01 | 2018-12-01 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0518 | 2015-11-13 12:38 | Horn Rapids Solar Project | Energy Northwest (CGS) | 3.2 MW solar, 1 MW Battery | Pole 3401, City of Richland | ENERGIZED | WA | Benton | GI | 2017-11-13 | 2021-11-20 | 5 | 5 | ERIS | Photovoltaic | Solar | 3 | Energy Storage | Battery | 1 |  |  |  | 4 |  |  | . | [5 empty] | FALSE
G0517 | 2015-11-13 06:36 |  |  |  | Alkali-Tower Road 115 kV Tap point or Willow Creek Energy Center 115 kV line tap. | STUDY COMPLETED | OR | Morrow | GI | 2018-07-01 | 2027-12-31 | 76 | 76 | NRIS & ERIS | Photovoltaic | Solar | 76 | [6 empty] | 76 |  |  | . | [5 empty] | FALSE
G0516 | 2015-10-20 14:59 |  |  |  | Iberdrola's Schoolhouse Substation at 230 kV | STUDY | OR | Sherman | GI | 2016-10-01 | 2024-06-30 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0391 | 2015-10-08 10:00 | Grandhaven Substation | The City of McMinnville, a municipal corporation of the State of Oregon, acting by and through its Water and Light Commission | Withdrawn by customer 10/23/19 | Walnut City 115kV Tap between structures 2/3 & 2/4 | WITHDRAWN | OR | Yamhill | LL | 2019-10-01 | 2020-10-01 | 10.2 | 10.2 |  | Other | Other | 10.2 | [6 empty] | 10.2 |  |  | . | [5 empty] | FALSE
G0515 | 2015-10-06 10:32 |  |  |  | Tapping into the Covington to Chehalis 230 kV line. | WITHDRAWN | WA | Lewis | GI | 2017-12-31 | 2020-01-01 | 150 | 150 | NRIS & ERIS | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G0514 | 2015-09-29 17:39 |  |  |  | 69 kV line tap proximate to Ione Substation. | WITHDRAWN | OR | Morrow | GI | 2016-12-31 | 2025-09-30 | 10 | 10 | ERIS | Photovoltaic | Solar | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0390 | 2015-09-28 10:00 | Chicken Creek Substation | Nespelem Valley Electric Cooperative, Inc. |  | East Omak Tap of the Grand Coulee Foster Creek #1 115kV Line | ENERGIZED | WA | Okanogan | LL | 2018-10-01 | 2020-09-01 |  |  |  | Other | Other | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0389 | 2015-09-21 10:00 | Industrial Load | Umatilla Electric Cooperative |  | Mcnary Substation or Morrow Flat Substation | ENERGIZED | OR | Morrow | LL | 2019-01-01 | 2019-10-01 | 1021.5 | 1021.5 |  | Other | Other | 1021.5 | [6 empty] | 1021.5 |  |  | . | [5 empty] | FALSE
G0513 | 2015-09-18 17:32 |  |  |  | 115 kV line tap proximate to Tower Road Switch Station | STUDY | OR | Morrow | GI | 2016-12-31 | 2026-05-01 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0388 | 2015-09-08 10:00 | Chenoweth Substation | Northern Wasco County People's Utility District |  | BPA's Chenoweth Substation | ENERGIZED | OR | Wasco | LL | 2017-10-01 | 2017-08-31 |  |  |  | Other | Other | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
G0512 | 2015-08-31 07:52 |  |  |  | Beach Access Station - McNary 115 kV. | WITHDRAWN | OR | Umatilla | GI | 2016-12-01 | 2021-12-31 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0387 | 2015-08-07 12:00 | SE Richland | City of Richland, Washington |  | Badger Canyon Substation | ENERGIZED | WA | Benton | LL | 2018-10-01 | 2018-11-28 | 35.5 | 35.5 |  | Other | Other | 35.5 | [6 empty] | 35.5 |  |  | . | [5 empty] | FALSE
G0511 | 2015-07-30 09:36 | Smith Creek | Eugene Water & Electric Board | Existing hydro generation currently in full operation. | BPA's Bonners Ferry Substation | ENERGIZED | ID | Boundary | GI | 1987-04-10 | 2019-03-04 | 39 | 39 | NRIS | Hydro | Water | 39 | [6 empty] | 39 |  |  | . | [5 empty] | FALSE
G0510 | 2015-06-30 17:34 |  |  |  | Redmond-Harney 115 kV transmission line. | WITHDRAWN | OR | Deschutes | GI | 2016-10-31 |  | 40 | 40 | ERIS | Photovoltaic | Solar | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
L0386 | 2015-06-29 14:00 | Clallam Port Angeles Interconnection | Public Utility District No. 1 of Clallam County |  | BPA Port Angeles Substation | STUDY | WA | Clallam | LL | 2019-10-01 | 2024-10-01 | 21.4 | 21.4 |  | Other | Other | 21.4 | [6 empty] | 21.4 |  |  | . | [5 empty] | FALSE
L0385 | 2015-06-05 16:00 | Southend Load | Public Utility District No. 1 of Cowlitz County |  | Kalama 115kV Sub Phase 1, then Longview 230kV Sub in next phase | WITHDRAWN | WA | Cowlitz | LL | 2018-10-01 | 2023-10-30 | 250 | 250 |  | Other | Other | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0509 | 2015-04-28 13:47 | UEC Solar PV Array | Umatilla Electric Cooperative | Generator Nameplate Rating: 999 kW | An existing UEC-owned 12.47 kV distribution line. | ENERGIZED | OR | Umatilla | GI | 2015-10-01 | 2018-02-23 | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0384 | 2015-04-20 11:00 | Industrial Load | Surprise Valley Electrification Corporation | Request withdrawn by customer. | Cedarville Jct. 69kV Substation | WITHDRAWN | CA | Modoc | LL | 2018-10-01 | 2019-10-31 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0383 | 2015-03-26 11:00 | Shelton Hills | Public Utility District No. 3 of Mason County | Withdrawn by customer. | Shelton 115kV Substation | WITHDRAWN | WA | Mason | LL | 2019-10-01 | 2020-09-30 |  |  |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G0508 | 2015-03-16 08:12 |  |  |  | 115 kV line between White Bluffs and DOE B3S4, Richland, WA. | WITHDRAWN | WA | Benton | GI | 2016-10-01 | 2019-12-31 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0382 | 2015-03-05 11:00 | Pyramid Substation | City of Cascade Locks | Withdrawn by customer | BPA Cascade Locks Substation | WITHDRAWN | OR | Hood River | LL | 2015-08-31 |  |  |  |  | Other | Other | 14 | [6 empty] | 14 |  |  | . | [5 empty] | FALSE
G0507 | 2015-02-03 08:52 | Boundary Powerhouse | The City of Seattle, City Light Department |  | Boundary 230 kV Switchyard | ENERGIZED | WA | Pend Oreille | GI | 2016-02-05 | 2016-08-01 | 70 | 70 | ERIS | Hydro | Water | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G0506 | 2015-01-22 10:30 | MESA 2 Energy Storage Project | Public Utility District No. 1 of Snohomish County | 2.2 MW capacity | Everett Substation (Snohomish County PUD) | ENERGIZED | WA | Snohomish | GI | 2015-11-01 | 2017-03-23 | 3 | 3 | ERIS | Energy Storage | Battery | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
G0505 | 2015-01-12 07:48 |  |  |  | Located on the 12.47 kV distribution line between SS162 Seal Rock and SS163 Lundy, approximately 2.5 miles south of Seal Rock. | STUDY COMPLETED | OR | Lincoln | GI | 2017-01-01 | 2025-06-15 | 20 | 20 | ERIS | Wave | Water | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0504 | 2014-12-15 11:34 | Nippon Biomass | Nippon Paper Industries USA Co., Ltd. | An increase in generating capacity of an existing facility from 20 MW to 25 MW total. Requesting 4.6 MW | BPA Port Angeles 230kV/69kV Substation | ENERGIZED | WA | Clallam | GI | 2013-12-20 | 2017-01-06 | 5 | 5 | NRIS | Reciprocating Engine | Biofuel | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
L0381 | 2014-12-02 11:00 | Sand Creek Substation | Northern Lights, Inc. |  | Sand Creek 115kV Substation | ENERGIZED | ID | Bonner | LL | 2018-10-01 | 2019-10-31 |  |  |  | Other | Other | 9 | [6 empty] | 9 |  |  | . | [5 empty] | FALSE
G0503 | 2014-11-24 12:52 |  |  | 9.5 MW Request | Samuels, ID Substation | WITHDRAWN | ID | Bonner | GI | 2016-10-01 | 2019-06-01 | 10 | 10 | ERIS | Gas Turbine | Natural Gas | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0502 | 2014-11-22 06:29 |  |  | Withdrawn per LGIP section 3.6 pending outcome of Dispute Resolution per LGIP section 13.5 | New substation and new transmission line to be built and located on the current Anderson Ranch Dam to Mountain Home, Idaho 115kV BPA line right of way. | WITHDRAWN | ID | Elmore | GI | 2017-01-01 | 2017-02-14 | 600 | 600 | NRIS & ERIS | Hydro | Water | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
L0380 | 2014-11-20 09:00 | Network Load Expansion 3 | Northern Wasco County People's Utility District |  | Chenoweth Substation | ENERGIZED | OR | Wasco | LL | 2018-10-01 | 2019-06-30 | 300 | 300 |  | Other | Other | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0379 | 2014-10-16 16:00 | The Lakes Substation | Benton Rural Electric Association | LLIR Withdrawn by customer via email. | Red Mountain-Richland #1 115kV line | WITHDRAWN | WA | Benton | LL | 2018-10-01 | 2018-10-31 | 11.1 | 11.1 |  | Other | Other | 11.1 | [6 empty] | 11.1 |  |  | . | [5 empty] | FALSE
G0501 | 2014-10-13 08:55 |  |  |  | Captain Jack 500 kV Substation | STUDY COMPLETED | OR | Klamath | GI | 2018-07-01 | 2024-10-31 | 1100 | 1100 | NRIS & ERIS | Combined Cycle | Natural Gas | 1100 | [6 empty] | 1100 |  |  | . |  |  |  |  | Available | FALSE
L0377 | 2014-10-10 10:00 | 16th Avenue | Vera Water & Power |  | Sullivan 115kV Substation | ENERGIZED | WA | Spokane | LL | 2016-07-01 | 2016-10-01 | 8.7 | 8.7 |  | Other | Other | 8.7 | [6 empty] | 8.7 |  |  | . | [5 empty] | FALSE
L0378 | 2014-10-10 10:00 | Transalta Industrial Park Tap | Public Utility District No. 1 of Lewis County | Withdrawn by customer | Chehalis-Covington 230kV line | WITHDRAWN | WA | Lewis | LL | 2017-10-01 | 2020-10-31 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0500 | 2014-10-02 07:03 | Hardeson Battery Storage Expansion | Public Utility District No. 1 of Snohomish County |  | Hardeson Substation | ENERGIZED | WA | Snohomish | GI | 2015-07-01 | 2015-11-30 | 1 | 1 | ERIS | Energy Storage | Battery | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0499 | 2014-09-26 11:00 |  |  | Withdrawn per LGIP section 3.6 pending outcome of Dispute Resolution per LGIP section 13.5 | Dixie Substation adjacent to Anderson Ranch Dam, Idaho. | WITHDRAWN | ID | Elmore | GI | 2017-01-01 |  | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
L0376 | 2014-08-14 07:00 | Grandview Substation | US DOI Bureau of Reclamation |  | BPA's Grandview Substation | STUDY COMPLETED | WA | Yakima | LL | 2016-05-02 | 2016-05-02 07:00 | 6.3 | 6.3 |  | Other | Other | 6.3 | [6 empty] | 6.3 |  |  | . | [5 empty] | FALSE
G0498 | 2014-08-12 18:45 | Lilliwaup Falls Hydro Project | Lilliwaup Falls Generating Company | 1.75 MW Request | BPA Potlatch Substation | ENERGIZED | WA | Mason | GI | 2014-10-20 | 2017-08-31 | 2 | 2 | ERIS | Hydro | Water | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
L0374 | 2014-07-07 19:00 | Phillips Substation | Public Utility District No. 1 of Benton County | Withdrawn by customer. | Franklin-Hedges 115kV | WITHDRAWN | WA | Benton | LL | 2017-10-01 | 2017-10-01 |  |  |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
L0375 | 2014-07-07 19:00 | Beck Road Switching Station | Public Utility District No. 1 of Benton County | This LLIR has been withdrawn by the customer effective 12/7/16. | Hedges Tap to Franklin-Badger Canyon #2 115kV line | WITHDRAWN | OR | Umatilla | LL | 2017-10-01 | 2019-10-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0373 | 2014-06-26 | Grand Ridge Substation | Puget Sound Energy, Inc. |  | Grand Ridge Substation | E&P EXECUTED | WA | King | LL | 2016-10-01 | 2027-01-01 | 24.8 | 24.8 |  | Other | Other | 24.8 | [6 empty] | 24.8 |  |  | . | [5 empty] | FALSE
L0371 | 2014-06-03 16:00 | Clodfelter Substation | Public Utility District No. 1 of Benton County |  | BPA's Franklin-Badger Canyon #1 115kV line | WITHDRAWN | WA | Franklin | LL | 2017-10-01 |  |  |  |  | Other | Other | 11 | [6 empty] | 11 |  |  | . | [5 empty] | FALSE
L0372 | 2014-06-03 16:00 | Southridge Substation | Public Utility District No. 1 of Benton County |  | BPA's Franklin-Badger Canyon #1 115kV line | ENERGIZED | WA | Franklin | LL | 2017-10-01 | 2021-07-01 | 9 | 9 |  | Other | Other | 9 | [6 empty] | 9 |  |  | . | [5 empty] | FALSE
L0370 | 2014-05-23 16:00 | Lyons Ferry Substation | Columbia Rural Electric Association | Withdrawn by customer 3/23/15 via email. | BPA's Central Ferry Substation | WITHDRAWN | WA | Garfield | LL | 2015-12-31 |  | 18.4 | 18.4 |  | Other | Other | 18.4 | [6 empty] | 18.4 |  |  | . | [5 empty] | FALSE
L0369 | 2014-03-21 09:00 | South Fork Substation | Public Utility District No. 2 of Pacific County | Withdrawn by customer email | Raymond 115kV Substation | WITHDRAWN | WA | Pacific | LL | 2017-10-01 | 2025-01-01 |  |  |  | Other | Other | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0368 | 2014-03-12 15:00 | Lower Monumental Substation | BPA Power Services |  | Lower Monumental Substation | STUDY COMPLETED | WA | Walla Walla | LL | 2017-10-01 | 2019-09-30 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0367 | 2014-03-04 14:39 | Southeast Richland Substation | City of Richland, Washington |  | BPA's Badger Canyon Substation | WITHDRAWN | WA | Benton | LL | 2017-10-01 |  | 17.3 | 17.3 |  | Other | Other | 17.3 | [6 empty] | 17.3 |  |  | . | [5 empty] | FALSE
G0497 | 2014-01-12 09:46 |  |  |  | Bridge Substation (or new substation nearby) | WITHDRAWN | ID | Cassia | GI | 2017-12-31 | 2021-08-01 | 38 | 45 | NRIS & ERIS | Steam Turbine | Geothermal | 45 | [6 empty] | 45 |  |  | . | [5 empty] | FALSE
L0366 | 2014-01-10 10:00 | New Commercial Load | Blachly-Lane Electric Cooperative | Withdrawn by Customer 3/27/2020 | Albany-Eugene #1 115kV line | WITHDRAWN | OR | Linn | LL | 2017-10-02 | 2024-10-02 | 16.6 | 16.6 |  | Other | Other | 16.6 | [6 empty] | 16.6 |  |  | Customer Delay | [5 empty] | FALSE
G0496 | 2013-12-12 18:00 |  |  |  | Boundary 230 kV Switchyard | WITHDRAWN | WA | Pend Oreille | GI | 2014-03-30 |  | 70 | 70 | ERIS | Hydro | Water | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G0495 | 2013-12-09 14:18 |  |  | FES Report issued | Troutdale, OR or Camas, WA | WITHDRAWN | WA | Clark | GI | 2016-01-01 |  | 60 | 60 | ERIS | Gas Turbine | Natural Gas | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
L0365 | 2013-10-25 10:00 | Blue Lake | Portland General Electric Company |  | BPA's Troutdale Substation | ENERGIZED | OR | Multnomah | LL | 2017-06-01 | 2018-11-06 | 4.3 | 4.3 |  | Other | Other | 4.3 | [6 empty] | 4.3 |  |  | . | [5 empty] | FALSE
L0364 | 2013-09-17 12:00 | Long Canyon | Wells Rural Electric Company | Withdrawn by customer 3/4/16. | BPA's West Wendover Substation | WITHDRAWN | NV | West Wendover | LL | 2017-10-01 |  | 7.4 | 7.4 |  | Other | Other | 7.4 | [6 empty] | 7.4 |  |  | . | [5 empty] | FALSE
L0363 | 2013-08-27 17:00 | Oregon LNG | LNG Development Company, LLC | Withdrawn by BPA 4/30/14 | BPA's Clatsop Substation | WITHDRAWN | OR | Clatsop | LL | 2016-10-03 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0494 | 2013-08-22 12:41 |  |  | Generator Nameplate Rating: 2.75 MW | Harney Substation | WITHDRAWN | OR | Malheur | GI | 2015-05-01 |  | 3 | 3 | ERIS | Hydro | Water | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
G0493 | 2013-08-06 13:01 |  |  | Withdrawn 6/2/2014 | At or near BPA's Bridge Substation. | WITHDRAWN | ID | Cassia | GI | 2016-01-01 |  | 30 | 30 | NRIS & ERIS | Steam Turbine | Geothermal | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
G0492 | 2013-08-02 15:22 | Dworshak Fourth Unit | BPA Power Services | ISIS Report issued 2/4/2014, no impact | Dworshak Substation. | STUDY COMPLETED | ID | Clearwater | GI | 2019-07-01 | 2025-01-01 | 300 | 300 | NRIS | Hydro | Water | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0491 | 2013-07-29 09:04 | Columbia Ridge Landfill Expansion | WM Renewable Energy, LLC |  | Alkali Canyon Substation on BPA's Tower Road-Alkali Canyon 115 kV line. | ENERGIZED | OR | Gilliam | GI | 2014-03-01 | 2014-08-01 | 7 | 7 | ERIS | Reciprocating Engine | Biofuel | 7 | [6 empty] | 7 |  |  | . | [5 empty] | FALSE
L0362 | 2013-07-22 10:00 | Neskowin Substation | Tillamook People's Utility District |  | BPA Tillamook-Boyer 115 kV Line | STUDY | OR | Polk | LL | 2016-10-03 | 2021-10-31 | 6.1 | 6.1 |  | Other | Other | 6.1 | [6 empty] | 6.1 |  |  | . | [5 empty] | FALSE
G0490 | 2013-07-05 15:05 |  |  | FAS Report issued 12/8/2013, no impact |  | STUDY COMPLETED | WA | Douglas | GI | 2022-01-02 | 2020-01-01 | 345 | 345 | ERIS | Hydro | Water | 345 | [6 empty] | 345 |  |  | . | [5 empty] | FALSE
L0361 | 2013-06-27 10:00 | Network Load Expansion Phase 2 | Northern Wasco County People's Utility District |  | Discovery Substation | ENERGIZED | OR | Wasco | LL | 2017-10-01 | 2017-10-02 |  |  |  | Other | Other | 112 | [6 empty] | 112 |  |  | . | [5 empty] | FALSE
L0360 | 2013-06-12 12:23 | EWEB Holden Creek | Eugene Water & Electric Board |  | Cougar-Thruston #1 115kV Line | ENERGIZED | OR | Lane | LL | 2015-10-01 | 2019-10-15 | 10.2 | 10.2 |  | Other | Other | 10.2 | [6 empty] | 10.2 |  |  | . | [5 empty] | FALSE
G0489 | 2013-06-06 11:02 |  |  |  | Low side of existing Wheatfield Wind Power Project, LLC 34.5 kV / 230 kV substation. | WITHDRAWN | OR | Gilliam | GI | 2015-12-15 |  | 5 | 5 | ERIS | Photovoltaic | Solar | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
L0359 | 2013-06-05 14:05 | PSE Cherry Point | Puget Sound Energy, Inc. | Withdrawn by customer. | Loop in of BPA Intalco-Custer #1 230 kV line | WITHDRAWN | WA | Whatcom | LL | 2017-03-01 |  | 1176.2 | 1176.2 |  | Other | Other | 1176.2 | [6 empty] | 1176.2 |  |  | . | [5 empty] | FALSE
G0488 | 2013-05-30 08:51 |  |  | This is a proposed 12.5 MW addition to a 10.2 MW generating capacity of an existing facility, making a combined total of 22.7 MW. |  | WITHDRAWN | ID | Gem | GI | 2016-07-01 |  | 13 | 13 | ERIS | Hydro | Water | 13 | [6 empty] | 13 |  |  | . | [5 empty] | FALSE
G0484 | 2013-05-07 09:20 | Hardeson Battery Storage | Public Utility District No. 1 of Snohomish County |  | BPA's Snohomish Substation | ENERGIZED | WA | Snohomish | GI | 2014-06-02 | 2014-12-23 | 1 | 1 | ERIS | Energy Storage | Battery | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0483 | 2013-05-01 15:10 |  |  | Generator Nameplate Rating: 2,165 kW; FAS issued 3/12/14; Request reduced to 2 MW on 12/10/14. | Trout Creek Field @ Wind River Business Park, Hemlock WA | WITHDRAWN | WA | Skamania | GI | 2014-05-01 | 2020-01-01 | 2 | 2 | ERIS | Reciprocating Engine | Biofuel | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0482 | 2013-04-30 14:06 |  |  | Project status has been changed to 'Withdrawn' as the Plan-of-Service requires only a meter installation and needs no technical or procedural study. | 11814 Hwy 12, Randle, WA 98377 | WITHDRAWN | WA | Lewis | GI | 2013-07-01 | 2017-09-30 | 1 | 1 | ERIS | Hydro | Water | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0481 | 2013-04-25 16:55 | Harbour Pointe | UniEnergy Technologies, LLC | Generator Nameplate Rating: 1.5 MW | Snohomish PUD's 12 kV distribution system (Harbour Pointe circuit 12-2277) | ENERGIZED | WA | Snohomish | GI | 2013-08-01 |  | 2 | 2 | ERIS | Energy Storage | Battery | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0480 | 2012-12-10 09:55 | G0480 Port of Tillamook Bay Gas Digester Project | Port of Tillamook Bay |  | TPUD Distribution System | ENERGIZED | OR | Tillamook | GI | 2013-05-30 | 2013-08-06 | 2 | 2 | ERIS | Reciprocating Engine | Biofuel | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
L0358 | 2012-11-23 10:36 | L0358 City of Ellensburg Helena Avenue Sub | City of Ellensburg |  | A proposed new Helena Avenue substation tap on the existing 115 kV East Ellensburg Tap approx. 2.1 miles before East Ellensburg Sub. | ENERGIZED | WA | Yakima | LL | 2015-12-31 | 2017-06-30 |  |  |  | Other | Other | 8 | [6 empty] | 8 |  |  | . | [5 empty] | FALSE
L0357 | 2012-11-15 10:00 | UEC McNary 115KV Breaker 3 | Umatilla Electric Cooperative |  | BPA McNary Substation | ENERGIZED | OR | Umatilla | LL | 2015-10-01 | 2016-10-26 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0479 | 2012-10-22 16:30 |  |  |  | Tap of 115 kV BPA line between LaPine and Fort Rock. POI approx. 1 mile N of the Fort Rock Substation. | WITHDRAWN | OR | Lake | GI | 2014-12-31 |  | 100 | 100 | NRIS & ERIS | Photovoltaic | Solar | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0356 | 2012-09-25 14:00 | Benton REA Huard Road | Benton Rural Electric Association | Withdrawn by Customer | Prosser Tap off Grandview to Snipes 115kV Line | WITHDRAWN | WA | Benton | LL | 2015-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | Customer Delay | [5 empty] | FALSE
L0355 | 2012-09-10 12:00 | Network Load Expansion | Northern Wasco County People's Utility District |  | Chenoweth-The Dalles 115 kV Line | ENERGIZED | OR | Wasco | LL | 2017-10-01 | 2017-10-01 |  |  |  | Other | Other | 90 | [6 empty] | 90 |  |  | . | [5 empty] | FALSE
G0478 | 2012-09-06 14:13 |  |  | FAS issued 7/17/14 | BPA's proposed Longhorn 500/230 kV Substation. | STUDY COMPLETED | OR | Morrow | GI | 2016-11-01 | 2028-09-30 | 500 | 500 | NRIS & ERIS | Photovoltaic | Solar | 300 | Energy Storage | Battery | 200 |  |  |  | 500 |  |  | . | [5 empty] | FALSE
G0477 | 2012-09-05 15:48 |  |  | Draft FAS report issued 5/15/14; final FAS pending | BPA's 230 kV Pilot Butte to LaPine transmission line, preferably via a line tap. | WITHDRAWN | OR | Deschutes | GI | 2015-12-31 |  | 38 | 38 | ERIS | Steam Turbine | Geothermal | 38 | [6 empty] | 38 |  |  | . | [5 empty] | FALSE
L0354 | 2012-08-09 14:01 | Cowlitz John Street | Public Utility District No. 1 of Cowlitz County | Withdrawn by Customer 2/1/13 | BPA Lexington Substation | WITHDRAWN | WA | Cowlitz | LL | 2015-11-06 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0351 | 2012-08-03 09:00 | PDX-1 and PDX-4 Data Centers - Phase 2 | Umatilla Electric Cooperative |  | Morrow Flats Substation | ENERGIZED | OR | Morrow | LL | 2015-11-02 | 2016-10-26 |  |  |  | Other | Other | 225 | [6 empty] | 225 |  |  | . | [5 empty] | FALSE
L0352 | 2012-08-03 09:00 | PDX-2 Data Center - Phase 2 | Umatilla Electric Cooperative |  | BPA McNary | ENERGIZED | OR | Morrow | LL | 2015-11-02 | 2016-10-26 |  |  |  | Other | Other | 117 | [6 empty] | 117 |  |  | . | [5 empty] | FALSE
L0353 | 2012-08-03 09:00 | Hat Rock | Umatilla Electric Cooperative | Withdrawn by Customer | BPA Hat Rock | WITHDRAWN | OR | Umatilla | LL | 2015-11-02 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0476 | 2012-07-18 09:53 | The Dalles Northshore Fishway Project | Northern Wasco County People's Utility District | On-line January 2013 | Existing Interconnection Point at Spearfish Substation | ENERGIZED | OR | Wasco | GI | 2012-11-12 | 2013-01-01 | 7 | 7 | ERIS | Hydro | Water | 7 | [6 empty] | 7 |  |  | . | [5 empty] | FALSE
L0350 | 2012-07-11 13:25 | Skokomish Substation | Public Utility District No. 1 of Mason County |  |  | ENERGIZED | WA | Mason | LL | 2013-10-31 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0349 | 2012-07-05 10:00 | Canby Substation | PacifiCorp | Withdrawn effective 6/10/15. | BPA's Canby Substation | WITHDRAWN | CA | Modoc | LL | 2014-10-31 |  |  |  |  | Other | Other | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0348 | 2012-06-25 09:00 | McNary 115kV Breaker | Umatilla Electric Cooperative |  | McNary Substation | ENERGIZED | OR | Umatilla | LL | 2015-10-01 | 2016-10-26 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0475 | 2012-06-21 11:42 | City of Walla Walla Mill Creek Hydroelectric | Columbia Rural Electric Association |  | Walla Walla Substation point of delivery #4048. | ENERGIZED | WA | Walla Walla | GI | 2013-01-01 | 2013-01-11 | 3 | 3 | ERIS | Hydro | Water | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
L0347 | 2012-05-29 09:00 | LNG Compressor Load | Columbia River People's Utility District | Withdrawn by customer. | St. Johns-Allston 115kV | WITHDRAWN | OR | Columbia | LL | 2017-10-01 |  | 40 | 40 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0346 | 2012-05-18 09:00 | Airport Substation | Consumers Power, Inc. |  | Albany-Lebanon 115kV #1 | ENERGIZED | OR | Linn | LL | 2013-11-01 | 2016-12-15 |  |  |  | Other | Other | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
L0345 | 2012-05-15 14:00 | Big Eddy-Redmond 230kV Line | Central Electric Cooperative, Inc. |  | BPA Big Eddy-Redmond #1 230kV Line | STUDY COMPLETED | OR | Wasco | LL | 2015-06-01 | 2021-09-20 | 22.9 | 22.9 |  | Other | Other | 22.9 | [6 empty] | 22.9 |  |  | . | [5 empty] | FALSE
G0473 | 2012-05-12 16:41 |  |  | Withdrawn on October 7, 2013. | Wasco Electric Cooperative's 115 kV Line. | WITHDRAWN | OR | Wasco | GI | 2013-07-15 |  | 10 | 10 | ERIS | Wind Turbine | Wind Turbine | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0474 | 2012-05-12 16:41 |  |  | Withdrawn on June 29, 2012. | Wasco Electric Cooperative's 115 kV line. | WITHDRAWN | OR | Wasco | GI | 2013-07-15 |  | 10 | 10 | ERIS | Wind Turbine | Wind Turbine | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0471 | 2012-04-11 16:44 |  |  | Withdrawn on March 8, 2013. | Harvalum 230 kV Substation | WITHDRAWN | WA | Klickitat | GI | 2016-03-01 |  | 590 | 590 | ERIS | Gas Turbine | Natural Gas | 590 | [6 empty] | 590 |  |  | . | [5 empty] | FALSE
G0470 | 2012-03-21 14:07 |  |  | 02/15/22 Generator Retired. | Breaker 51 out of Booth Bend. | DECOMMISSIONED | OR | Yamhill | GI | 2012-10-15 | 2012-10-18 | 1 | 1 | ERIS | Reciprocating Engine | Biofuel | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0344 | 2012-03-15 09:00 | Slatt Substation | PacifiCorp | LLIR withdrawn by customer on February 19, 2013. | At or near Slatt Substation | WITHDRAWN | OR | Gilliam | LL | 2015-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0469 | 2012-01-27 10:07 | Whitefish In-Line Hydroelectric Project | City of Whitefish, Montana | Generator Nameplate: 261 kW | BPA's Flathead Substation | ENERGIZED | MT | Flathead | GI | 2012-08-07 | 2012-09-14 | 1 | 1 | ERIS | Hydro | Water | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0340 | 2011-12-13 17:00 | DLB2 | Umatilla Electric Cooperative |  | Boardman or Longhorn | ENERGIZED | OR | Morrow | LL | 2015-10-01 | 2016-10-26 | 90 | 90 |  | Other | Other | 105 | [6 empty] | 105 |  |  | . | [5 empty] | FALSE
L0341 | 2011-12-13 17:00 | Maverick Data Center | Umatilla Electric Cooperative | Withdrawn by customer 8/3/2012 | Boardman | WITHDRAWN | OR | Morrow | LL | 2015-10-01 |  | 30 | 30 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0342 | 2011-12-13 17:00 | PDX1&4 Data Centers | Umatilla Electric Cooperative |  | Boardman | ENERGIZED | OR | Morrow | LL | 2015-10-01 | 2016-10-26 | 60 | 60 |  | Other | Other | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
L0343 | 2011-12-13 17:00 | PDX2 | Umatilla Electric Cooperative |  | McNary | ENERGIZED | OR | Morrow | LL | 2015-10-01 | 2016-10-26 | 30 | 30 |  | Other | Other | 29 | [6 empty] | 29 |  |  | . | [5 empty] | FALSE
L0339 | 2011-12-07 09:42 | Bertelsen-Seneca Upgrade | Eugene Water & Electric Board |  | BPA Eugene Substation | ENERGIZED | OR | Lane | LL | 2014-12-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0468 | 2011-12-06 15:57 | Stoltze Land and Lumber Project | F.H. Stoltze Land and Lumber Co. | Generator Nameplate: 2.5 MW | Flathead 12.5 kV Radial from Trumble Creek Substation. | ENERGIZED | MT | Flathead | GI | 2013-10-01 | 2013-10-01 | 3 | 3 | ERIS | Reciprocating Engine | Biofuel | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
L0338 | 2011-10-26 13:39 | Worden Substation | Columbia Rural Electric Association |  | BPA's Franklin-Walla Walla 115kV Line 13/6 | ENERGIZED | WA | Franklin | LL | 2013-01-01 | 2017-01-31 |  |  |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0337 | 2011-10-24 09:18 | DLB1 | Umatilla Electric Cooperative |  | BPA's future Longhorn Substation | ENERGIZED | OR | Morrow | LL | 2015-02-11 | 2016-10-26 | 30 | 30 |  | Other | Other | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0467 | 2011-10-19 14:42 |  |  | Withdrawn by Customer on December 19, 2011. | BPA's Maupin Substation from at or near Wasco's Antelope Substation. | WITHDRAWN | OR | Wasco | GI | 2015-12-31 |  | 101 | 101 | NRIS & ERIS | Wind Turbine | Wind Turbine | 101 | [6 empty] | 101 |  |  | . | [5 empty] | FALSE
L0336 | 2011-10-05 15:37 | S. Tacoma-Southwest 230kV, Tacoma-Southwest 230kV | Tacoma Power |  | BPA Tacoma & BPA South Tacoma Substations | ENERGIZED | WA | Pierce | LL | 2012-05-31 | 2013-07-18 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0466 | 2011-10-04 10:36 | Sisters Irrigation Hydro Project | Three Sisters Irrigation District |  | 68000 Hwy 20 W, Bend, OR 97701 | ENERGIZED | OR | Deschutes | GI | 2013-09-03 | 2014-07-15 | 1 | 1 | ERIS | Hydro | Water | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0465 | 2011-09-15 14:46 |  |  | Withdrawn on May 11,2012. | Wasco Electric Cooperative's 115 kV line. | WITHDRAWN | OR | Wasco | GI | 2012-12-31 |  | 10 | 10 | ERIS | Wind Turbine | Wind Turbine | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0335 | 2011-09-13 09:43 | Project Maverick | Central Electric Cooperative, Inc. | Withdrawn by customer | BPA's Ponderosa Substation | WITHDRAWN | OR | Crook | LL | 2012-10-01 | 2029-10-01 |  |  |  | Other | Other | 31 | [6 empty] | 31 |  |  | . | [5 empty] | FALSE
G0464 | 2011-09-02 11:23 |  |  |  | CPUD feeder connected to CPUD's King Station and closest BPA point of receipt is BPA's Ross Substation. | WITHDRAWN | WA | Clark | GI | 2013-09-12 |  | 5 | 5 | ERIS | Reciprocating Engine | Biofuel | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
G0463 | 2011-09-01 12:11 |  |  | Withdrawn on September 6, 2013. | BPA's 230 kV transmission facilities at Ponderosa Substation. | WITHDRAWN | OR | Lake, Harney | GI | 2014-12-31 |  | 400 | 400 | NRIS & ERIS | Wind Turbine | Wind Turbine | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0462 | 2011-09-01 12:10 |  |  | Withdrawn by Customer on February 27, 2012. | BPA's transmission facilities at Summer Lake Substation. | WITHDRAWN | OR | Lake, Harney | GI | 2014-12-31 |  | 500 | 500 | NRIS & ERIS | Wind Turbine | Wind Turbine | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G0461 | 2011-08-12 15:54 |  |  | Withdrawn on May 11,2012 | Wasco Electric Cooperative's 115 kV Line. | WITHDRAWN | OR | Wasco | GI | 2012-12-31 |  | 10 | 10 | ERIS | Wind Turbine | Wind Turbine | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0334 | 2011-08-12 09:38 | Grand Coulee-Westside | Avista Corporation | Withdrawn by Avista 11/20/12. | BPA's Grand Coulee-Westside 230kV Transmission Line near mile 76, tower 3 | WITHDRAWN | WA | Grant | LL | 2014-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0460 | 2011-08-10 15:32 |  |  | Withdrawn on September 6, 2013 | BPA's McNary Substation. | WITHDRAWN | OR | Umatilla | GI | 2015-01-01 |  | 220 | 220 | NRIS & ERIS | Gas Turbine | Natural Gas | 220 | [6 empty] | 220 |  |  | . | [5 empty] | FALSE
G0459 | 2011-08-07 16:21 |  |  | Withdrawn by Customer on December 20,2011. | At a point on BPA's Albany-Salem 115 kV transmsission line within a mile either side of Conser Road. | WITHDRAWN | OR | Linn | GI | 2013-05-01 |  | 65 | 45 | NRIS & ERIS | Gas Turbine | Natural Gas | 65 | [6 empty] | 65 |  |  | . | [5 empty] | FALSE
L0333 | 2011-08-05 10:22 | La Grande Substation | Oregon Trail Electric Consumers Cooperative, Inc. | Withdrawn by Customer | BPA's La Grande Substation | WITHDRAWN | OR | Union | LL | 2015-01-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0458 | 2011-08-04 09:25 |  |  | Withdrawn on May 2, 2012 | Oregon Trail Electric Cooperative's Cove Avenue Substation | WITHDRAWN | OR | Union | GI | 2011-12-31 |  | 2 | 2 | ERIS | Photovoltaic | Solar | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0457 | 2011-07-28 16:10 | Carty CCCT | Portland General Electric Company | Increment to Interconnection Request G0380; Expected Synch date 11/15/15 | Slatt substation. | ENERGIZED | OR | Morrow | GI | 2015-05-01 | 2016-08-01 | 36 | 36 | NRIS | Gas Turbine | Natural Gas | 36 | [6 empty] | 36 |  |  | . | [5 empty] | FALSE
L0332 | 2011-06-30 09:57 | Baldwin Data Center | Central Electric Cooperative, Inc. | Withdrawn by customer | BPA Ponderosa Substation | WITHDRAWN | OR | Crook | LL | 2014-10-01 | 2029-10-01 |  |  |  | Other | Other | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G0456 | 2011-06-08 15:35 |  |  |  | At existing interconnection facilities in BPA's Fairmount Substation. | WITHDRAWN | WA | Jefferson | GI | 2013-12-31 |  | 25 | 25 | NRIS & ERIS | Reciprocating Engine | Biofuel | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G0455 | 2011-05-20 11:31 |  |  |  | In the area of Ione Substation/Kinger Tap. | WITHDRAWN | OR | Morrow | GI | 2014-12-31 |  | 50 | 50 | NRIS & ERIS | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
L0331 | 2011-05-12 12:59 | CEC POD at Ponderosa | Central Electric Cooperative, Inc. | Withdrawn by customer | BPA Ponderosa Substation | WITHDRAWN | OR | Crook | LL | 2014-10-01 | 2029-10-01 |  |  |  | Other | Other | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0454 | 2011-05-11 10:53 |  |  |  | Slatt Substation | WITHDRAWN | OR | Morrow | GI | 2012-12-01 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0452 | 2011-05-10 00:45 |  |  | FAS issued 7/17/14 | BPA's McNary Substation at 500 kV. | WITHDRAWN | OR | Umatilla | GI | 2015-06-01 | 2022-09-30 | 410 | 390 | NRIS & ERIS | Gas Turbine | Natural Gas | 410 | [6 empty] | 410 |  |  | . | [5 empty] | FALSE
G0453 | 2011-05-06 11:53 | University of Oregon CoGeneration | University of Oregon | on-line September 2012 | EWEB's new UofO Substation | ENERGIZED | OR | Lane | GI | 2012-06-01 | 2012-10-30 | 11 | 11 | ERIS | Gas Turbine | Natural Gas | 11 | [6 empty] | 11 |  |  | . | [5 empty] | FALSE
L0330 | 2011-04-28 09:00 | Addy | New Customer Pending | Withdrawn by customer 11/9/11. | BPA's Addy Substation | WITHDRAWN | WA | Stevens | LL | 2013-10-31 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0329 | 2011-04-22 09:00 | Red Mountain-Reata 115kV/Dallas Road Substation | City of Richland, Washington | Withdrawn by customer | BPA's Red Mountain-Badger Canyon 115kV Transmission Line | WITHDRAWN | WA | Benton | LL | 2013-10-31 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0327 | 2011-04-19 06:58 | Lower Snake Redundant PH Tie Lines | US Department of Army Corps of Engineers |  | Lower Monumental Little Goose Lower Granite | WITHDRAWN | WA | Walla Walla | LL | 2013-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0328 | 2011-04-14 11:20 | Ellensburg-Moxee Tap | Public Utility District No. 1 of Kittitas County | Withdrawn by customer 11/26/12 | Columbia-Moxee 115kV Line | WITHDRAWN | WA | Kittitas | LL | 2013-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0450 | 2011-03-16 16:04 | Farm Power Tillamook | Farm Power Tillamook LLC |  | Tillamook PUD's Feeder Circuit #63, connected to the Wilson River Substation. | ENERGIZED | OR | Tillamook | GI | 2011-11-01 | 2012-04-20 | 1 | 1 | ERIS | Reciprocating Engine | Biofuel | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0326 | 2011-03-07 14:46 | Ponderosa Substation | PAC |  | BPA Ponderosa Substation | ENERGIZED | OR | Crook | LL | 2013-10-01 | 2013-04-23 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0325 | 2011-02-15 10:41 | Alcoa Substation | Clark Public Utilities |  | BPA Alcoa Substation | STUDY COMPLETED | WA | Clark | LL | 2013-09-01 | 2018-12-31 | 6 | 6 |  | Other | Other | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
G0449 | 2011-02-11 15:01 | Farm Power Misty Meadow | Farm Power Misty Meadow, LLC |  | Tillamook PUD's Feeder Circuit #63, connected to the Wilson River Substation. | ENERGIZED | OR | Tillamook | GI | 2011-11-01 | 2013-01-10 | 1 | 1 | ERIS | Reciprocating Engine | Biofuel | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0324 | 2011-01-10 11:47 | Knights Bridge Substation | Canby Utility Board |  | Knigts Bridge Rd & S. Barlow Rd (adjacent to PGE Canby Sub) | ENERGIZED | CA | Modoc | LL | 2013-10-01 |  | 7.2 | 7.2 |  | Other | Other | 7.2 | [6 empty] | 7.2 |  |  | . | [5 empty] | FALSE
G0447 | 2010-12-16 13:58 |  |  | Withdrawn by Customer on November 19, 2011. | A proposed new substation on BPA's McNary-Calpine 500 kV transmission line. | WITHDRAWN | OR | Morrow | GI | 2013-05-01 |  | 215 | 240 | NRIS & ERIS | Gas Turbine | Natural Gas | 240 | [6 empty] | 240 |  |  | . | [5 empty] | FALSE
G0446 | 2010-12-16 13:57 |  |  | Withdrawn by customer; letter instructions received November 15, 2013. | A proposed new substation on BPA's McNary-Coyote Springs 500 kV transmission line. | WITHDRAWN | OR | Morrow | GI | 2013-05-01 |  | 215 | 240 | NRIS & ERIS | Gas Turbine | Natural Gas | 240 | [6 empty] | 240 |  |  | . | [5 empty] | FALSE
L0323 | 2010-12-14 15:14 | Aurora Project | City of Richland, Washington | Withdrawn by customer 4/21/14 | BPA Ashe Substation and Ashe-Coyote Springs Transmission Line | WITHDRAWN | WA | Benton | LL | 2012-07-14 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0448 | 2010-12-13 19:12 |  |  | Status changed to Withdrawn on 8/27/14. Customer failed to timely execute an agreement. | Idahome Substation | WITHDRAWN | ID | Cassia | GI | 2011-09-01 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0445 | 2010-12-07 02:09 |  |  | Status changed to Withdrawn on 8/27/14. Customer did not timely execute an agreement. | Idahome Substation | WITHDRAWN | ID | Cassia | GI | 2011-09-01 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0441 | 2010-11-03 15:44 | Esquatzel Project | Green Energy Today, LLC |  | Pole 66 G 129 at the Esquatzel Canal and Columbia River Road | ENERGIZED | WA | Franklin | GI | 2011-02-01 | 2011-11-23 | 2 | 2 | ERIS | Hydro | Water | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0440 | 2010-11-02 23:52 |  |  |  | UEC's Butter Creek Substation | WITHDRAWN | OR | Umatilla | GI | 2011-12-31 |  | 10 | 10 | ERIS | Wind Turbine | Wind Turbine | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0439 | 2010-11-02 10:55 |  |  | on-line | Blachly-Lane Electric Cooperative's Parker Substation | DECOMMISSIONED | OR | Lane | GI | 2011-10-31 | 2013-09-05 | 2 | 2 | ERIS | Reciprocating Engine | Biofuel | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0443 | 2010-10-22 23:59 |  |  | Withdrawn on 10/31/13 | Canal to Minidoka BPA 13.8kV line, 6-8 miles south of Minidoka. | WITHDRAWN | ID | Cassia | GI | 2011-12-31 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0442 | 2010-10-22 23:57 |  |  | Withdrawn 10/31/13 | Canal to Minidoka BPA 13.8kV line, 6-8 miles South of Minidoka Dam | WITHDRAWN | ID | Cassia | GI | 2011-12-31 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0438 | 2010-10-15 17:38 |  |  |  | On BPA's Salem-Grande Ronde-Tillamook line east of PGE's Grande Ronde Substation. | WITHDRAWN | OR | Polk and Lincoln | GI | 2013-10-01 |  | 125 | 125 | NRIS & ERIS | Wind Turbine | Wind Turbine | 125 | [6 empty] | 125 |  |  | . | [5 empty] | FALSE
G0437 | 2010-09-30 21:13 |  |  | Withdrawn by Customer 6/23/2015. | Ponderosa 230kV | WITHDRAWN | OR | Lake | GI | 2013-12-31 |  | 30 | 38 | ERIS | Steam Turbine | Geothermal | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
L0322 | 2010-09-29 14:18 | Klondike/Blalock Reinforcement | Wasco Electric Cooperative, Inc. |  | BPA's DeMoss 115kV Substation | WITHDRAWN | OR | Sherman | LL | 2014-07-01 | 2018-03-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0321 | 2010-09-29 13:56 | Fossil-Big Eddy Loop | Wasco Electric Cooperative, Inc. | Withdrawn effective April 9, 2013 | 69kV loop from Fossil to Maupin and Maupin to Big Eddy | WITHDRAWN | OR | Sherman | LL | 2013-07-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0436 | 2010-09-27 20:16 |  |  |  | Stanfield | WITHDRAWN | OR | Morrow and Umatilla | GI | 2014-12-31 |  | 481 | 481 | NRIS & ERIS | Wind Turbine | Wind Turbine | 481 | [6 empty] | 481 |  |  | . | [5 empty] | FALSE
G0444 | 2010-09-10 16:50 |  |  | Withdrawn 11/25/13 | Cowlitz 115 | WITHDRAWN | WA | Cowlitz | GI | 2011-10-01 |  | 35 | 35 | NRIS & ERIS | Reciprocating Engine | Biofuel | 35 | [6 empty] | 35 |  |  | . | [5 empty] | FALSE
G0435 | 2010-08-27 21:13 |  |  | Comprehensive FAS issued 3/7/2014 | New substation on 500 kV McNary-HPP Line | STUDY COMPLETED | OR | Morrow | GI | 2013-11-01 | 2028-12-31 | 238 | 238 | NRIS & ERIS | Wind Turbine | Wind Turbine | 238 | [6 empty] | 238 |  |  | . | [5 empty] | FALSE
L0320 | 2010-08-23 15:49 | Woodland Tap | Public Utility District No. 1 of Cowlitz County | Request withdrawn by customer on 10/24/12. | BPA Woodland Tap, Ross-Lexington 230kV Line | WITHDRAWN | WA | Cowlitz | LL | 2012-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0434 | 2010-08-19 20:49 |  |  | Withdrawn on January 28, 2011. | At Emerald PUD Facility 12.47 kV bus A-3 | WITHDRAWN | OR | Linn | GI | 2012-03-01 |  | 11 | 11 | ERIS | Reciprocating Engine | Biofuel | 11 | [6 empty] | 11 |  |  | . | [5 empty] | FALSE
G0433 | 2010-08-02 10:24 | Outback | Outback Solar, LLC |  | Midstate Electric 24.9 kV distribution system | ENERGIZED | OR | Lake | GI | 2010-11-15 |  | 1 | 1 | ERIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
G0432 | 2010-07-08 20:21 |  |  | Incremental to Request No. G105. May 25, 2011: reduced from 31 to 18 MW | BPA's Bettas Road 230 kV Substation | WITHDRAWN | WA | Kittitas | GI | 2012-12-01 |  | 18 | 18 | ERIS | Wind Turbine | Wind Turbine | 18 | [6 empty] | 18 |  |  | . | [5 empty] | FALSE
G0431 | 2010-06-30 14:47 |  |  | Awaiting Customer permits | Fort Rock Substation | WITHDRAWN | OR | Lake | GI | 2012-06-29 | 2018-12-31 | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0430 | 2010-05-14 12:48 |  |  | Withdrawn by customer by letter received May 4, 2011. | Red Mountain Sub | WITHDRAWN | WA | Benton | GI | 2013-12-31 |  | 200 | 200 | NRIS & ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0429 | 2010-05-06 17:08 |  |  |  |  | WITHDRAWN | OR | Wasco | GI | 2012-12-31 |  | 135 | 135 | NRIS & ERIS | Wind Turbine | Wind Turbine | 135 | [6 empty] | 135 |  |  | . | [5 empty] | FALSE
G0428 | 2010-05-06 12:23 |  |  | Comprehensive FAS issued 3/7/2014 | New substation on 500 kV McNary-HPP Line | WITHDRAWN | OR | Morrow | GI | 2014-12-01 | 2020-09-30 | 201 | 201 | NRIS & ERIS | Wind Turbine | Wind Turbine | 201 | [6 empty] | 201 |  |  | . | [5 empty] | FALSE
G0427 | 2010-04-30 14:26 |  |  | Withdrawn by Customer on June 18, 2010. | TBD | WITHDRAWN | OR | Wheeler | GI | 2013-04-01 |  | 300 | 300 | NRIS & ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0426 | 2010-04-23 12:34 |  |  | Withdrawn by Customer on March 17, 2011. | BPA's transmission facilities in or near Shelton substation. | WITHDRAWN | WA | Mason | GI | 2013-06-01 |  | 31 | 31 | ERIS | Reciprocating Engine | Biofuel | 31 | [6 empty] | 31 |  |  | . | [5 empty] | FALSE
G0424 | 2010-04-22 11:34 |  |  | Withdrawn on September 27, 2010. | Summer Lake substation. | WITHDRAWN | OR | Lake | GI | 2013-12-31 |  | 103 | 103 | ERIS | Wind Turbine | Wind Turbine | 103 | [6 empty] | 103 |  |  | . | [5 empty] | FALSE
G0425 | 2010-04-22 11:34 |  |  | Withdrawn on September 27, 2010. | Summer Lake Subtstation. | WITHDRAWN | OR | Lake | GI | 2013-12-31 |  | 103 | 103 | ERIS | Wind Turbine | Wind Turbine | 103 | [6 empty] | 103 |  |  | . | [5 empty] | FALSE
G0423 | 2010-04-09 14:37 |  |  |  | 115 kV BPA De Moss-Big Eddy line (4.2 miles west of De Moss Substation) | WITHDRAWN | OR | Grant | GI | 2011-07-26 |  | 10 | 10 | ERIS | Wind Turbine | Wind Turbine | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0422 | 2010-04-09 13:07 |  |  | Withdrawn by Customer on June 18, 2010, following Scoping Meeting. | Fossil Substation | WITHDRAWN | OR | Wheeler | GI | 2013-04-01 |  | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0420 | 2010-04-06 12:58 | Lund Hill | Pacific Wind Development, LLC | FAS Restudy Issued 1/19/2017. 4/3/2018: Resource fuel type changed from wind to solar. | BPA's Rock Creek Substation | ENERGIZED | WA | Klickitat | GI | 2020-12-31 | 2022-01-21 | 60 | 60 | Energy | Photovoltaic | Solar | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
G0421 | 2010-04-05 07:16 |  |  |  | BPA's Gardiner Substation via Douglas Electric Cooperative's Transmission/Distribution Facility. | WITHDRAWN | OR | Douglas | GI | 2012-06-01 | 2019-01-01 | 2 | 2 | ERIS | Wave | Water | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0419 | 2010-04-01 14:22 | Nippon Biomass | Nippon Paper Industries USA Co., Ltd. | Operational | At the 69kV bus in BPA's Port Angeles Substation. | ENERGIZED | WA | Clallam | GI | 2012-04-30 | 2013-04-01 | 20 | 20 | NRIS | Reciprocating Engine | Biofuel | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0418 | 2010-03-29 10:50 |  |  |  | Boardman 115 | WITHDRAWN | OR | Morrow | GI | 2011-06-15 | 2018-12-31 | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0417 | 2010-03-25 10:31 |  |  | Request reduced to 50 MW per letter received on January 3, 2011. | Into the Wendover-Minidoka 138 kV transmission line. | WITHDRAWN | UT | Box Elder | GI | 2013-10-01 |  | 50 | 50 | NRIS & ERIS | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0416 | 2010-03-23 18:04 |  |  | effective July 30, 2010, G0416 seeks interconnection of a reduced nameplate generating capacity of 20 MW (in lieu of 75 MW). | To BPA's Transmission Facilities through the 115 kV facilities of Midstate Electric Cooperative. Midstate Electric Coop 115 kV line | WITHDRAWN | OR | Lake | GI | 2012-09-30 | 2020-12-30 | 20 | 20 | NRIS & ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0415 | 2010-03-22 11:21 |  |  | Withdrawn on January 28, 2011 | BPA's 115 kV Transmission Facilities at or near Fern Hill Substation. | WITHDRAWN | OR | Clatsop | GI | 2012-04-01 |  | 20 | 20 | ERIS | Reciprocating Engine | Biofuel | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0413 | 2010-03-19 09:28 |  |  | Withdrawn by Customer on September 1, 2011. | BPA's Summer Lake Substation at 230 kV | WITHDRAWN | OR | Lake | GI | 2012-12-31 |  | 103 | 103 | NRIS & ERIS | Wind Turbine | Wind Turbine | 103 | [6 empty] | 103 |  |  | . | [5 empty] | FALSE
G0414 | 2010-03-19 09:28 |  |  | Withdrawn by Customer on September 1, 2011. | BPA's Summer Lake Substation at 230 kV | WITHDRAWN | OR | Lake | GI | 2012-12-31 |  | 103 | 103 | NRIS & ERIS | Wind Turbine | Wind Turbine | 103 | [6 empty] | 103 |  |  | . | [5 empty] | FALSE
G0412 | 2010-03-12 14:37 |  |  | Withdrawn on April 13, 2010 | Minidoka-Unity 138 kV line | WITHDRAWN | ID | Cassia | GI | 2011-12-01 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0411 | 2010-03-12 14:35 |  |  | Withdrawn on April 13, 2010 | Minidoka-Unity 138 kV line | WITHDRAWN | ID | Cassia | GI | 2011-12-01 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0409 | 2010-02-26 09:20 |  |  | Awaiting Customer permits | TO THE MIDSTATE ELECTRIC 24.9 KV DISTRIBUTION SYSTEM ON THE EAST BORDER OF THE PROPERTY, ALONG OIL DRI ROAD. | WITHDRAWN | OR | Lake | GI | 2010-12-07 | 2021-09-25 | 5 | 5 | ERIS | Photovoltaic | Solar | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
G0410 | 2010-02-26 09:20 |  |  | Awaiting Customer permits. | TO THE MIDSTATE ELECTRIC 24.9 KV DISTRIBUTION SYSTEM ON THE WEST BORDER OF THE PROPERTY, ALONG FOSSIL LAKE ROAD. | WITHDRAWN | OR | Lake | GI | 2010-12-07 | 2021-09-25 | 5 | 5 | ERIS | Photovoltaic | Solar | 5 | [6 empty] | 5 |  |  | . | [5 empty] | FALSE
G0408 | 2010-02-09 09:43 |  |  | Comprehensive FAS issued 3-7-2014 |  | WITHDRAWN | OR | Umatilla | GI | 2012-12-01 |  | 400 | 400 | NRIS & ERIS | Wind Turbine | Wind Turbine | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G0407 | 2010-02-04 09:41 | Coastal Energy Project | Coastal Energy Project, LLC | on-line June 2010 | Grays Harbor PUD 15 kV Distribution Pole Number P1/64 | ENERGIZED | WA | Grays Harbor | GI | 2010-05-17 |  | 6 | 6 | ERIS | Wind Turbine | Wind Turbine | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
G0406 | 2010-02-01 15:08 |  |  | Withdrawn by Customer on September 14, 2010. | BPA’s Big Eddy-McNary 230 kV Transmission Line in Klickitat County, Wash. | WITHDRAWN | WA | Klickitat | GI | 2012-12-31 |  | 99 | 99 | ERIS | Wind Turbine | Wind Turbine | 99 | [6 empty] | 99 |  |  | . | [5 empty] | FALSE
G0405 | 2010-01-29 12:45 |  |  | Withdrawn by Customer on November 1, 2010. | BPA’s Goshen-Drummond No. 1 161 kV Transmission Line in Madison Co. Idaho | WITHDRAWN | ID | Madison | GI | 2010-11-30 |  | 240 | 240 | NRIS | Wind Turbine | Wind Turbine | 240 | [6 empty] | 240 |  |  | . | [5 empty] | FALSE
G0403 | 2010-01-27 16:51 |  |  | FAS issued 7/17/14 | New substation on 500 kV McNary-HPP Line | WITHDRAWN | OR | Morrow | GI | 2014-11-01 | 2025-01-01 | 302 | 302 | NRIS | Wind Turbine | Wind Turbine | 302 | [6 empty] | 302 |  |  | . | [5 empty] | FALSE
G0404 | 2010-01-27 16:51 |  |  | FAS issued 7/17/14 | New substation on 500 kV McNary-HPP Line | WITHDRAWN | OR | Morrow | GI | 2014-11-01 | 2025-01-01 | 302 | 302 | NRIS | Wind Turbine | Wind Turbine | 302 | [6 empty] | 302 |  |  | . | [5 empty] | FALSE
G0402 | 2010-01-12 09:19 |  |  | Withdrawn on July 1, 2013 |  | WITHDRAWN | OR | Sherman | GI | 2013-10-01 |  | 110 | 110 | ERIS | Wind Turbine | Wind Turbine | 110 | [6 empty] | 110 |  |  | . | [5 empty] | FALSE
G0401 | 2010-01-12 03:44 |  |  | FAS Study Issued 9/16/2011 Optional Study issued 6/25/2012 | BPA’s 230 kV Transmission Facilities in or close to Maupin Substation. | WITHDRAWN | OR | Wasco | GI | 2013-12-31 |  | 299 | 299 | NRIS & ERIS | Wind Turbine | Wind Turbine | 299 | [6 empty] | 299 |  |  | Awaiting Customer Permits To Complete NEPA Review | [5 empty] | FALSE
G0400 | 2010-01-06 09:23 |  |  | Withdrawn on January 5, 2011 | 115 kV Fort Rock Line(between LaPine Substation and Midstate’s Fort Rock Substation) | WITHDRAWN | OR | Lake | GI | 2011-12-31 |  | 20 | 20 | ERIS | Photovoltaic | Solar | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0399 | 2009-12-16 15:00 |  |  | Withdrawn on July 21, 2010 | The 69 kV transmission system of Columbia Basin Electric Cooperative, approximately 15 line miles from BPA’s Ione Substation | WITHDRAWN | OR | Morrow | GI | 2010-08-01 |  | 10 | 10 | Energy | Reciprocating Engine | Biofuel | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0397 | 2009-12-15 09:31 |  |  | Withdrawn by Customer on September 14, 2010. | BPA’s Goldendale-Chenoweth Transmission Line at 115 kV | WITHDRAWN | WA | Klickitat | GI | 2011-12-31 |  | 202 | 202 | Energy | Wind Turbine | Wind Turbine | 202 | [6 empty] | 202 |  |  | . | [5 empty] | FALSE
G0398 | 2009-12-15 09:31 |  |  | Withdrawn by Customer on April 29, 2010. | BPA’s Transmission Facilities at or near Centerville, Wash. at 230 kV | WITHDRAWN | WA | Klickitat | GI | 2011-12-31 |  | 101 | 101 | Energy | Wind Turbine | Wind Turbine | 101 | [6 empty] | 101 |  |  | . | [5 empty] | FALSE
L0318 | 2009-12-14 13:39 | McNary Substation | Umatilla Electric Cooperative | Request withdrawn by customer 9/19/11 |  | WITHDRAWN | OR | Umatilla | LL | 2012-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0317 | 2009-12-14 13:30 | Decatur Island Tap | Orcas Power & Light Cooperative |  |  | ENERGIZED | WA | Skagit | LL | 2013-09-01 | 2018-08-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0396 | 2009-11-30 16:07 |  |  | Withdrawn on November 19, 2012 |  | WITHDRAWN | WA | Klickitat | GI | 2013-01-01 |  | 56 | 56 | NRIS | Wind Turbine | Wind Turbine | 56 | [6 empty] | 56 |  |  | . | [5 empty] | FALSE
G0394 | 2009-11-24 12:49 |  |  | FAS Study Issued 11/21/2011 |  | WITHDRAWN | OR | Deschutes | GI | 2012-03-01 | 2020-08-01 | 28 | 28 | NRIS | Reciprocating Engine | Biofuel | 28 | [6 empty] | 28 |  |  | . | [5 empty] | FALSE
G0395 | 2009-11-23 14:37 |  |  |  | Minidoka-Unity 138 kV line | WITHDRAWN | ID | Cassia | GI | 2010-10-15 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0393 | 2009-11-17 09:30 |  |  | Withdrawn on 4/8/2014 | 345 kV Rocky Reach - Maple Valley transmission line | WITHDRAWN | WA | Kittitas | GI | 2010-12-15 |  | 75 | 75 | NRIS | Photovoltaic | Solar | 75 | [6 empty] | 75 |  |  | . | [5 empty] | FALSE
G0392 | 2009-11-09 08:49 |  |  | Withdrawn on October 24, 2012 |  | WITHDRAWN | OR | Gilliam | GI | 2013-12-01 |  | 300 | 300 | NRIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0391 | 2009-11-03 16:44 |  |  | Withdrawn by Customer on February 25, 2014. | BPA’s Transmission Facilities on the Slatt-Buckley or Ashe-Marion transmission lines approx. 9 miles SW of Slatt | WITHDRAWN | OR | Gilliam | GI | 2013-03-01 |  | 425 | 425 | NRIS | Wind Turbine | Wind Turbine | 425 | [6 empty] | 425 |  |  | . | [5 empty] | FALSE
G0388 | 2009-11-02 18:45 |  |  | Deemed Withdrawn May 27, 2014 | BPA’s Idahome Substation | WITHDRAWN | ID | Cassia | GI | 2010-10-15 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0389 | 2009-11-02 12:02 |  |  | FAS issued 7/17/14 | New Substation near McNary 500 kV | WITHDRAWN | OR | Morrow | GI | 2013-11-01 | 2020-09-30 | 207 | 207 | NRIS | Wind Turbine | Wind Turbine | 207 | [6 empty] | 207 |  |  | . | [5 empty] | FALSE
G0390 | 2009-11-02 12:02 |  |  | FAS issued 7/17/14 | New Substation near McNary 500 kV | WITHDRAWN | OR | Morrow | GI | 2013-11-01 | 2020-09-30 | 207 | 207 | NRIS | Wind Turbine | Wind Turbine | 207 | [6 empty] | 207 |  |  | . | [5 empty] | FALSE
G0386 | 2009-10-28 08:47 |  |  | Withdrawn by Customer on June 1, 2011. | BPA’s Pomeroy Substation | WITHDRAWN | WA | Garfield | GI | 2011-12-01 |  | 20 | 20 | ERIS | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0387 | 2009-10-26 15:49 |  |  |  | Midstate Electric 24.9kV distribution system at Christmas Valley Substation | WITHDRAWN | OR | Lake | GI | 2009-12-31 | 2015-06-30 | 10 | 10 | ERIS | Photovoltaic | Solar | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
G0385 | 2009-10-08 18:07 |  |  | Integration; Studies completed |  | WITHDRAWN | OR | Lake | GI | 2011-12-01 | 2019-01-01 | 15 | 15 | ERIS | Photovoltaic | Solar | 15 | [6 empty] | 15 |  |  | . | [5 empty] | FALSE
G0383 | 2009-10-06 23:06 |  |  | Withdrawn on 7/30/2014 | Raymond 115 kV Substation | WITHDRAWN | WA | Pacific | GI | 2012-12-31 |  | 100 | 100 | NRIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0384 | 2009-10-06 09:06 |  |  | Withdrawn by Customer on July 12, 2010. | Bandon 115 kV Substation | WITHDRAWN | OR | Coos | GI | 2011-06-01 |  | 101 | 101 | NRIS | Wind Turbine | Wind Turbine | 101 | [6 empty] | 101 |  |  | . | [5 empty] | FALSE
G0381 | 2009-09-21 16:19 |  |  | Withdrawn by Customer on September 1, 2011. | Summer Lake 500 | WITHDRAWN | OR | Harney | GI | 2012-12-31 |  | 103 | 103 | ERIS | Wind Turbine | Wind Turbine | 103 | [6 empty] | 103 |  |  | . | [5 empty] | FALSE
G0382 | 2009-09-21 14:51 |  |  | Withdrawn by Customer on March 31, 2011. |  | WITHDRAWN | WA | Yakima & Benton | GI | 2012-10-30 |  | 100 | 100 | NRIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0380 | 2009-09-15 16:40 | Carty CCCT | Portland General Electric Company | Expected Synch date is 11/15/15 | 500 kV Slatt Substation | ENERGIZED | OR | Morrow | GI | 2014-05-01 | 2016-10-01 | 413 | 464 | NRIS | Gas Turbine | Natural Gas | 464 | [6 empty] | 464 |  |  | . | [5 empty] | FALSE
G0379 | 2009-09-02 15:30 |  |  | Integration, Study issued 5/12/2010 | Midstate Electric 24.9 kV distribution system | WITHDRAWN | OR | Lake | GI | 2010-07-30 | 2018-09-28 | 4 | 4 | ERIS | Photovoltaic | Solar | 4 | [6 empty] | 4 |  |  | . | [5 empty] | FALSE
L0316 | 2009-08-28 14:25 | McNary Substation | PacifiCorp |  | BPA's McNary Substation | ENERGIZED | OR | Umatilla | LL | 2011-10-01 | 2019-02-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0314 | 2009-08-27 09:25 | Merchant Txm Line-Townsend | Tonbridge Power Inc | Withdrawn by customer 6/4/15 | BPA Colstrip line at or near Townsend, MT | WITHDRAWN | MT | Jefferson | LL | 2013-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0315 | 2009-08-27 09:25 | Merchant Txm Line-Garrison | Tonbridge Power Inc | Withdrawn by customer 6/4/15 | BPA Colstrip 500kV Line at Garrison Substation | WITHDRAWN | MT | Powell | LL | 2013-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0378 | 2009-08-27 09:22 |  |  | Withdrawn by Customer on March 18, 2011 | BPA’s Substation at Shelton, Wash. | WITHDRAWN | WA | Mason | GI | 2012-12-31 |  | 65 | 65 | ERIS | Reciprocating Engine | Biofuel | 65 | [6 empty] | 65 |  |  | . | [5 empty] | FALSE
L0313 | 2009-08-20 11:34 | Bridge Substation | Raft River Rural Electric Cooperative, Inc. |  | BPA's Bridge Substation | WITHDRAWN | ID | Cassia | LL | 2010-11-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0311 | 2009-08-10 16:53 | Lancaster Substation | Avista Corporation |  | Lancaster 230 | ENERGIZED | ID | Kootenai | LL | 2012-09-01 | 2013-12-13 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0312 | 2009-08-10 10:48 | Bell-Boundary #1 230 kV | Inland Power & Light Company |  | Bell-Boundary #1 transmission line. | ENERGIZED | WA | Spokane | LL | 2011-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0376 | 2009-08-06 10:09 |  |  | Integration, Study Issued 3/12/10 | Midstate Electric 24.9 kV distribution system | WITHDRAWN | OR | Lake | GI | 2010-07-30 | 2018-09-28 | 4 | 4 | ERIS | Photovoltaic | Solar | 4 | [6 empty] | 4 |  |  | . | [5 empty] | FALSE
G0377 | 2009-08-06 10:09 | Outback | Outback Solar, LLC | Integration; on-line November 2012 | Midstate Electric 24.9 kV distribution system | ENERGIZED | OR | Lake | GI | 2010-07-30 | 2012-10-17 | 4 | 4 | ERIS | Photovoltaic | Solar | 4 | [6 empty] | 4 |  |  | . | [5 empty] | FALSE
L0310 | 2009-07-30 14:52 | Mount Adams Substation | Yakama Power |  | Feeder #2 out of BPA's Alfalfa Substation | ENERGIZED | WA | Yakima | LL | 2009-12-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0375 | 2009-07-14 13:18 |  |  | Withdrawn on September 17, 2012 | BPA’s proposed Wood Creek 230 kV Substation | WITHDRAWN | WA | Klickitat | GI | 2011-10-01 |  | 50 | 50 | ERIS | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0374 | 2009-06-30 09:53 | Horse Butte Wind | Horse Butte Wind I LLC | on-line August 2012 | 115 kV Goshen-Palisades transmission line | ENERGIZED | ID | Bonneville | GI | 2010-12-31 | 2019-07-15 | 100 | 100 | NRIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0373 | 2009-06-29 10:27 |  |  | Withdrawn on June 5, 2013 | 230 kV Libby-Haskill line | WITHDRAWN | MT | Flathead & Lincoln | GI | 2012-04-30 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0371 | 2009-06-03 14:15 |  |  | Withdrawn on May 4, 2010 | TBA | WITHDRAWN | WA | Grays Harbor | GI | 2012-12-31 |  | 65 | 65 | ERIS | Reciprocating Engine | Biofuel | 65 | [6 empty] | 65 |  |  | . | [5 empty] | FALSE
G0372 | 2009-06-03 14:15 |  |  | Withdrawn by Customer on June 14, 2010. | TBA | WITHDRAWN | ID | Latah | GI | 2012-12-31 |  | 65 | 65 | ERIS | Reciprocating Engine | Biofuel | 65 | [6 empty] | 65 |  |  | . | [5 empty] | FALSE
G0369 | 2009-06-02 12:55 |  |  | Withdrawn by Customer on September 8, 2011. |  | WITHDRAWN | WA | Benton | GI | 2012-12-31 |  | 65 | 65 | ERIS | Wind Turbine | Wind Turbine | 65 | [6 empty] | 65 |  |  | . | [5 empty] | FALSE
G0368 | 2009-06-01 12:04 |  |  | FAS Issued 4/27/2011 |  | STUDY COMPLETED | OR | Wasco | GI | 2013-08-01 | 2024-05-31 | 101 | 101 | NRIS | Photovoltaic | Solar | 101 | [6 empty] | 101 |  |  | . | [5 empty] | FALSE
G0367 | 2009-06-01 12:03 |  |  | 10/13/2020 Fuel Source changed to 100% solar. FAS Study Issued 4/27/2011 Facility Type Change 1/2/19: 142 MW wind/60 MW solar; |  | STUDY COMPLETED | OR | Wasco | GI | 2012-12-01 | 2024-04-30 | 202 | 202 | NRIS | Photovoltaic | Solar | 202 | [6 empty] | 202 |  |  | . |  |  |  |  | Available | FALSE
G0370 | 2009-06-01 10:39 | Young’s Creek Hydro Project | Public Utility District No. 1 of Snohomish County | on-line December 2010 | Sultan Substation | ENERGIZED | WA | Snohomish | GI | 2010-12-31 |  | 8 | 8 | ERIS | Hydro | Water | 8 | [6 empty] | 8 |  |  | . | [5 empty] | FALSE
G0366 | 2009-05-18 21:41 |  |  | FAS Study Issued 7/6/2011 | A 230 kV substation on BPA's Transmission system in Gilliam or Morrow Co. Ore. near or west of Boardman | STUDY COMPLETED | OR | Morrow | GI | 2014-11-01 | 2021-09-30 | 302 | 302 | NRIS | Wind Turbine | Wind Turbine | 302 | [6 empty] | 302 |  |  | . | [5 empty] | FALSE
G0365 | 2009-05-18 21:40 | Ella Wind 3 | Wheatridge Wind Energy, LLC | FAS Study Issued 11/1/2012. Reduced from 302 MW to 300 MW on 4/27/18 | A 230 kV substation on BPA's Transmission system in Gilliam or Morrow Co. Ore. near or west of Boardman | ENERGIZED | OR | Morrow | GI | 2013-11-01 | 2020-09-29 | 300 | 300 | NRIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0309 | 2009-05-18 14:01 | Transmission Reinforcement | Benton Rural Electric Association |  | Grandview-Red Mountain #1 115kV | ENERGIZED | WA | Yakima | LL | 2012-11-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0308 | 2009-05-18 10:43 | Transmission Reinforcement | Peninsula Light Company |  | Shelton-Kitsap 115kV Line | ENERGIZED | WA | Mason | LL | 2012-11-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0364 | 2009-04-24 13:41 |  |  | Withdrawn by Customer on August 7, 2009. | TBD | WITHDRAWN | WA | Kittitas | GI | 2011-12-31 |  | 50 | 50 | NRIS | Reciprocating Engine | Biofuel | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0363 | 2009-04-03 15:40 |  |  | Study Issued 11/1/2012 | BPA's Boardman 230 kV Substation | STUDY COMPLETED | OR | Gilliam | GI | 2012-11-01 | 2025-10-01 | 204 | 204 | NRIS | Wind Turbine | Wind Turbine | 204 | [6 empty] | 204 |  |  | . | [5 empty] | FALSE
G0362 | 2009-04-03 15:39 |  |  | FAS Study Issued 7/6/2011 | New Substation near McNary 500 kV | STUDY COMPLETED | OR | Gilliam | GI | 2012-11-01 | 2025-12-01 | 204 | 204 | NRIS | Wind Turbine | Wind Turbine | 204 | [6 empty] | 204 |  |  | . | [5 empty] | FALSE
G0361 | 2009-04-02 15:29 |  |  | FAS Study Issued 12/22/2010 |  | WITHDRAWN | OR | Umatilla | GI | 2011-10-01 | 2025-09-30 | 201 | 201 | NRIS | Wind Turbine | Wind Turbine | 201 | [6 empty] | 201 |  |  | . | [5 empty] | FALSE
G0360 | 2009-03-25 11:26 |  |  | Withdrawn on December 16, 2009. | Grays Harbor PUD’s 15 kV Distribution line | WITHDRAWN | WA | Grays Harbor | GI | 2009-07-01 |  | 6 | 6 | ERIS | Wind Turbine | Wind Turbine | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
G0359 | 2009-03-25 09:53 |  |  | Withdrawn by Customer on February 27, 2012. |  | WITHDRAWN | OR | Umatilla | GI | 2012-10-01 |  | 101 | 101 | NRIS | Wind Turbine | Wind Turbine | 101 | [6 empty] | 101 |  |  | . | [5 empty] | FALSE
G0358 | 2009-03-24 09:13 | Flathead LFGTE Project | Flathead Electric Cooperative, Inc. | on-line June 2009 | Flathead’s LaSalle Substation | ENERGIZED | MT | Flathead | GI | 2009-05-01 |  | 2 | 2 | ERIS | Steam Turbine | Biofuel | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0357 | 2009-03-18 20:10 |  |  | Withdrawn by Customer on October 4, 2010. | HEC 115 | WITHDRAWN | OR | Harney | GI | 2010-12-31 |  | 104 | 104 | NRIS | Wind Turbine | Wind Turbine | 104 | [6 empty] | 104 |  |  | . | [5 empty] | FALSE
L0307 | 2009-03-16 11:02 | Flathead Substation 230kV Bay | Flathead Electric Cooperative, Inc. |  | BPA's Flathead Substaion 230kV | ENERGIZED | MT | Flathead | LL | 2010-11-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0356 | 2009-03-09 15:49 |  |  | Withdrawn by Customer on June 26, 2012. |  | WITHDRAWN | MT | Wheatland | GI | 2015-12-31 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0355 | 2009-03-09 15:47 |  |  | Withdrawn by Customer on June 26, 2012. |  | WITHDRAWN | MT | Meagher | GI | 2014-12-31 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0354 | 2009-03-09 15:45 |  |  | Withdrawn by Customer on June 26, 2012. |  | WITHDRAWN | MT | Meagher | GI | 2014-12-31 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0353 | 2009-03-09 15:42 |  |  | Withdrawn by Customer on June 26, 2012. |  | WITHDRAWN | MT | Meagher | GI | 2013-12-31 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0306 | 2009-02-17 12:38 | Dayton Substation | Columbia Rural Electric Association |  | Walla Walla-Tucannon 115kV Line | ENERGIZED | WA | Walla Walla | LL | 2011-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0305 | 2009-02-06 09:32 | Westside Phase II | City of Idaho Falls |  | BPA's Westside Substation | WITHDRAWN | ID | Bonneville | LL | 2011-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0352 | 2009-01-26 16:09 |  |  | Withdrawn by Customer on April 12, 2010. 8/12/09: FES review meeting held; FES report available on request. ISIS completed. April 12, 2010: Following review of the ISIS report, customer withdrew the Request by letter. | Reedsport-Fairview 115 kV transmission line | WITHDRAWN | OR | Coos | GI | 2013-12-31 |  | 120 | 120 | ERIS | Gas Turbine | Natural Gas | 120 | [6 empty] | 120 |  |  | . | [5 empty] | FALSE
G0350 | 2008-12-02 09:34 |  |  | Withdrawn by Customer on January 12, 2009. | BPA's Harvalum 230 kV substation | WITHDRAWN | WA | Klickitat | GI | 2099-01-01 |  | 1200 | 1200 | NRIS | Energy Storage | Pumped-Storage Hydro | 1200 | [6 empty] | 1200 |  |  | . | [5 empty] | FALSE
G0351 | 2008-12-02 09:34 |  |  | Withdrawn November 28, 2012 | BPA's Rock Creek substation | WITHDRAWN | WA | Klickitat | GI | 2099-01-01 |  | 1200 | 1200 | NRIS | Energy Storage | Pumped-Storage Hydro | 1200 | [6 empty] | 1200 |  |  | . | [5 empty] | FALSE
G0349 | 2008-11-18 09:23 | Senaca Sawmill | Blachly-Lane Electric Cooperative | on-line | Blachly Lane Substation | ENERGIZED | OR | Blachly Lane | GI | 2010-10-01 | 2014-07-01 | 20 | 20 | N/A | Reciprocating Engine | Biofuel | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0348 | 2008-10-23 15:52 |  |  | Withdrawn on October 29, 2010 | Umatilla Electric Coop’s 12.47kV Line, Pole #3N 27E 138000 | WITHDRAWN | OR | Umatilla | GI | 2008-12-31 |  | 2 | 2 | Energy | Wind Turbine | Wind Turbine | 2 | [6 empty] | 2 |  |  | . | [5 empty] | FALSE
G0347 | 2008-09-24 19:43 |  |  | Withdrawn on Febuary 20, 2009 | HEC's Harney-Fields 115kV line | WITHDRAWN | OR | Harney | GI | 2013-12-31 |  | 76 | 76 | NRIS | Wind Turbine | Wind Turbine | 76 | [6 empty] | 76 |  |  | . | [5 empty] | FALSE
G0346 | 2008-09-24 19:42 |  |  | Withdrawn on February 20, 2009 | At a point on Harney Electric Cooperative's Harney-Fields 115 kV transmission line. Withdrawn by Customer on February 20, 2009. | WITHDRAWN | OR | Harney | GI | 2013-12-31 |  | 76 | 76 | NRIS | Wind Turbine | Wind Turbine | 76 | [6 empty] | 76 |  |  | . | [5 empty] | FALSE
L0304 | 2008-09-24 11:14 | Saddleback Mountain Interconnection | Public Utility District No. 1 of Klickitat County |  | BPA's Midway-North Bonneville 230kV Line | WITHDRAWN | WA | Skamania | LL | 2010-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0345 | 2008-09-16 16:50 |  |  | FAS Study Issued 8/8/2010 |  | STUDY COMPLETED | OR | Wasco | GI | 2010-08-30 | 2027-01-01 | 201 | 201 | ERIS | Wind Turbine | Wind Turbine | 201 | [6 empty] | 201 |  |  | . | [5 empty] | FALSE
G0344 | 2008-09-04 16:35 |  |  | Re-study underway | Ashe-Marion 500kV #1 | STUDY COMPLETED | OR | Gilliam | GI | 2024-04-30 | 2027-10-01 | 488 | 488 | NRIS | Wind Turbine | Wind Turbine | 488 | [6 empty] | 488 |  |  | . |  |  |  |  | Available | FALSE
L0302 | 2008-09-03 12:15 | Tower Road Substation | Umatilla Electric Cooperative |  | BPA's Boardman-Alkali 115kV Line | WITHDRAWN | OR | Morrow | LL | 2010-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0303 | 2008-09-03 12:15 | Port of Morrow Substation | Umatilla Electric Cooperative | Request withdrawn by customer 9/19/11 | BPA's Boardman-Tower Rd 115kV Line | WITHDRAWN | OR | Morrow | LL | 2010-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0343 | 2008-09-02 09:33 |  |  | Withdrawn by Customer on June 9, 2009. | BPA's Big Eddy-Maupin 230 kV transmission line | WITHDRAWN | OR | Wasco | GI | 2010-12-01 |  | 107 | 107 | NRIS | Wind Turbine | Wind Turbine | 107 | [6 empty] | 107 |  |  | . | [5 empty] | FALSE
G0341 | 2008-08-27 16:17 |  |  | Deemed Withdrawn on April 5, 2011. Customer did not meet terms of LGIP, Section 3.3.5. | Boardman - Ione 69 kV line | WITHDRAWN | OR | Morrow | GI | 2012-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0342 | 2008-08-27 09:17 |  |  | Re-study underway |  | WITHDRAWN | OR | Gilliam | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0340 | 2008-08-07 19:42 |  |  | Withdrawn on July 30, 2013 |  | WITHDRAWN | WA | Grant | GI | 2011-12-31 |  | 185 | 185 | NRIS | Wind Turbine | Wind Turbine | 185 | [6 empty] | 185 |  |  | . | [5 empty] | FALSE
G0338 | 2008-07-28 16:05 |  |  | Withdrawn on January 24, 2013 | Walla Walla-Pendleton 69 kV line | WITHDRAWN | OR | Umatilla | GI | 2013-12-31 |  | 100 | 100 | NRIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0339 | 2008-07-28 16:05 |  |  | Withdrawn by Customer on August 31, 2009. | Walla Walla-Pendleton 69 kV line | WITHDRAWN | OR | Umatilla | GI | 2013-12-31 |  | 152 | 152 | NRIS | Wind Turbine | Wind Turbine | 152 | [6 empty] | 152 |  |  | . | [5 empty] | FALSE
G0337 | 2008-07-11 14:49 |  |  | Withdrawn by Customer on June 10, 2009. | New substation on BPA's 500 kV McNary-John Day 500 kV line | WITHDRAWN | WA | Klickitat & Yakima | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0336 | 2008-07-11 14:48 |  |  | Withdrawn by Customer on June 10, 2009. | New substation on BPA's 500 kV McNary-John Day 500 kV line | WITHDRAWN | WA | Klickitat & Yakima | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0301 | 2008-07-03 09:31 | Spearfish Substation Expansion | Public Utility District No. 1 of Klickitat County |  | BPA's Chenoweth-Goldendale 115kV Line | WITHDRAWN | OR | Wasco | LL | 2010-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0300 | 2008-06-20 11:28 | Pinecreek Substation | Okanogan County Public Utility District No. 1 |  | Omak-Tonasket #1 & #2 Txm Line, Twr 11/1 | ENERGIZED | WA | Okanogan | LL | 2009-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0299 | 2008-06-18 11:00 | Skamania PUD Transmission Reinforcement | Public Utility District #1 of Skamania County |  | BPA's Midway-N.Bonneville 230kV line in the vicinity of Underwood Substation. | WITHDRAWN | OR | Sherman | LL | 2010-10-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0334 | 2008-05-30 16:18 |  |  | Re-study underway | New Substation near Slatt 500 kV. | WITHDRAWN | OR | Gilliam | GI | 2010-10-01 | 2025-01-01 | 300 | 300 | NRIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0333 | 2008-05-20 16:08 |  |  | Withdrawn by Customer on March 19, 2009. | Big Eddy-Maupin 230 kV line | WITHDRAWN | OR | Wasco | GI | 2010-12-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0332 | 2008-05-19 15:41 | King Estate Solar Generator Project | Lane Electric Cooperative, Inc. | on-line November 2009 | Integrating in Lane Electric Coop's system (Fox Hollow Substation) | ENERGIZED | OR | Lane | GI | 2008-12-01 |  | 1 | 1 | NRIS | Photovoltaic | Solar | 1 | [6 empty] | 1 |  |  | . | [5 empty] | FALSE
L0298 | 2008-05-14 12:50 | NorthernLights Transmission Project | NorthernLights Transmission, Inc. |  | BPA's Buckley Substation | WITHDRAWN | OR | Sherman | LL | 2014-05-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0328 | 2008-05-12 23:28 |  |  | Withdrawn on July 12, 2013 | Central Ferry Substation | WITHDRAWN | WA | Garfield | GI | 2012-07-01 |  | 252 | 252 | ERIS | Wind Turbine | Wind Turbine | 252 | [6 empty] | 252 |  |  | . | [5 empty] | FALSE
G0329 | 2008-05-12 23:28 |  |  | Withdrawn on July 12, 2013 | Central Ferry Substation | WITHDRAWN | WA | Garfield | GI | 2013-08-01 |  | 252 | 252 | ERIS | Wind Turbine | Wind Turbine | 252 | [6 empty] | 252 |  |  | . | [5 empty] | FALSE
G0330 | 2008-05-12 23:28 |  |  | Withdrawn by Customer on August 1, 2011. | Central Ferry Substation | WITHDRAWN | WA | Garfield | GI | 2014-10-01 |  | 116 | 116 | ERIS | Wind Turbine | Wind Turbine | 116 | [6 empty] | 116 |  |  | . | [5 empty] | FALSE
G0327 | 2008-05-09 13:30 | Columbia Ridge Landfill | WM Renewable Energy, LLC | on-line December 2009 | At or near Alkali Substation | ENERGIZED | OR | Gilliam | GI | 2009-01-01 |  | 7 | 7 | Energy | Reciprocating Engine | Biofuel | 7 | [6 empty] | 7 |  |  | . |  |  |  |  | Available | FALSE
G0326 | 2008-05-05 16:29 |  |  | FAS Study Issued 8/17/2010 | At BPA's 138 kV Bridge Substation | WITHDRAWN | UT | Box Elder | GI | 2010-06-30 | 2020-06-01 | 42 | 42 | NRIS | Wind Turbine | Wind Turbine | 42 | [6 empty] | 42 |  |  | . | [5 empty] | FALSE
G0325 | 2008-04-29 12:25 |  |  | Withdrawn by Customer on March 5, 2009. | A point on BPA’s Midway-Rocky Ford 230kV line | WITHDRAWN | WA | Grant | GI | 2011-12-31 |  | 130 | 130 | NRIS | Wind Turbine | Wind Turbine | 130 | [6 empty] | 130 |  |  | . | [5 empty] | FALSE
L0297 | 2008-04-24 10:00 | Data Center | Umatilla Electric Cooperative |  |  | WITHDRAWN | OR | Umatilla | LL | 2010-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0296 | 2008-04-18 11:00 | Sunriver | Midstate Electric Cooperative, Inc. |  | BPA LaPine-Pilot Butte 230kV Line | ENERGIZED | OR | Deschutes | LL | 2012-09-01 | 2021-08-19 | 88.7 | 88.7 |  | Other | Other | 88.7 | [6 empty] | 88.7 |  |  | . | [5 empty] | FALSE
L0295 | 2008-04-17 15:57 | St.Johns-Allston Interconnection | Columbia River People's Utility District |  | St.Johns-Allston 115kV Line | ENERGIZED | OR | Columbia | LL | 2012-10-01 |  |  |  |  | Other | Other | 6 | [6 empty] | 6 |  |  | . | [5 empty] | FALSE
L0294 | 2008-04-14 09:34 | New Commercial/Industrial Substation | Blachly-Lane Electric Cooperative | All studies for this request are complete (3/30/10). | Between BPA Parker and Junction City Substations | ENERGIZED | OR | Lane | LL | 2017-09-01 | 2019-07-18 | [12 empty] | 0 |  |  | . | [5 empty] | FALSE
G0324 | 2008-04-08 13:55 |  |  | Withdrawn on February 26, 2010 | BPA's Tucannon River-North Lewiston No. 1 115 kV transmission line | WITHDRAWN | WA | Garfield | GI | 2010-12-01 |  | 300 | 300 | NRIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0323 | 2008-04-08 13:53 |  |  | Withdrawn by customer email on 12/28/2015. FAS Study Issued 9/20/2009 | New Substation near John Day 500 kV Substation | WITHDRAWN | OR | Sherman | GI | 2011-12-01 |  | 300 | 300 | NRIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0293 | 2008-04-08 08:19 | Vantage Substation | PacifiCorp |  | BPA Vantage Substation | ENERGIZED | WA | Grant | LL | 2009-09-01 | 2020-10-01 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0322 | 2008-04-07 08:55 |  |  | Withdrawn on June 3, 2008 | At a point in BPA's Harvalum Substation, at 230 kV | WITHDRAWN | WA | Klickitat | GI | 2009-12-31 |  | 51 | 51 | ERIS | Wind Turbine | Wind Turbine | 51 | [6 empty] | 51 |  |  | . | [5 empty] | FALSE
L0292 | 2008-04-01 09:10 | Bakers Corner Tap | Public Utility District No. 1 of Cowlitz County | Studies complete | Lexington-Longview 115 kV Line | ENERGIZED | WA | Cowlitz | LL | 2009-09-01 | 2012-12-31 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0321 | 2008-03-27 15:19 |  |  | Withdrawn by Customer on March 5, 2010. On February 20, 2009, Customer was notified that the FES Report would be delayed until March 27, 2009, to allow more detailed study of line routings and constraints for a preferred plan of service. | Satsop 230 kV | WITHDRAWN | WA | Grays Harbor | GI | 2010-06-01 |  | 290 | 295 | NRIS | Gas Turbine | Natural Gas | 290 | [6 empty] | 290 |  |  | . | [5 empty] | FALSE
L0291 | 2008-03-27 14:59 | Chenowith Tap | Northern Wasco County People's Utility District |  | Big Eddy - Chenowith 115 kV | WITHDRAWN | OR | Wasco | LL | 2009-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0318 | 2008-03-27 14:38 |  |  | Withdrawn by Customer on March 8, 2012. | Goldendale 115 kV | WITHDRAWN | WA | Klickitat | GI | 2010-07-01 |  | 20 | 20 | Energy | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0319 | 2008-03-27 14:38 |  |  | Withdrawn by Customer on March 8, 2012. | Goldendale 115 kV | WITHDRAWN | WA | Klickitat | GI | 2010-07-01 |  | 20 | 20 | Energy | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0320 | 2008-03-27 14:38 |  |  | Withdrawn by Customer on March 8, 2012. | Goldendale 115 kV | WITHDRAWN | WA | Klickitat | GI | 2010-07-01 |  | 20 | 20 | Energy | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0290 | 2008-03-27 12:58 | Ethanol Facility | Public Utility District No. 1 of Franklin County |  | Franklin Substation | WITHDRAWN | WA | Franklin | LL | 2009-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0335 | 2008-03-20 09:20 |  |  | on-line October 2011 | Roosevelt 115 kV | DECOMMISSIONED | WA | Klickitat | GI | 2010-09-01 |  | 17 | 17 | Energy | Reciprocating Engine | Biofuel | 17 | [6 empty] | 17 |  |  | . | [5 empty] | FALSE
G0317 | 2008-03-17 12:05 | Libby 6th Unit | BPA Power Services | Withdrawn by Customer on April 9, 2010. | Existing T-3 at the Libby Project | WITHDRAWN | MT | Lincoln | GI | 2010-09-07 |  | 120 | 120 | NRIS | Hydro | Water | 120 | [6 empty] | 120 |  |  | . | [5 empty] | FALSE
L0289 | 2008-03-17 09:41 | Gardiner-Reedsport | Central Lincoln People's Utility District | Studies complete | Gardiner Substation | STUDY COMPLETED | OR | Douglas | LL | 2009-09-01 | 2018-10-01 | 7.6 | 7.6 |  | Other | Other | 7.6 | [6 empty] | 7.6 |  |  | . | [5 empty] | FALSE
L0288 | 2008-03-14 13:00 | Industrial Park | Columbia Rural Electric Association |  | Franklin-Walla Walla 115 kV/Sacajawea Sub | WITHDRAWN | WA | Franklin | LL | 2009-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0316 | 2008-03-12 10:11 |  |  | Withdrawn February 9, 2009 |  | WITHDRAWN | OR | Yamhill | GI | 2011-07-01 |  | 100 | 100 | ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0315 | 2008-03-03 11:25 |  |  | Withdrawn February 9, 2009 | 115 kV line at Pe Ell Substation | WITHDRAWN | WA | Lewis | GI | 2012-12-01 |  | 150 | 150 | NRIS | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G0314 | 2008-02-29 16:21 |  |  | Withdrawn by customer instruction on December 12, 2014. | Noxon-Hot Springs 230 kV line near Thompson Falls, MT | WITHDRAWN | MT | Sanders | GI | 2010-07-01 |  | 95 | 95 | NRIS | Hydro | Water | 95 | [6 empty] | 95 |  |  | . | [5 empty] | FALSE
G0313 | 2008-02-07 14:57 |  |  | FAS Study Issued 11/1/2010 Integration project. | South Elma Substation | WITHDRAWN | WA | Lewis | GI | 2011-12-01 | 2020-12-31 | 128 | 128 | NRIS | Wind Turbine | Wind Turbine | 128 | [6 empty] | 128 |  |  | . | [5 empty] | FALSE
L0286 | 2008-02-05 11:00 | Mt. Si | Puget Sound Energy, Inc. | Project name formerly Tanner Tap | Tanner 115 kV Tap | WITHDRAWN | WA | King | LL | 2009-01-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0287 | 2008-02-05 11:00 | Novelty Substation | Puget Sound Energy, Inc. |  | Monroe-Sammamish 230 kV Line | WITHDRAWN | WA | King | LL | 2009-09-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0309 | 2008-01-29 18:33 |  |  | Withdrawn on July 30, 2013 | New substation on BPA's 500 kV McNary-John Day line | WITHDRAWN | WA | Klickitat & Yakima | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0310 | 2008-01-29 18:33 |  |  | Withdrawn on July 30, 2013 | New substation on BPA's 500 kV McNary-John Day line near Alderdale, Washington | WITHDRAWN | WA | Klickitat & Yakima | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0311 | 2008-01-29 10:33 |  |  | Withdrawn on July 30, 2013 | New substation on BPA's 500 kV McNary-John Day line near Roosevelt and Alderdale, Washington | WITHDRAWN | OR | Klickitat & Yakima | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0312 | 2008-01-29 10:33 |  |  | Withdrawn on July 30, 2013 | New substation on BPA's 500 kV McNary-John Day line near Alderdale, Washington | WITHDRAWN | WA | Klickitat & Yakima | GI | 2011-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0308 | 2008-01-28 18:52 |  |  |  |  | WITHDRAWN | OR | Gilliam | GI | 2012-10-01 |  | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0307 | 2008-01-28 10:52 |  |  |  |  | WITHDRAWN | OR | Gilliam | GI | 2011-10-01 |  | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0306 | 2008-01-24 16:39 |  |  | Withdrawn by Customer on October 6, 2008. | BPA's Harney/Redmond transmission line near Harney. | WITHDRAWN | OR | Harney Lake Crook Deschutes | GI | 2009-12-01 |  | 600 | 600 | NRIS | Wind Turbine | Wind Turbine | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G0305 | 2008-01-18 09:58 |  |  | Withdrawn on September 2, 2010 | BPA's 230 kV LaGrande Substation | WITHDRAWN | OR | Union | GI | 2010-01-15 |  | 200 | 200 | ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0285 | 2008-01-15 11:12 | McNary Substation | PacifiCorp |  | McNary Substation | WITHDRAWN | OR | Umatilla | LL | 2010-12-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0304 | 2008-01-09 12:09 |  |  | Withdrawn by Customer on December 15, 2009. | At a point on BPA's Harney/Redmond transmission line close to Harney Electric Cooperative's interconnection to BPA | WITHDRAWN | OR | Harney | GI | 2009-12-01 |  | 416 | 416 | NRIS | Wind Turbine | Wind Turbine | 416 | [6 empty] | 416 |  |  | . | [5 empty] | FALSE
L0284 | 2008-01-09 09:07 | Merchant Transmission Line | Green Pacific Highway, LLC |  | Merchant Transmission Line | WITHDRAWN | OR | Columbia | LL | 2009-07-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0301 | 2008-01-08 16:00 |  |  | Withdrawn by Customer on December 13, 2012. |  | WITHDRAWN | OR | Harney | GI | 2009-12-01 | 2014-12-31 | 104 | 104 | NRIS | Wind Turbine | Wind Turbine | 104 | [6 empty] | 104 |  |  | . | [5 empty] | FALSE
G0302 | 2008-01-08 16:00 |  |  | Withdrawn by Customer on October 4, 2010. | BPA's Harney/Redmond transmission line near Harney | WITHDRAWN | OR | Harney | GI | 2010-12-01 |  | 104 | 104 | NRIS | Wind Turbine | Wind Turbine | 104 | [6 empty] | 104 |  |  | . | [5 empty] | FALSE
G0303 | 2008-01-08 16:00 |  |  | Withdrawn by Customer on October 4, 2010. | At a point on BPA's Harney/Redmond transmission line close to Harney Electric Cooperative's interconnection to BPA | WITHDRAWN | OR | Harney | GI | 2011-12-01 |  | 104 | 104 | NRIS | Wind Turbine | Wind Turbine | 104 | [6 empty] | 104 |  |  | . | [5 empty] | FALSE
G0300 | 2007-12-18 08:47 |  |  | FAS Study Issued 7/1/2009 | At a point on BPA's Brasada-Harney 115 kV transmission line | WITHDRAWN | OR | Crook | GI | 2010-10-30 |  | 104 | 104 | ERIS | Wind Turbine | Wind Turbine | 104 | [6 empty] | 104 |  |  | . | [5 empty] | FALSE
L0283 | 2007-12-17 10:50 | Kalispell Substation | Flathead Electric Cooperative, Inc. |  | BPA Kalispell Substation 115kV Bay #9 | WITHDRAWN | MT | Flathead | LL | 2009-06-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0331 | 2007-12-17 09:30 |  |  | Withdrawn on August 11, 2016: customer non-responsive. FAS Study Issued March 29, 2008 | Harney-Brasada 115 kV line near Hampton Substation | WITHDRAWN | OR | Harney | GI | 2009-07-01 | 2025-01-01 | 8 | 8 | ERIS | Wind Turbine | Wind Turbine | 8 | [6 empty] | 8 |  |  | . | [5 empty] | FALSE
G0299 | 2007-11-19 17:10 |  |  | Withdrawn by Customer on March 11, 2008 | BPA’s Lower Granite/Little Goose 500 kV line | WITHDRAWN | WA | Columbia | GI | 2010-12-15 |  | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0298 | 2007-11-19 17:03 |  |  | Withdrawn by Customer on March 11, 2008 | Little Goose 500 kV Substation | WITHDRAWN | WA | Columbia | GI | 2009-12-15 |  | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0297 | 2007-11-01 11:46 | Biglow Canyon Wind Farm Addition | Portland General Electric Company | on-line May 2010 (combined with Phase 3 of G099 for 125 MW) |  | ENERGIZED | OR | Sherman | GI | 2009-10-01 |  | 50 | 50 | ERIS | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0296 | 2007-10-29 08:45 |  |  | Withdrawn on November 17, 2008 | BPA's McNary-Roundup 230 kV line | WITHDRAWN | OR | Morrow | GI | 2012-10-01 |  | 300 | 300 | NRIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0295 | 2007-10-25 23:06 |  |  | LGIA in Progress | Central Ferry Substation | IA EXECUTED | WA | Columbia & Garfield | GI | 2011-12-31 | 2027-01-01 | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0294 | 2007-10-25 16:06 |  |  | LGIA in progress | Central Ferry Substation | IA EXECUTED | WA | Columbia & Garfield | GI | 2011-12-31 | 2027-01-01 | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0293 | 2007-10-24 13:50 |  |  | Withdrawn on July 31, 2013 | BPA's LaGrande 230 kV Substation | WITHDRAWN | OR | Union | GI | 2015-10-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0292 | 2007-10-17 09:30 |  |  | Withdrawn on November 23, 2009 | Prosser 115 kV Substation | WITHDRAWN | WA | Benton | GI | 2011-07-01 |  | 180 | 180 | ERIS | Wind Turbine | Wind Turbine | 180 | [6 empty] | 180 |  |  | . | [5 empty] | FALSE
G0291 | 2007-10-15 09:48 | Shepherds Flat Wind Farm addition | Shepherds Flat Wind, LLC | on-line June 2012 | Slatt 500 kV Substation | ENERGIZED | OR | Gilliam | GI | 2009-07-01 |  | 96 | 96 | NRIS | Wind Turbine | Wind Turbine | 96 | [6 empty] | 96 |  |  | . | [5 empty] | FALSE
L0282 | 2007-09-26 11:29 | Cowlitz Substation | Tacoma Power | BPA's S.Tacoma 230kV line to be disconnected from Cowlitz and connect directly to Tacoma's Southwest #4 line. | Reterminate BPA's South Tacoma-Cowlitz 230kV Line | WITHDRAWN | WA | Pierce | LL | 2010-01-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0281 | 2007-09-14 16:04 | Grant Rocky Ford | Public Utility District No. 2 of Grant County, Washington |  |  | ENERGIZED | WA | Douglas | LL | 2010-01-01 | 2014-02-06 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0290 | 2007-09-06 09:19 |  |  | Withdrawn by Customer on November 17, 2008 | Wasco Co., Oregon | WITHDRAWN | OR | Wasco | GI | 2011-10-01 |  | 75 | 75 | NRIS | Wind Turbine | Wind Turbine | 75 | [6 empty] | 75 |  |  | . | [5 empty] | FALSE
G0289 | 2007-08-29 02:08 |  |  | FAS Study Issued 7/2/2010 | Satsop 230 kV Substation | WITHDRAWN | WA | Grays Harbor | GI | 2010-12-31 | 2015-03-01 | 628 | 659 | NRIS | Gas Turbine | Natural Gas | 628 | [6 empty] | 628 |  |  | . | [5 empty] | FALSE
G0288 | 2007-08-24 09:09 |  |  | Withdrawn on December 12, 2011 | One mile from Naselle 115 kV Substation | WITHDRAWN | WA | Pacific | GI | 2011-07-01 |  | 82 | 82 | ERIS | Wind Turbine | Wind Turbine | 82 | [6 empty] | 82 |  |  | . | [5 empty] | FALSE
L0279 | 2007-08-23 09:24 | Victor Transformer | Fall River Rural Electric Cooperative, Inc. |  | Victor Substation | ENERGIZED | ID | Teton | LL | 2010-01-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0278 | 2007-08-22 10:05 | North Loop | City of Idaho Falls |  | Westside Substation | ENERGIZED | ID | Bonneville | LL | 2010-01-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0287 | 2007-08-17 08:59 |  |  | Withdrawn by Customer on July 8, 2008. | Midway-N. Bonneville 230 kV line north of Goldendale, Wa. | WITHDRAWN | WA | Klickitat | GI | 2010-09-01 |  | 200 | 200 | ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0284 | 2007-08-13 10:51 | Lower Snake Phase 1 | Puget Sound Energy, Inc. | Phase I for 250 MW; on-line January 2010 | Central Ferry Substation | ENERGIZED | WA | Columbia | GI | 2011-12-31 | 2012-02-01 | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0285 | 2007-08-13 10:51 | Lower Snake Phase 1 | Puget Sound Energy, Inc. | Phase I for 93 MW; on-line January 2012 | Central Ferry Substation | ENERGIZED | WA | Columbia & Garfield | GI | 2011-12-31 | 2026-08-01 | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0286 | 2007-08-13 10:51 | Tucannon River Wind Farm | Portland General Electric Company | Phase 2 for 267 MW acquired by PGE; on-line scheduled for December 2014. | Central Ferry Substation | ENERGIZED | WA | Columbia & Garfield | GI | 2011-12-31 | 2014-12-02 | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0283 | 2007-08-10 10:25 |  |  | Withdrawn by Customer on June 24, 2011. | DeMoss Springs | WITHDRAWN | OR | Sherman | GI | 2009-04-01 |  | 40 | 40 | ERIS | Wind Turbine | Wind Turbine | 40 | [6 empty] | 40 |  |  | . | [5 empty] | FALSE
G0282 | 2007-08-10 09:11 |  |  | Withdrawn on November 29, 2012 | Chandler 115 kV line | WITHDRAWN | WA | Benton | GI | 2011-10-01 |  | 100 | 100 | NRIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0277 | 2007-08-03 10:05 | Oceanside | Tillamook People's Utility District |  | Tillamook Substation | ENERGIZED | OR | Tillamook | LL | 2010-01-01 | 2025-06-30 | 10 | 10 |  | Other | Other | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0276 | 2007-07-25 09:28 | Network Connection, 230 kV loop line | Puget Sound Energy, Inc. | Energized 6/11/14 | St Clair or Spurgeon Creek Substation | ENERGIZED | WA | Thurston | LL | 2008-08-01 | 2014-06-11 |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0279 | 2007-07-17 14:15 |  |  |  | To be determined | WITHDRAWN | OR | Sherman | GI | 2010-08-01 |  | 105 | 105 | NRIS | Wind Turbine | Wind Turbine | 105 | [6 empty] | 105 |  |  | . | [5 empty] | FALSE
G0280 | 2007-07-17 14:15 |  |  |  |  | WITHDRAWN | OR | Sherman | GI | 2011-07-01 |  | 242 | 242 | NRIS | Wind Turbine | Wind Turbine | 242 | [6 empty] | 242 |  |  | . | [5 empty] | FALSE
G0281 | 2007-07-17 09:00 |  |  | Withdrawn by Customer on February 12, 2008. | Lower Monumental-McNary 500kV line in vicinity of Wallula, WA. | WITHDRAWN | WA | Walla Walla | GI | 2013-06-01 |  | 760 | 760 | NRIS | Gas Turbine | Natural Gas | 760 | [6 empty] | 760 |  |  | . | [5 empty] | FALSE
G0278 | 2007-07-12 08:56 |  |  | Withdrawn by Customer on March 5, 2009. | Midway-North Bonneville 230kV Line | WITHDRAWN | WA | Klickitat | GI | 2009-12-01 |  | 75 | 75 | ERIS | Wind Turbine | Wind Turbine | 75 | [6 empty] | 75 |  |  | . | [5 empty] | FALSE
G0277 | 2007-07-10 16:25 |  |  | Withdrawn on July 30, 2013 | to be determined | WITHDRAWN | OR | Klickitat | GI | 2010-12-31 |  | 250 | 250 | ERIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G0276 | 2007-07-06 09:55 |  |  | Withdrawn on January 27, 2009 | Grand Coulee-Columbia 230kV Line | WITHDRAWN | WA | Douglas | GI | 2010-12-01 |  | 300 | 300 | NRIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0275 | 2007-07-06 07:05 | Merchant Transmission Line | Green Pacific Highway, LLC |  | Allston Substation | WITHDRAWN | OR | Columbia | LL | 2009-07-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0275 | 2007-07-03 16:44 |  |  | Withdrawn on January 7, 2013 | 20Miles West of Milton-Freewater | WITHDRAWN | OR | Umatilla | GI | 2009-11-01 |  | 100 | 100 | NRIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0274 | 2007-06-29 10:00 | Hopkins Ridge Addition | Puget Sound Energy, Inc. | on-line August 2008 | Tucannon River Switching Station | ENERGIZED | WA | Columbia | GI | 2008-08-01 |  | 7 | 7 | NRIS | Wind Turbine | Wind Turbine | 7 | [6 empty] | 7 |  |  | . | [5 empty] | FALSE
G0273 | 2007-06-14 09:36 |  |  | Witrhdrawn by Customer on July 18, 2008. | Vantage Substation | WITHDRAWN | WA | Kittitas | GI | 2008-09-01 |  | 104 | 104 | ERIS | Wind Turbine | Wind Turbine | 104 | [6 empty] | 104 |  |  | . | [5 empty] | FALSE
L0273 | 2007-05-25 09:16 | Beverly Park Expansion | Public Utility District No. 1 of Snohomish County |  | Snohomish Substation | WITHDRAWN | WA | Snohomish | LL | 2008-10-01 |  | 178 | 178 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0272 | 2007-05-17 09:20 | Wallula 500kV | Public Utility District No. 1 of Douglas County |  | BPA's Columbia Substation | WITHDRAWN | WA | Douglas | LL | 2008-06-01 |  | 5 | 5 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0271 | 2007-05-04 10:00 |  |  | Withdrawn on May 30, 2008 | BPA's Wautoma 230 kV Line | WITHDRAWN | WA | Yakima | GI | 2009-09-01 |  | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0272 | 2007-05-04 10:00 |  |  | Withdrawn on May 30, 2008. | BPA's Wautoma 230kV Line | WITHDRAWN | WA | Yakima | GI | 2008-08-01 |  | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
L0271 | 2007-03-29 11:26 | Brothers Tap Upgrade | Midstate Electric Cooperative, Inc. |  | Christmas Valley 115 kV | WITHDRAWN | OR | Lake | LL | 2008-05-01 |  | 14 | 14 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0263 | 2007-03-08 17:03 |  |  | Withdrawn August 28, 2007 | N/A | WITHDRAWN | OR | Sherman | GI | 2009-11-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0262 | 2007-03-07 10:21 |  |  | Withdrawn September 10, 2007 | Big Eddy-DeMoss 115 kV Line | WITHDRAWN | OR | Wasco | GI | 2007-12-01 |  | 3 | 3 | Energy | Wind Turbine | Wind Turbine | 3 | [6 empty] | 3 |  |  | . | [5 empty] | FALSE
G0261 | 2007-02-22 17:06 |  |  | Withdrawn November 8, 2007 | Ashe-Marion 500 kV | WITHDRAWN | WA | Klickitat | GI | 2010-09-01 |  | 1200 | 1200 | ERIS | Wind Turbine | Wind Turbine | 1200 | [6 empty] | 1200 |  |  | . | [5 empty] | FALSE
L0259 | 2007-02-06 09:19 | Wahkiakum PUD 115kV Tap | Public Utility District No. 1 of Wahkiakum County | Studies complete | Naselle Tap to Allston-Astoria #1 115kV | ENERGIZED | WA | Wahkiakum | LL | 2009-02-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0258 | 2007-02-02 09:56 |  |  | Withdrawn on September 6, 2013. | Longview Substation | WITHDRAWN | WA | Cowlitz | GI | 2012-01-01 |  | 320 | 375 | ERIS | Gas Turbine | Natural Gas | 320 | [6 empty] | 320 |  |  | . | [5 empty] | FALSE
G0255 | 2007-01-25 12:26 | Willow Creek and Horn Butte | Invenergy Wind Development LLC | LGIA executed for Phase 1, 72 MW; on-line November 2008. | Boardman-Alkali 115 kV Line | ENERGIZED | OR | Gilliam | GI | 2008-05-01 |  | 72 | 72 | ERIS | Wind Turbine | Wind Turbine | 72 | [6 empty] | 72 |  |  | . | [5 empty] | FALSE
L0260 | 2007-01-18 16:49 | Midstate LaPine Addition | Midstate Electric Cooperative, Inc. |  | LaPine Substation | ENERGIZED | OR | Deschutes | LL | 2008-12-01 |  | 163 | 163 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0257 | 2007-01-18 08:28 | West Wendover | Wells Rural Electric Company |  | West Wendover POD | ENERGIZED | NV | West Wendover | LL | 2008-01-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0256 | 2007-01-12 13:33 | Targhee Substation | Fall River Rural Electric Cooperative, Inc. |  | Targhee Substation | ENERGIZED | ID | Teton | LL | 2008-01-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0252 | 2006-12-19 08:54 |  |  | Withdrawn by Customer on February 29, 2008. | Wautoma 500 kV Substation | WITHDRAWN | WA | Yakima | GI | 2008-09-01 |  | 350 | 350 | ERIS | Wind Turbine | Wind Turbine | 350 | [6 empty] | 350 |  |  | . | [5 empty] | FALSE
G0253 | 2006-12-19 08:54 |  |  | Withdrawn on July 18, 2007 | Horse Heaven Substation 115 kV | WITHDRAWN | WA | Klickitat | GI | 2008-09-01 |  | 100 | 100 | ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0251 | 2006-12-14 09:15 |  |  | FAS Study Issued 5/27/2009. Withdrawn by customer letter dated 11/6/14 received by email 11/7/14. | New substation on BPA's 500 kV McNary-John Day line | WITHDRAWN | WA | Klickitat | GI | 2010-09-01 |  | 700 | 700 | ERIS | Wind Turbine | Wind Turbine | 700 | [6 empty] | 700 |  |  | . | [5 empty] | FALSE
L0250 | 2006-12-13 09:25 | Pacific Ethnanol Tap | United Electric Co-op, Inc. |  | Unity-West Burley 138 kV | ENERGIZED | ID | Cassia | LL | 2008-12-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0249 | 2006-12-07 05:54 |  |  | Withdrawn on July 11, 2008 | Midway-Big Eddy 230 kV | WITHDRAWN | WA | Klickitat | GI | 2008-12-01 |  | 75 | 75 | Energy | Wind Turbine | Wind Turbine | 75 | [6 empty] | 75 |  |  | . | [5 empty] | FALSE
L0244 | 2006-11-01 08:11 | PSE Alderton Substation | Puget Sound Energy, Inc. | Generation Facility Location Pierce County, WA | Olympia-White River 230 kV | WITHDRAWN | WA | Pierce | LL | 2008-11-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0248 | 2006-11-01 04:00 |  |  | Withdrawn on March 31, 2009 | Idahome Sub | WITHDRAWN | ID | Cassia | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0247 | 2006-11-01 03:58 |  |  | Withdrawn on March 31, 2009 | Idahome Substation | WITHDRAWN | ID | Cassia | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0246 | 2006-11-01 03:52 |  |  |  | Idahome Substation | WITHDRAWN | ID | Cassia | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
G0245 | 2006-11-01 03:49 |  |  | Withdrawn on March 31, 2009 | Idahome Substation | WITHDRAWN | ID | Cassia | GI | 2007-12-31 |  | 20 | 20 | Energy | Wind Turbine | Wind Turbine | 20 | [6 empty] | 20 |  |  | . | [5 empty] | FALSE
L0243 | 2006-10-26 09:12 | Canyon Substation | Tacoma Power |  | South Tacoma Substation | ENERGIZED | WA | Pierce | LL | 2008-10-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0237 | 2006-10-10 16:33 |  |  | Withdrawn by customer email 12/28/2015. FAS Study Issued 7/2/2008 | New Substation near John Day 500kV Substation | WITHDRAWN | OR | Sherman | GI | 2009-11-01 |  | 100 | 100 | NRIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0238 | 2006-10-10 16:01 | Montague I | Avangrid Renewables, LLC | FAS Study Issued 7/20/2008 | Slatt | ENERGIZED | OR | Gilliam | GI | 2010-09-01 | 2019-07-31 | 202 | 202 | ERIS | Wind Turbine | Wind Turbine | 202 | [6 empty] | 202 |  |  | . | [5 empty] | FALSE
G0239 | 2006-10-10 16:01 | Montague 2 | Avangrid Renewables, LLC | FAS Study Issued 7/20/2008 | BPA Slatt Substation | ENERGIZED | OR | Gilliam | GI | 2010-07-01 | 2022-04-30 | 202 | 202 | ERIS | Photovoltaic | Solar | 202 | [6 empty] | 202 |  |  | . | [5 empty] | FALSE
G0240 | 2006-10-10 16:01 |  |  | Withdrawn on August 31, 2007 | Boardman Substation | WITHDRAWN | OR | Morrow | GI | 2010-07-01 |  | 202 | 202 | NRIS | Wind Turbine | Wind Turbine | 202 | [6 empty] | 202 |  |  | . | [5 empty] | FALSE
G0241 | 2006-10-10 16:01 |  |  | Withdrawn on August 31, 2007 | Boardman Substation | WITHDRAWN | OR | Morrow | GI | 2010-09-01 |  | 202 | 202 | NRIS | Wind Turbine | Wind Turbine | 202 | [6 empty] | 202 |  |  | . | [5 empty] | FALSE
G0242 | 2006-10-10 16:01 | Juniper Canyon 2 | Avangrid Renewables, LLC | FAS Restudy Issued 1/19/2017. 4/3/18: Resource fuel type changed from wind to solar | Horse Heaven-Harvalum 230 kV line | ENERGIZED | WA | Klickitat | GI | 2020-12-31 | 2022-01-21 | 90 | 90 | NRIS | Photovoltaic | Solar | 90 | [6 empty] | 90 |  |  | . | [5 empty] | FALSE
L0236 | 2006-10-06 02:38 | Clatskanie Tap | Clatskanie People's Utility District | Clatskanie PUD | Clatskanie Tap | ENERGIZED | OR | Columbia | LL | 2007-11-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0235 | 2006-09-25 09:08 |  |  | Withdrawn by customer email 12/28/2015. FAS Study Issued 7/2/2008 | New Substation near John Day 500kV Substation | WITHDRAWN | OR | Sherman | GI | 2009-11-01 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0234 | 2006-09-05 12:39 |  |  | Withdrawn by Customer on July 8, 2008 | Station Z 230kV | WITHDRAWN | WA | Klickitat | GI | 2007-12-01 |  | 300 | 300 | Energy | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G0233 | 2006-09-05 12:38 |  |  | FAS Study Issued 9/27/2008; NEPA complete 10/1/2008 | Rock Creek Substation | WITHDRAWN | WA | Klickitat | GI | 2007-12-01 |  | 150 | 150 | Energy | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G0232 | 2006-08-25 15:41 |  |  | Withdrawn September 3, 2008 | Big Eddy-DeMoss 115 kV Line | WITHDRAWN | OR | Wasco | GI | 2007-10-01 |  | 10 | 10 | Energy | Wind Turbine | Wind Turbine | 10 | [6 empty] | 10 |  |  | . | [5 empty] | FALSE
L0231 | 2006-08-23 09:37 | Albany Lebanon | Consumers Power, Inc. |  | Tap on Albany-Lebanon 115 kV line | WITHDRAWN | OR | Linn | LL | 2007-09-01 |  | 10 | 10 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0274 | 2006-07-20 11:23 | Lauderdale Project | Public Utility District No. 1 of Kittitas County |  | Columbia-Ellensburg 115kV Line | ENERGIZED | WA | Douglas | LL | 2009-06-01 |  |  |  |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0230 | 2006-07-19 15:58 |  |  | Withdrawn July 17, 2007 | Jones Canyon 230 kV Substation | WITHDRAWN | OR | Gilliam | GI | 2008-06-01 |  | 200 | 200 | ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
L0229 | 2006-06-28 09:00 | Bradwood Tap | PacifiCorp |  | Allston -Astoria #1 115 kV Line near Cathlamet Tap | WITHDRAWN | OR | Clatsop | LL | 2008-01-01 |  | 40 | 40 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0228 | 2006-06-27 09:33 |  |  |  |  | WITHDRAWN | OR | Wasco | GI | 2008-06-30 |  | 80 | 80 | NRIS | Wind Turbine | Wind Turbine | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
L0227 | 2006-06-08 14:58 | Zephyr Heights | Public Utility District No. 1 of Benton County |  | Franklin-Badger Canyon 115 kV | ENERGIZED | WA | Franklin | LL | 2006-12-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0226 | 2006-05-24 09:30 | Leaning Juniper II | Avangrid Renewables, LLC | on-line April 2011 | Jones Canyon Substation | ENERGIZED | OR | Gilliam | GI | 2009-06-01 | 2011-04-01 07:00 | 200 | 200 | ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0225 | 2006-05-18 12:00 |  |  | Withdrawn January 11, 2006 | to be determind | WITHDRAWN | WA | Douglas | GI | 2008-06-01 |  | 127 | 127 | NRIS | Wind Turbine | Wind Turbine | 127 | [6 empty] | 127 |  |  | . | [5 empty] | FALSE
G0224 | 2006-05-09 09:57 | Big Horn 2 | Avangrid Renewables, LLC | on-line September 2010 | Spring Creek 230 kv Sub | ENERGIZED | WA | Klickitat | GI | 2007-06-01 |  | 50 | 50 | NRIS | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0223 | 2006-04-19 15:56 | Hay Canyon/Star Point | Avangrid Renewables, LLC | Hay Canyon on-line December 2008 for 101 MW; Star Point on-line January 2010. Two LGIAs provided. | John Day substation | ENERGIZED | OR | Sherman | GI | 2008-12-01 | 2008-12-01 08:00 | 201 | 201 | NRIS | Wind Turbine | Wind Turbine | 201 | [6 empty] | 201 |  |  | . | [5 empty] | FALSE
G0222 | 2006-03-24 10:17 | Windy Flats -Dooley Wind | Windy Point Partners, LLC | on-line November 2009, combined with G0122, in part | Rock Creek Substation | ENERGIZED | WA | Klickitat | GI | 2008-12-31 | 2009-11-01 07:00 | 250 | 250 | NRIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
L0254 | 2006-03-13 10:39 | Joyce Substation | Public Utility District No. 1 of Clallam County | Studies complete | Port Angeles-Sappho 115 kV Line | ENERGIZED | WA | Clallam | LL | 2008-09-30 |  | 9 | 9 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0214 | 2006-01-05 11:59 |  |  | FAS Study Issued 9/11/2007 | La Pine 230 KV | WITHDRAWN | OR | Deschutes | GI | 2009-09-01 | 2023-01-01 | 140 | 140 | ERIS | Steam Turbine | Geothermal | 140 | [6 empty] | 140 |  |  | . | [5 empty] | FALSE
G0213 | 2005-12-21 10:12 |  |  |  | Longview Substation 230kV | WITHDRAWN | WA | Cowlitz | GI | 2012-01-01 |  | 600 | 600 | NRIS | Gas Turbine | Natural Gas | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
L0219 | 2005-11-17 | Sunset Substation | Portland General Electric Company | Studies complete | Keeler Substation | ENERGIZED | OR | Washington | LL | 2007-01-01 | 2012-06-12 | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0212 | 2005-11-15 14:25 |  |  | Withdrawn by Customer on January 23, 2006. | To Be determined | WITHDRAWN | WA | Kittitas | GI | 2008-01-01 |  | 100 | 100 | NRIS & ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G0211 | 2005-11-14 15:38 |  |  |  | to be determined | WITHDRAWN | WA | Douglas | GI | 2007-10-01 |  | 127 | 127 | NRIS | Wind Turbine | Wind Turbine | 127 | [6 empty] | 127 |  |  | . | [5 empty] | FALSE
L0221 | 2005-11-01 | Pacific West Coast Cable | Sea Breeze Pacific West Coast Cable LP | Sea Breeze Pacific West Coast Cable, LP - failed to execute Facility Study | Allston 500 kV | WITHDRAWN | OR | Columbia | LL | 2007-01-01 |  | 1600 | 1600 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0216 | 2005-09-22 | Vintage Valley | PacifiCorp | Pacificorps | Midway-Mabton 230 | ENERGIZED | OR | Wasco | LL | 2007-04-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0217 | 2005-09-22 | Yew Ave. Sub | PacifiCorp | Pacificorps | Redmond-Harney 115 | ENERGIZED | OR | Deschutes | LL | 2006-12-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
L0218 | 2005-09-22 | Bradwood Tap | PacifiCorp | Pacificorps | Cathlamet Tap-Cathlamet 115 | WITHDRAWN | OR | Clatsop | LL | 2007-01-01 |  | 25 | 25 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0210 | 2005-09-15 09:50 |  |  | Withdrawn by Customer on May 1, 2008. | Grand Coulee-Bell 115 kV line, north of Reardan, WA. | WITHDRAWN | WA | Lincoln | GI | 2006-10-31 |  | 75 | 75 | ERIS | Wind Turbine | Wind Turbine | 75 | [6 empty] | 75 |  |  | . | [5 empty] | FALSE
L0215 | 2005-08-23 | Montanore Mine | Flathead Electric Cooperative, Inc. | Withdrawn by FEC on 4/2/2013. | Libby-Noxon 230 | WITHDRAWN | MT | Lincoln | LL | 2007-06-01 |  | 26 | 26 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G0209 | 2005-08-22 12:28 |  |  | Withdrawn May 21, 2008 | Grand Coulee-Rocky Ford 230 kV line | WITHDRAWN | WA | Grant | GI | 2008-02-01 |  | 124 | 0 | ERIS | Hydro | Water | 124 | [6 empty] | 124 |  |  | . | [5 empty] | FALSE
G0208 | 2005-07-18 13:12 | Tuolumne Wind (Windy Point 1) | Windy Point Partners, LLC | on-line December 2008(sold to Turlock Irrigation District, operated as Tuolumne Wind) | Rock Creek Substation 230 kV | ENERGIZED | WA | Klickitat | GI | 2007-03-01 | 2008-12-01 08:00 | 125 | 125 | NRIS | Wind Turbine | Wind Turbine | 125 | [6 empty] | 125 |  |  | . | [5 empty] | FALSE
G0207 | 2005-06-29 09:46 |  |  |  | John Day Substation 230 kV | WITHDRAWN | OR | Gilliam | GI | 2006-07-15 |  | 200 | 200 | NRIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G0206 | 2005-06-24 |  |  |  |  | WITHDRAWN | OR | Union | GI | 2008-10-01 |  | 110 | 110 | ERIS | Wind Turbine | Wind Turbine | 110 | [6 empty] | 110 |  |  | . | [5 empty] | FALSE
G0205 | 2005-06-16 09:37 | Grays Harbor 1 | Grays Harbor Energy LLC |  | Satsop Substation | ENERGIZED | WA | Grays Harbor | GI | 2006-12-31 |  | 628 | 659 | NRIS | Gas Turbine | Natural Gas | 659 | [6 empty] | 659 |  |  | . | [5 empty] | FALSE
G0203 | 2005-05-26 09:56 | Juniper Canyon 1 | Avangrid Renewables, LLC | on-line February 2011 | Rock Creek | ENERGIZED | WA | Klickitat | GI | 2007-12-01 | 2010-12-16 | 50 | 50 | NRIS | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G0204 | 2005-05-26 09:56 | Juniper Canyon 1 | Avangrid Renewables, LLC | on-line February 2012 | Rock Creek Substation 230 kV. | ENERGIZED | WA | Klickitat | GI | 2007-12-01 | 2011-02-01 08:00 | 100 | 100 | ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
L0201 | 2005-04-04 09:38 | Juan de Fuca HVDC (Port Angeles) | Olympic Converter, LP - Don'T Use | FAS complete. NEPA complete. | Port Angeles 230 kV | STUDY COMPLETED | WA | Clallam | LL | 2007-05-01 | 2025-01-01 | 550 | 550 |  | Other | Other | 550 | [6 empty] | 550 |  |  | . | [5 empty] | FALSE
L0202 | 2005-04-04 09:38 | Juan de Fuca HVDC (Fairmount) | Olympic Converter, LP - Don'T Use | Sea Breeze Olympic Converter, LP | Fairmount 230 kV | STUDY COMPLETED | WA | Jefferson | LL | 2008-05-01 | 2025-01-01 | 550 | 550 |  | Other | Other | 550 | [6 empty] | 550 |  |  | . | [5 empty] | FALSE
G135 | 2004-06-23 13:00 | White Creek Wind I | White Creek Wind I, LLC | on-line August 2007 | Rock Creek | ENERGIZED | WA | Klickitat | GI | 2006-08-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G132 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 1 | Olympic Converter, LP - Don'T Use |  | Port Angeles 230 kV | WITHDRAWN | WA | Clallam | GI | 2007-05-01 |  | 330 | 330 | Energy | Wind Turbine | Wind Turbine | 330 | [6 empty] | 330 |  |  | . | [5 empty] | FALSE
G133 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 2 | Olympic Converter, LP - Don'T Use |  | Port Angeles 230 kV or Fairmount 230 kV | WITHDRAWN | WA | Clallam | GI | 2008-05-01 |  | 330 | 330 | Energy | Wind Turbine | Wind Turbine | 330 | [6 empty] | 330 |  |  | . | [5 empty] | FALSE
G134 | 2004-06-07 11:16 | Sea Breeze Olympic Ph 3 | Olympic Converter, LP - Don'T Use |  | Port Angeles 230 kV or Fairmount 230 kV | WITHDRAWN | WA | Clallam | GI | 2010-05-01 |  | 330 | 330 | Energy | Wind Turbine | Wind Turbine | 330 | [6 empty] | 330 |  |  | . | [5 empty] | FALSE
L0220 | 2004-05-17 | Monmouth Tap | City of Monmouth | Ciy of Monmouth | Salem-Albeni 115 | ENERGIZED | OR | Polk | LL | 2006-12-01 |  | 0 | 0 |  | Other | Other | 0 | [6 empty] | 0 |  |  | . | [5 empty] | FALSE
G131 | 2004-04-27 03:54 | Windtricity Ventures LLC | Windtricity Ventures |  | Rock Creek 230kV | ENERGIZED | WA | Klickitat | GI | 2007-09-15 |  | 150 | 150 | ERIS | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G130 | 2004-04-02 10:28 | N/A | BPA Power Services | Withdrawn by Customer on December 1, 2008. | McNary 230 kV | WITHDRAWN | OR | Umatilla | GI | 2005-10-01 |  | 200 | 200 | Energy | Hydro | Water | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G129 | 2004-03-15 11:38 | River Road Generating Plant | Clark Public Utilities | Plant constructed and operational | Interconnect between River Road Gen and BPA's Alcoa Sub | ENERGIZED | WA | Clark | GI | 2005-07-01 |  | 240 | 240 | Energy | Combined Cycle | Natural Gas | 240 | [6 empty] | 240 |  |  | . | [5 empty] | FALSE
G128 | 2004-03-08 09:53 | Summit/Westward | Summit Power Northwest Project, LLC | March 11, 2010: This is provisionally posted as 'Withdrawn' pending confirmation that OR EFSC has terminated the site certificate. | BPA’s Driscoll 230kV switchyard | WITHDRAWN | OR | Clatsop | GI | 2009-03-10 |  | 536 | 536 | Energy | Gas Turbine | Natural Gas | 536 | [6 empty] | 536 |  |  | . | [5 empty] | FALSE
G127 | 2004-03-04 16:47 | Orion Energy LLC | Orion Energy, LLC |  | DeMoss Substation | WITHDRAWN | OR | Wasco | GI | 2006-12-01 |  | 450 | 450 | Energy | Wind Turbine | Wind Turbine | 450 | [6 empty] | 450 |  |  | . | [5 empty] | FALSE
G126 | 2004-03-04 09:53 | Iberdrola Renewables Inc | Avangrid Renewables, LLC |  | Big Eddy-Midway 230 kV line | ENERGIZED | OR | Wasco | GI | 2005-12-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G125 | 2004-03-01 19:17 | USGeothermal | US Geothermal, Inc. | on-line June 2006 | At Bridge Substation, 34.5 kV ·or·138 kV bus | WITHDRAWN | ID | Cassia | GI | 2006-01-01 |  | 30 | 30 | Energy | Steam Turbine | Geothermal | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
G123 | 2004-02-13 17:28 | NextEra Energy Resources | NextEra Energy Resources, LLC |  | At Stateline Wind Project 115 kV substation | WITHDRAWN | OR | Umatilla | GI | 2005-01-01 |  | 17 | 17 | Energy | Wind Turbine | Wind Turbine | 17 | [6 empty] | 17 |  |  | . | [5 empty] | FALSE
G124 | 2004-02-12 11:53 | Klondike 3 Wind | Klondike Wind Power III, LLC | on-line October 2007, April 2008. | Klondike Schoolhouse 230kV | ENERGIZED | OR | Wasco | GI | 2007-10-15 |  | 300 | 300 | ERIS | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G122 | 2004-01-16 09:55 | Windy Point 1 Wind | Cannon Power Corporation | on-line December 2008, as Tuolumue Wind. | Rock Creek 230kV | ENERGIZED | WA | Klickitat | GI | 2009-07-01 |  | 125 | 125 | ERIS | Wind Turbine | Wind Turbine | 125 | [6 empty] | 125 |  |  | . | [5 empty] | FALSE
G121 | 2003-12-05 11:06 | Willow Creek | Invenergy Wind Development LLC |  | McNary – Santiam 230 kV transmission line | WITHDRAWN | OR | Gilliam | GI | 2005-12-01 |  | 180 | 180 | ERIS | Wind Turbine | Wind Turbine | 180 | [6 empty] | 180 |  |  | . | [5 empty] | FALSE
G120 | 2003-11-24 11:06 | Invenergy Wind Development | Invenergy Wind Development LLC |  | McNary – Santiam 230 kV transmission line | WITHDRAWN | OR | Morrow | GI | 2005-12-01 |  | 180 | 180 | Energy | Wind Turbine | Wind Turbine | 180 | [6 empty] | 180 |  |  | . | [5 empty] | FALSE
G119 | 2003-09-17 17:00 | LifeLine Renewable Energy | Lifeline Renewable Energy, Inc. |  | BPA's McNary - Santiam 230kV Line | WITHDRAWN | OR | Morrow | GI | 2004-10-01 |  | 200 | 200 | ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G118 | 2003-09-17 10:00 | Shepherds Flat | Shepherds Flat Wind, LLC | on-line August 2011; June 2012 (Phase 2 & 3) | BPA's Slatt 500kV Substation | ENERGIZED | OR | Gilliam | GI | 2009-10-01 |  | 750 | 750 | ERIS | Wind Turbine | Wind Turbine | 750 | [6 empty] | 750 |  |  | . | [5 empty] | FALSE
G117 | 2003-07-31 18:45 | NextEra Energy Resources | NextEra Energy Resources, LLC | Withdrawn by Customer on January 30, 2004. | Big Eddy Substation at 230kV. | WITHDRAWN | OR | wasco | GI | 2004-12-31 |  | 100 | 100 | Energy | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G116 | 2003-05-19 18:06 | Oregon Wind | Oregon Wind, LLC | Withdrawn by Customer on January 8, 2009. | Hood River-The Dalles 115 KV Line. | WITHDRAWN | OR | Wasco | GI | 2008-06-01 |  | 50 | 50 | ERIS | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G115 | 2003-05-01 17:58 | Windland Inc | Windland, Inc. | Withdrawn by Customer on July 13, 2005. | Minidoka-Wendover 138 kV Line and/or East Hills 138 kV line | WITHDRAWN | ID | Cassia | GI | 2005-07-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G114 | 2003-01-22 19:44 | Horizon Wind Energy-WRidge | Wind Ridge Power Partners, LLC |  | 230 kV Columbia - Covington line near Kittitas | WITHDRAWN | WA | Kittitas | GI | 2004-09-15 |  | 252 | 252 | Energy | Wind Turbine | Wind Turbine | 252 | [6 empty] | 252 |  |  | . | [5 empty] | FALSE
G113 | 2002-11-20 17:28 | RES North America LLC | RES North America |  | John Day Substation | WITHDRAWN | OR | Sherman | GI | 2004-06-01 |  | 250 | 250 | Energy | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G111 | 2002-11-04 21:29 | Iberdrola Renewables Inc | Avangrid Renewables, LLC | Withdrawn on December 17, 2003. | On Midway – Big Eddy 230 kV Line, 8 mi SW of Bickleton | WITHDRAWN | WA | klickitat | GI | 2004-03-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G112 | 2002-11-01 21:29 | Iberdrola Renewables Inc | Avangrid Renewables, LLC |  | On Hanford-JohnDay 500 kV Line, ~8 miles SW of Bickleton | WITHDRAWN | OR | Klickitat | GI | 2004-03-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G110 | 2002-09-18 11:12 | Shepherds Flat Wind | Shepherds Flat Wind, LLC |  | BPA Slatt 500 kV Substation | WITHDRAWN | OR | Morrow | GI | 2003-10-01 |  | 250 | 250 | ERIS | Wind Turbine | Wind Turbine | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G109-01 | 2002-09-16 21:03 | Iberdrola Renewables Inc | Avangrid Renewables, LLC | Withdrawn on December 19, 2003 by Customer. | Near Slatt 500kV Substation | WITHDRAWN | OR | Gilliam | GI | 2003-12-30 |  | 100 | 100 | Energy | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G109 | 2002-07-24 09:52 | Combine Hills II | Eurus Combine Hills II LLC | on-line January 2010 | Walla Walla-Pendleton 69kV line | ENERGIZED | OR | Umatilla | GI | 2009-12-10 |  | 63 | 63 | ERIS | Wind Turbine | Wind Turbine | 63 | [6 empty] | 63 |  |  | . | [5 empty] | FALSE
G106 | 2002-06-24 17:25 | Pebble Springs Wind Project | Avangrid Renewables, LLC | on-line November 2008 | Jones Canyon substation on McNary Santiam line | ENERGIZED | OR | Gilliam | GI | 2004-01-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G107 | 2002-06-24 17:25 | Ib | Avangrid Renewables, LLC | Withdrawn per 12/16/2003 letter from Customer. | Near Slatt 500kV Substation | WITHDRAWN | OR | Gilliam | GI | 2004-01-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G108 | 2002-06-24 17:22 | Whistling Ridge | Whistling Ridge Energy, LLC | Restudy of plan-of-service, site permit approved; FAS issued 9/12/07 | Midway-North Bonneville 230kV Transmission line | WITHDRAWN | OR | Skamania | GI | 2009-12-31 | 2025-01-01 | 70 | 70 | ERIS | Wind Turbine | Wind Turbine | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G105 | 2002-06-20 23:16 | Desert Claim | enXco Northwest | New plan-of-serivce per customer request, site permits approved; FAS issued 2/4/13 | Covington-Columbia 230kV transmission line | WITHDRAWN | WA | Kittitas | GI | 2009-10-01 |  | 159 | 159 | ERIS | Wind Turbine | Wind Turbine | 159 | [6 empty] | 159 |  |  | Awaiting Customer Permits To Complete NEPA Review | [5 empty] | FALSE
G102 | 2002-06-10 17:00 | Energy Northwest Inc | Energy Northwest Inc |  | Mabton-Big Eddy 230kV line. | WITHDRAWN | WA | Benton | GI | 2004-05-01 |  | 75 | 75 | Energy | Wind Turbine | Wind Turbine | 75 | [6 empty] | 75 |  |  | . | [5 empty] | FALSE
G103 | 2002-06-07 08:30 | Telephone Flat | Calpine Energy Services, L.P. |  | BPA's 230kV Malin-Hilltop line | WITHDRAWN | OR | Klamath | GI | 2004-10-01 |  | 60 | 60 | Energy | Steam Turbine | Geothermal | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
G104 | 2002-06-07 08:30 | Fourmile Hill | Calpine Energy Services, L.P. |  | The BPA's 230kV Malin-Hilltop line | WITHDRAWN | OR | Klamath | GI | 2004-10-01 |  | 60 | 60 | Energy | Steam Turbine | Geothermal | 60 | [6 empty] | 60 |  |  | . | [5 empty] | FALSE
G101 | 2002-06-03 21:10 | NextEra Energy Resources | NextEra Energy Resources, LLC |  | 500 kV McNary-Lower Monumental line | WITHDRAWN | WA | Garfield | GI | 2003-09-01 |  | 300 | 300 | Energy | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G100 | 2002-05-07 06:45 | Hopkins Ridge Wind | Puget Sound Energy, Inc. | on-line December 2005 | At BPA Tucannon River 115 kV Substation on N. Lewiston - Walla Walla line | ENERGIZED | WA | Columbia | GI | 2003-12-01 |  | 150 | 150 | Energy | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G99 | 2002-04-05 14:12 | Biglow Canyon Wind | Portland General Electric Company | PGE acquired 400 MWs of interconnection rights, executed an LGIA and have energized a 400 MW wind project. The other 200 MW is subject to an LGIA executed by Orion Golden Hills Wind Farm LLC. This LGIA was suspended on 11/13/13,pursuant to LGIA Article 5.16, before construction commenced.To restart Transmission Provider's work under this LGIA (including any restudies or supplemental environmental analysis, and preparation of any cost estimates and construction schedule that Transmission Provider may deem necessary) Interconnection Customer must notify Transmission Provider in writing, per Appendix F, to recommence work by Close of Business on November 14, 2016. | Biglow Canyon | ENERGIZED | OR | Sherman | GI | 2008-12-01 |  | 600 | 600 | ERIS | Wind Turbine | Wind Turbine | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G98-01 | 2002-04-05 09:20 | Summit Ridge Project | Seawest Windpower, Inc. | Withdrawn by Customer | Big Eddy–DeMoss 115 kV line 8-9 miles east of Big Eddy | WITHDRAWN | OR | Wasco | GI | 2003-10-31 |  | 75 | 75 | Energy | Wind Turbine | Wind Turbine | 75 | [6 empty] | 75 |  |  | . | [5 empty] | FALSE
G98-02 | 2002-04-05 09:20 | White Creek | Harvest Wind Project | on line January 2010 | Rock Creek 230kV | ENERGIZED | OR | Klickitat | GI | 2009-10-01 |  | 100 | 100 | ERIS | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G97 | 2002-03-19 13:50 | Anderson Ranch Wind Farm | NextEra Energy Resources, LLC | Withdrawn by Customer | Slatt - John Day 500 kV | WITHDRAWN | OR | Gilliam | GI | 2002-09-01 |  | 100 | 100 | Energy | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G98 | 2002-03-19 13:50 | The Dalles Wind Farm | NextEra Energy Resources, LLC | Withdrawn by Customer | Big Eddy-Redmond 230 kV line | WITHDRAWN | OR | Wasco | GI | 2003-09-01 |  | 350 | 350 | Energy | Wind Turbine | Wind Turbine | 350 | [6 empty] | 350 |  |  | . | [5 empty] | FALSE
G96 | 2002-03-08 16:57 | Klondike 2 Wind | Klondike Wind Power II, LLC | on-line June 2005 for 76 MW (combined with G82) | BPA's John Day 230 kV | ENERGIZED | OR | Wasco | GI | 2003-09-01 |  | 50 | 50 | Energy | Wind Turbine | Wind Turbine | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G95 | 2002-02-15 13:18 | Arlington Wind_Wheatfield Wind | EDP Renewables North America LLC | on-line November 2008 for 103 MW and February 2009 for 93 MW (LGIA split) | Jones Canyon Substation | ENERGIZED | OR | Gilliam | GI | 2008-10-01 |  | 200 | 200 | ERIS | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G94 | 2002-02-08 13:00 | Peoples Energy Resources | Peoples Energy Resources Corporation |  | BPA’s 500 kV Grizzly – Malin transmission line approximately 30 miles north of Malin Substation | WITHDRAWN | OR | Klamath | GI | 2005-02-01 |  | 600 | 600 | Energy | Steam Turbine | Geothermal | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G93 | 2002-01-09 13:15 | Duke Energy NA | Duke Energy North America, LLC |  | Between Santiam and Wren Tap at 230kV Line. | WITHDRAWN | OR | Linn | GI | 2005-01-01 |  | 600 | 600 | Energy | Gas Turbine | Natural Gas | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G92 | 2002-01-04 10:45 | Plymouth Energy | Plymouth Energy, LLC |  | BPA’s McNary - John Day 500kV Line in the vicinity of Plymouth, WA. | WITHDRAWN | WA | Benton | GI | 2004-04-27 |  | 306 | 306 | Energy | Gas Turbine | Natural Gas | 306 | [6 empty] | 306 |  |  | . | [5 empty] | FALSE
G91 | 2001-12-20 11:01 | Duke Energy NA | Duke Energy North America, LLC |  | BPA's 230 kV transmission line between Redmond and Pilot Butte substations in Deschutes Co., OR | WITHDRAWN | OR | Deschutes | GI | 2005-06-01 |  | 640 | 640 | Energy | Gas Turbine | Natural Gas | 640 | [6 empty] | 640 |  |  | . | [5 empty] | FALSE
G90 | 2001-11-29 10:39 | Cal Geo | Cal Geo Company |  | Cedarville Junction Substation | WITHDRAWN | CA | modoc | GI | 2003-07-01 |  | 30 | 30 | Energy | Steam Turbine | Geothermal | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
G89 | 2001-11-23 14:32 | Enron Power Marketing | Enron Power Marketing, Inc. | Withdrawn by Customer | Maple Valley 230 kV Substation | WITHDRAWN | WA | King | GI | 2004-01-01 |  | 300 | 300 | Energy | Gas Turbine | Natural Gas | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G88 | 2001-11-21 10:00 | NextEra Energy Resources | NextEra Energy Resources, LLC | Withdrawn by Customer | Sacajawea Substation | WITHDRAWN | WA | Walla Walla | GI | 2002-09-01 |  | 150 | 150 | Energy | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G87 | 2001-10-31 10:26 | Peoples Energy Resources | Peoples Energy Resources Corporation | Withdrawn by Customer | 500 kV Grizzly – Malin line near Malin Substation | WITHDRAWN | OR | Klamath | GI | 2005-03-01 |  | 1200 | 1200 | Energy | Gas Turbine | Natural Gas | 1200 | [6 empty] | 1200 |  |  | . | [5 empty] | FALSE
G84 | 2001-10-29 10:43 | Touchet Wind Farm | Winds Over Washington Energy Group | Withdrawn by Customer | 500 kV Lower Monumental - McNary line near Wallula, WA | WITHDRAWN | WA | Walla Walla | GI | 2004-01-01 |  | 150 | 150 | Energy | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G85 | 2001-10-29 10:43 | Windy Ridge Wind Farm | Winds Over Washington Energy Group | Withdrawn by Customer | BPA's Lower Monumental Substation | WITHDRAWN | WA | Garfield | GI | 2004-01-01 |  | 150 | 150 | Energy | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G86 | 2001-10-29 10:43 | Eureka Flats Wind Farm | Winds Over Washington Energy Group | Withdrawn by Customer | 500 kV Lower Monumental McNary line | WITHDRAWN | WA | Whatcom | GI | 2004-01-01 |  | 150 | 150 | Energy | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G83 | 2001-10-24 08:05 | Sempra Generation | Sempra Generation, LLC | Withdrawn by Customer | BPA's Pearl - Marion 500 kV line in the vicinity of Aurora, OR | WITHDRAWN | OR | Marion | GI | 2005-06-01 |  | 612 | 612 | Energy | Gas Turbine | Natural Gas | 612 | [6 empty] | 612 |  |  | . | [5 empty] | FALSE
G82 | 2001-10-18 13:33 | Klondike 1 Wind | Northwestern Wind Power, LLC | combined with G96 | Interconnection is BPA's De Moss 115 kV Substation | ENERGIZED | OR | Wasco | GI | 2002-09-01 |  | 26 | 26 | Energy | Wind Turbine | Wind Turbine | 26 | [6 empty] | 26 |  |  | . | [5 empty] | FALSE
G81 | 2001-10-10 18:39 | Clipper WindPower | Clipper Windpower Development, Inc. | Withdrawn by Customer | BPA's 115kV transmission line near Langlois Substation | WITHDRAWN | OR | Curry | GI | 2002-06-01 |  | 53 | 53 | Energy | Wind Turbine | Wind Turbine | 53 | [6 empty] | 53 |  |  | . | [5 empty] | FALSE
G80 | 2001-09-28 11:54 | Kittitas Valley Wind | Sagebrush Power Partners, LLC | on-line 12/20/2010. Request reduced to 101 MW | Columbia Covington 230kV line (Bettas Road Substation) | ENERGIZED | WA | Kittitas | GI | 2009-12-31 |  | 108 | 108 | ERIS | Wind Turbine | Wind Turbine | 108 | [6 empty] | 108 |  |  | . | [5 empty] | FALSE
G79 | 2001-09-27 16:34 | Horizon Wind Energy-WRidge | Wind Ridge Power Partners, LLC | Withdrawn by Customer | 115 kV North Lewiston-Walla Walla line near Clarkston WA | WITHDRAWN | WA | Asotin | GI | 2003-06-15 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G78 | 2001-09-27 16:32 | Horizon Wind Energy-Wheat | Wheat Field Power Partners, LLC | Withdrawn on July 11, 2003 | BPA's Big Eddy - Maupin 230kV transmission line in the vicinity of Dufur, Oregon | WITHDRAWN | OR | Wasco | GI | 2005-10-01 |  | 195 | 195 | Energy | Wind Turbine | Wind Turbine | 195 | [6 empty] | 195 |  |  | . | [5 empty] | FALSE
G77 | 2001-09-21 17:49 | 300MW Lower Monumental-Starbuck | RES North America | Withdrawn by Customer | Lower Monumental-Starbuck 500 kV line. | WITHDRAWN | WA | Columbia | GI | 2004-06-01 |  | 300 | 300 | Energy | Wind Turbine | Wind Turbine | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G76 | 2001-09-19 17:49 | 200MW North Lewiston-Walla Walla 2 | RES North America | Withdrawn by Customer | 115 kV North Lewiston-Walla Walla line | WITHDRAWN | WA | Walla Walla | GI | 2002-12-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G75 | 2001-09-19 14:02 | 200MW North Lewiston-Walla Walla 1 | RES North America | Withdrawn by Customer | 115 kV North Lewiston-Walla Walla line | WITHDRAWN | WA | Walla Walla | GI | 2002-12-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G74 | 2001-09-19 09:20 | Cielo Wind Power | Cielo Wind Power | Withdrawn by Customer | Big Eddy 230 kV line South of Goldendale. | WITHDRAWN | WA | Klickitat | GI | 2003-08-01 |  | 80 | 80 | Energy | Wind Turbine | Wind Turbine | 80 | [6 empty] | 80 |  |  | . | [5 empty] | FALSE
G73-01 | 2001-09-18 11:06 | Nine Canyon 2 | Energy Northwest (CGS) | on-line January 2008; reduced request from 100 MW | 115 kV McNary-Badger Canyon line (Nine Canyon Substation) | ENERGIZED | WA | Benton | GI | 2007-11-01 |  | 32 | 32 | ERIS | Wind Turbine | Wind Turbine | 32 | [6 empty] | 32 |  |  | . | [5 empty] | FALSE
G73 | 2001-09-12 10:03 | OR-CAL Power | Or-Cal Power, Inc. | Withdrawn by Customer | LaPine Substation | WITHDRAWN | OR | Deschutes | GI | 2003-03-01 |  | 97 | 97 | Energy | Steam Turbine | Geothermal | 97 | [6 empty] | 97 |  |  | . | [5 empty] | FALSE
G72 | 2001-08-20 17:19 | AES Pacific Inc | AES Pacific Inc | Withdrawn by Customer | BPA's Proposed Wallula 500 kV Substation | WITHDRAWN | WA | Walla Walla | GI | 2002-06-01 |  | 300 | 300 | Energy | Gas Turbine | Natural Gas | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G71-01 | 2001-08-20 09:30 | GNA Energy | GNA Energy, LLC | Withdrawn on December 3, 2010 | BPA's Harvalum 230 kV Substation in Goldendal WA. | WITHDRAWN | WA | Klickitat | GI | 2003-01-15 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G71 | 2001-08-17 15:50 | AES Pacific Inc | AES Pacific Inc | Withdrawn by Customer | BPA's Canby 230 kV Substation in Modoc County, CA. | WITHDRAWN | CA | Modoc | GI | 2002-06-01 |  | 300 | 300 | Energy | Reciprocating Engine | Biofuel | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G70-01 | 2001-08-14 13:47 | 01 37MW Connell | Effective Energy Corporation | Withdrawn on December 3, 2010 | BPA's Connell Substation | WITHDRAWN | WA | Franklin | GI | 2002-06-01 |  | 37 | 37 | Energy | Gas Turbine | Natural Gas | 37 | [6 empty] | 37 |  |  | . | [5 empty] | FALSE
G70-02 | 2001-08-14 13:47 | 02 37MW Franklin PUD,Franklin Riverview | Effective Energy Corporation | Request submitted as 36.1 MW | Franklin PUD's Oregon Street Substation | WITHDRAWN | WA | Franklin | GI | 2002-06-01 |  | 37 | 37 | Energy | Gas Turbine | Natural Gas | 37 | [6 empty] | 37 |  |  | . | [5 empty] | FALSE
G70 | 2001-07-24 10:32 | Frederickson Power LP | Frederickson Power, LP | Withdrawn by Customer | South Tacoma Substation. | WITHDRAWN | WA | Pierce | GI | 2002-10-01 |  | 300 | 300 | Energy | Gas Turbine | Natural Gas | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G69 | 2001-07-12 15:37 | National Energy and Gas Tx | National Energy & Gas Transmission, Inc. | Withdrawn by Customer | Coyote Springs loop on the McNary/Slatt 500 kV line | WITHDRAWN | OR | Morrow | GI | 2005-02-01 |  | 620 | 620 | Energy | Gas Turbine | Natural Gas | 620 | [6 empty] | 620 |  |  | . | [5 empty] | FALSE
G68 | 2001-07-05 09:56 | Clatskanie | Clatskanie People's Utility District | Withdrawn by Customer | The Wauna Substation | WITHDRAWN | OR | Clatsop | GI | 2001-11-15 |  | 65 | 65 | Energy | Gas Turbine | Natural Gas | 65 | [6 empty] | 65 |  |  | . | [5 empty] | FALSE
G66 | 2001-06-29 12:07 | 100MW Harvalum | ABB Equity Ventures Inc | Withdrawn by Customer | Harvalum Substation | WITHDRAWN | WA | Klickitat | GI | 2003-09-01 |  | 100 | 100 | Energy | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G67 | 2001-06-29 12:07 | 100MW Midway-Bonneville | ABB Equity Ventures Inc | Withdrawn by Customer | Midway-Bonneville 230 kV line near Goldendale WA | WITHDRAWN | OR | Klickitat | GI | 2003-09-01 |  | 100 | 100 | Energy | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G65 | 2001-06-22 07:12 | 310MW Cardwell | Cogentrix Energy, Inc. | Withdrawn by Customer | Cardwell Substation | WITHDRAWN | WA | Cowlitz | GI | 2003-06-01 |  | 310 | 310 | Energy | Gas Turbine | Natural Gas | 310 | [6 empty] | 310 |  |  | . | [5 empty] | FALSE
G64 | 2001-06-21 08:15 | US Elect Power Corp | US Electric Power Corporation | Withdrawn by Customer | Interconnection at 230 kV Customer Substation | WITHDRAWN | WA | Whatcom | GI | 2004-03-01 |  | 349 | 349 | Energy | Gas Turbine | Natural Gas | 349 | [6 empty] | 349 |  |  | . | [5 empty] | FALSE
G62 | 2001-06-07 09:45 | 30MW Walla Walla-Pendleton | FPL Energy Power Marketing Inc | Withdrawn by Customer | Walla Walla-Pendleton 69 kV line near Duroc | WITHDRAWN | OR | Umatilla | GI | 2002-09-01 |  | 30 | 30 | Energy | Wind Turbine | Wind Turbine | 30 | [6 empty] | 30 |  |  | . | [5 empty] | FALSE
G63 | 2001-06-07 09:45 | 70MW Walla Walla-Franklin | FPL Energy Power Marketing Inc | Withdrawn by Customer | Nine Mile Tap on the Walla Walla-Franklin 115 kV line | WITHDRAWN | OR | Umatilla | GI | 2002-09-01 |  | 70 | 70 | Energy | Wind Turbine | Wind Turbine | 70 | [6 empty] | 70 |  |  | . | [5 empty] | FALSE
G61 | 2001-06-05 14:25 | Black Hills Energy | Black Hills Energy Capital Inc | Withdrawn by Customer | Hay Mill 138 kV Substation | WITHDRAWN | ID | Minidoka | GI | 2002-07-01 |  | 55 | 55 | Energy | Gas Turbine | Natural Gas | 55 | [6 empty] | 55 |  |  | . | [5 empty] | FALSE
G59 | 2001-05-31 14:33 | 700MW Sickler-Schultz | Calpine Energy Services, L.P. | Withdrawn by Customer | Sickler-Schultz 500 kV | WITHDRAWN | WA | Benton | GI | 2005-06-01 |  | 700 | 700 | Energy | Gas Turbine | Natural Gas | 700 | [6 empty] | 700 |  |  | . | [5 empty] | FALSE
G60 | 2001-05-31 14:33 | 1300MW Sickler-Schultz | Calpine Energy Services, L.P. | Withdrawn by Customer | Sickler-Schultz 500 kV | WITHDRAWN | WA | Benton | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Gas Turbine | Natural Gas | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G58 | 2001-05-23 10:02 | 105MW McNary-Roundup | Seawest Windpower, Inc. | Withdrawn by Customer | McNary-Roundup 230 kV line | WITHDRAWN | OR | Umatilla | GI | 2003-09-01 |  | 105 | 105 | Energy | Wind Turbine | Wind Turbine | 105 | [6 empty] | 105 |  |  | . | [5 empty] | FALSE
G57 | 2001-05-22 15:15 | GNA Energy | Seawest Windpower, Inc. | Withdrawn by Customer | Big Eddy-DeMoss 115 kV line | WITHDRAWN | OR | Sherman | GI | 2003-09-01 |  | 105 | 105 | Energy | Wind Turbine | Wind Turbine | 105 | [6 empty] | 105 |  |  | . | [5 empty] | FALSE
G56 | 2001-05-11 17:54 | GNA Energy | GNA Energy, LLC | Withdrawn by Customer | Harvalum 230 kV Substation | WITHDRAWN | WA | Klickitat | GI | 2002-02-01 |  | 45 | 45 | Energy | Gas Turbine | Natural Gas | 45 | [6 empty] | 45 |  |  | . | [5 empty] | FALSE
G55 | 2001-05-11 16:34 | Cedar Hills Energy LLC | Cedar Hills Energy LLC | Withdrawn by Customer | Maple Valley 230 kV Substation | WITHDRAWN | WA | King | GI | 2004-01-01 |  | 300 | 300 | Energy | Gas Turbine | Natural Gas | 300 | [6 empty] | 300 |  |  | . | [5 empty] | FALSE
G54 | 2001-05-09 11:19 | Klondike Wind Power | Klondike Wind Power, LLC | on-line December 2000; later sold to Iberdrola and operated as Klondike 1 | De Moss 69 kV Substation, relocated to 230 kV KSHS | ENERGIZED | OR | Sherman | GI | 2001-10-31 |  | 24 | 24 | Energy | Wind Turbine | Wind Turbine | 24 | [6 empty] | 24 |  |  | . | [5 empty] | FALSE
G53 | 2001-05-04 11:37 | Tacoma Power TC-PSE | Tacoma Power | Withdrawn by Customer | 230 kV Sedro Wooley-Bellingham line | WITHDRAWN | WA | Skagit | GI | 2002-01-01 |  | 83 | 83 | Energy | Gas Turbine | Natural Gas | 83 | [6 empty] | 83 |  |  | . | [5 empty] | FALSE
G51 | 2001-05-03 15:17 | Pierce County Project No 1 | Duke Energy North America, LLC | Withdrawn by Customer | South Tacoma 230 kV Substation | WITHDRAWN | WA | Pierce | GI | 2003-01-01 |  | 170 | 170 | Energy | Gas Turbine | Natural Gas | 170 | [6 empty] | 170 |  |  | . | [5 empty] | FALSE
G52 | 2001-05-03 15:17 | Pierce County Project No 2 | Duke Energy North America, LLC | Pierce County Project No. 2 | South Tacoma 230 kV Substation | WITHDRAWN | WA | Pierce | GI | 2003-01-01 |  | 170 | 170 | Energy | Gas Turbine | Natural Gas | 170 | [6 empty] | 170 |  |  | . | [5 empty] | FALSE
G48-01 | 2001-04-23 18:47 |  | Washington Winds, Inc. | Withdrawn by Customer | 230 kV Big Eddy-Midway/ 500 kV Hanford-John Day line | WITHDRAWN | WA | BentoN | GI | 2002-11-15 |  | 249 | 249 | Energy | Wind Turbine | Wind Turbine | 249 | [6 empty] | 249 |  |  | . | [5 empty] | FALSE
G48 | 2001-04-23 18:47 |  | Washington Winds, Inc. | Withdrawn on January 28, 2004 | 230 kV Big Eddy-Midway/ 500 kV Hanford-John Day line | WITHDRAWN | WA | Benton | GI | 2002-11-15 |  | 150 | 150 | Energy | Wind Turbine | Wind Turbine | 150 | [6 empty] | 150 |  |  | . | [5 empty] | FALSE
G49 | 2001-04-23 09:46 |  | Washington Winds, Inc. |  | 230 kV Big Eddy-Midway/ 500 kV Hanford-John Day line | WITHDRAWN | WA | Benton | GI | 2002-11-30 |  | 249 | 249 | Energy | Wind Turbine | Wind Turbine | 249 | [6 empty] | 249 |  |  | . | [5 empty] | FALSE
G50 | 2001-04-23 09:46 | Pacific Winds Inc | Pacific Winds, Inc. | Withdrawn by Customer | 230/kV McNary - Horse Heaven/ 345 kV McNary - Ross line | WITHDRAWN | WA | Klickitat | GI | 2003-03-31 |  | 249 | 249 | Energy | Wind Turbine | Wind Turbine | 249 | [6 empty] | 249 |  |  | . | [5 empty] | FALSE
G47 | 2001-04-19 09:52 | Nordic Energy Barge No 2 | Nordic Energy Barge #2, LLC | Withdrawn by Customer | Trojan Switching Station | WITHDRAWN | OR | Columbia | GI | 2001-12-01 |  | 170 | 170 | Energy | Gas Turbine | Natural Gas | 170 | [6 empty] | 170 |  |  | . | [5 empty] | FALSE
G46-03 | 2001-04-18 09:00 | 100MW Cowlitz-Cardwell | Avista Power, LLC | Withdrawn by Customer | Cowlitz-Cardwell 115 kV line | WITHDRAWN | WA | Cowlitz | GI | 2001-12-01 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G46-01 | 2001-04-17 16:21 | Clark Public Utilities | Clark Public Utilities |  | 115 kV bus at BPA Alcoa Substation | WITHDRAWN | WA | Clark | GI | 2002-07-01 |  | 250 | 250 | Energy | Gas Turbine | Natural Gas | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G46 | 2001-04-16 16:31 | Coburg Power | Coberg Power LLC | Withdrawn on October 16, 2004 | Marion-Lane No. 1 500 kV line near Colburg | WITHDRAWN | OR | Lane | GI | 2004-08-01 |  | 570 | 570 | Energy | Gas Turbine | Natural Gas | 570 | [6 empty] | 570 |  |  | . | [5 empty] | FALSE
G45 | 2001-04-11 17:50 | 100MW Longview 2 | Avista Power, LLC | Withdrawn by Customer | BPA's Longview Substation | WITHDRAWN | WA | Cowlitz | GI | 2001-12-01 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G44 | 2001-04-11 17:50 | 100MW Longview 1 | Avista Power, LLC | Withdrawn by Customer | BPA's Longview Substation | WITHDRAWN | WA | Cowlitz | GI | 2001-12-01 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G43 | 2001-04-06 17:03 | Clatskanie | Clatskanie People's Utility District | Withdrawn by Customer | Alcoa Substation 115 kV | WITHDRAWN | OR | Columbia | GI | 2002-05-15 |  | 88 | 88 | Energy | Gas Turbine | Natural Gas | 88 | [6 empty] | 88 |  |  | . | [5 empty] | FALSE
G42 | 2001-04-06 12:25 | 50MW Alcoa | Calpine Energy Services, L.P. | Withdrawn by Customer | Alcoa Substation 230 kV in the vicinity of Vancouver, WA | WITHDRAWN | WA | Clark | GI | 2001-10-31 |  | 50 | 50 | Energy | Gas Turbine | Natural Gas | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G41 | 2001-04-06 12:25 | 100MW McNary | Calpine Energy Services, L.P. | Withdrawn by Customer | McNary Substation | WITHDRAWN | OR | Umatilla | GI | 2001-12-01 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G40 | 2001-04-06 12:24 | 250MW Covington-Chehalis,Tacoma-Olympia | Calpine Energy Services, L.P. | Withdrawn by Customer | 230 kV Covington-Chehalis and/or Tacoma-Olympia lines | WITHDRAWN | WA | Pierce | GI | 2001-05-01 |  | 250 | 250 | Energy | Gas Turbine | Natural Gas | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G39 | 2001-04-04 12:04 | Grant Generation | Grant Generation, LLC | Withdrawn by Customer | Vantage-Hanford 500 kV line | WITHDRAWN | WA | Grant | GI | 2005-02-01 |  | 1300 | 1300 | Energy | Gas Turbine | Natural Gas | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G46-02 | 2001-04-01 09:00 | 100MW Cowlitz PUD BHP at Kalama | Avista Power, LLC | Withdrawn by Customer | Cowlitz PUD BHP at Kalama 115 kV line | WITHDRAWN | WA | Cowlitz | GI | 2001-12-01 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G38 | 2001-03-22 17:21 | 600 MW Monroe-Custer | Calpine Energy Services, L.P. | Withdrawn by Customer | Monroe-Custer 500 kV line near Sedro Wooley | WITHDRAWN | WA | Skagit | GI | 2005-06-01 |  | 600 | 600 | Energy | Gas Turbine | Natural Gas | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G37 | 2001-03-20 08:12 | Nordic Energy Barge 1 | Nordic Energy Barge #1, LLC | Withdrawn by Customer | Cowlitz Substation | WITHDRAWN | WA | Cowlitz | GI | 2001-08-01 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G36 | 2001-03-16 14:23 | Frontier Technology | Frontier Technology, Inc | Withdrawn on October 11, 2002 | Marion-Lane No. 1 500 kV transmission line near Colburg | WITHDRAWN | OR | Lane | GI | 2003-08-01 |  | 265 | 265 | Energy | Gas Turbine | Natural Gas | 265 | [6 empty] | 265 |  |  | . | [5 empty] | FALSE
G35 | 2001-03-06 18:36 | Grant Generation | Grant Generation, LLC | Withdrawn on October 11, 2002 | Grand Coulee-Schultz 500 kV line | WITHDRAWN | WA | Grant | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Gas Turbine | Natural Gas | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G34 | 2001-03-06 16:08 | Competitive Power Venture | Newport Northwest, LLC |  | Intalco 500 kV Substation | WITHDRAWN | WA | Whatcom | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Gas Turbine | Natural Gas | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G33 | 2001-03-06 10:57 | Tenaska Inc | Tenaska, Inc. | Withdrawn on July 15, 2002 | Captain Jack 500 kV Substation | WITHDRAWN | OR | Klamath | GI | 2004-06-01 |  | 450 | 450 | Energy | Gas Turbine | Natural Gas | 450 | [6 empty] | 450 |  |  | . | [5 empty] | FALSE
G32 | 2001-03-05 08:28 | Kootenai Generation | Kootenai Electric Cooperative, Inc. | Withdrawn on October 11, 2002 | BPA's Taft-Bell 500 kV line | WITHDRAWN | WA | Kootenai | GI | 2005-06-01 |  | 1300 | 1300 | Energy | Gas Turbine | Natural Gas | 1300 | [6 empty] | 1300 |  |  | . | [5 empty] | FALSE
G30 | 2001-03-01 13:57 | Pacific Winds Inc | Pacific Winds, Inc. | Withdrawn by Customer | 230 kV Hanford-Mabton transmission line near Rattlesnake Hills | WITHDRAWN | WA | Benton | GI | 2002-11-15 |  | 100 | 100 | Energy | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G31 | 2001-03-01 13:57 | Pacific Winds Inc | Pacific Winds, Inc. | Withdrawn by Customer | 230 kV Franklin-McNary line near Horse Heaven Hills | WITHDRAWN | WA | Benton | GI | 2002-11-15 |  | 100 | 100 | Energy | Wind Turbine | Wind Turbine | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G29 | 2001-02-23 14:46 | BP Energy Company | BP Energy Company | Withdrawn on October 11, 2002 | John Day | WITHDRAWN | OR | Grant | GI | 2004-01-01 |  | 200 | 200 | Energy | Wind Turbine | Wind Turbine | 200 | [6 empty] | 200 |  |  | . | [5 empty] | FALSE
G28 | 2001-02-22 14:59 | N/A | Clark Public Utilities | Withdrawn on October 30, 2002 | Alcoa Substation | WITHDRAWN | WA | Clark | GI | 2001-01-01 |  | 100 | 100 | Energy | Gas Turbine | Natural Gas | 100 | [6 empty] | 100 |  |  | . | [5 empty] | FALSE
G27-01 | 2001-02-20 17:05 | Cherry Point Refinery | BP Energy Company | LGIA terminated on February 1, 2011. | Custer Substation | WITHDRAWN | WA | Whatcom | GI | 2004-01-01 |  | 1000 | 1000 | Energy | Gas Turbine | Natural Gas | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
G22 | 2001-02-16 06:13 | 50MW Alcoa-St Johns | Calpine Energy Services, L.P. |  | Tap of Alcoa-St. Johns 115 kV line | WITHDRAWN | WA | Clark | GI | 2001-11-01 |  | 50 | 50 | Energy | Gas Turbine | Natural Gas | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G27 | 2001-02-15 16:26 | Benton PUD | Public Utility District No. 1 of Benton County |  | Unocal Finley Substation | WITHDRAWN | WA | Benton | GI | 2001-08-01 |  | 25 | 25 | Energy | Gas Turbine | Natural Gas | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G26 | 2001-02-15 15:51 | Wanapa Energy Center | Confederated Tribes Umatilla Indian Reservation | Withdrawn by Customer 7/30/2015 | McNary 500 kV bus | WITHDRAWN | OR | Umatilla | GI | 2003-07-01 |  | 1000 | 1000 | Energy | Gas Turbine | Natural Gas | 1000 | [6 empty] | 1000 |  |  | . | [5 empty] | FALSE
G25 | 2001-02-15 14:14 | 500MW Custer-[Intalco,Portal Way] 2 | Calpine Energy Services, L.P. |  | Custer-Inalco/Portal Way 230 kV transmission line | WITHDRAWN | WA | Whatcom | GI | 2004-06-01 |  | 500 | 500 | Energy | Gas Turbine | Natural Gas | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G24 | 2001-02-15 14:14 | 500MW Custer-[Intalco,Portal Way] 1 | Calpine Energy Services, L.P. |  | Custer-Intalco/Portal Way 230 kV transmission line | WITHDRAWN | WA | Whatcom | GI | 2005-06-01 |  | 500 | 500 | Energy | Gas Turbine | Natural Gas | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G23 | 2001-02-15 14:13 | 500MW St Johns-Ross | Calpine Energy Services, L.P. |  | St. Johns-Ross 230 kV line | WITHDRAWN | WA | Clark | GI | 2005-06-01 |  | 500 | 500 | Energy | Gas Turbine | Natural Gas | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G21 | 2001-02-05 14:48 | Condon Wind Farm | Seawest Windpower, Inc. | on-line 2000 | At the Demoss-Fossil 69 kV line near Condon, OR | ENERGIZED | OR | Gilliam | GI | 2002-01-01 |  | 25 | 25 | Energy | Wind Turbine | Wind Turbine | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G20 | 2001-02-05 14:48 | Centralia Generation Addition | TransAlta Utilities Cooperative | on-line | Tap of the Centralia-Paul 500 kV line | DECOMMISSIONED | WA | Lewis | GI | 2002-01-01 |  | 248 | 248 | Energy | Gas Turbine | Natural Gas | 248 | [6 empty] | 248 |  |  | . | [5 empty] | FALSE
G19-01 | 2001-01-25 16:06 | Summit PNW | Summit Power Northwest Project, LLC | Withdrawn on March 11, 2010. | Allston 230 KV | WITHDRAWN | OR | Clatsop | GI | 2003-10-31 |  | 520 | 520 | Energy | Gas Turbine | Natural Gas | 520 | [6 empty] | 520 |  |  | . | [5 empty] | FALSE
G19 | 2001-01-18 18:18 | 500MW Snohomish | FPL Energy Power Marketing Inc |  | At 115 kV and 230 kV Snohomish Substation | WITHDRAWN | WA | Snohomish | GI | 2002-09-01 |  | 500 | 500 | Energy | Gas Turbine | Natural Gas | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G18 | 2001-01-10 12:42 | 250MW Snohomish | FPL Energy Power Marketing Inc |  | Snohomish 115 kV Substation | WITHDRAWN | WA | Snohomish | GI | 2002-09-01 |  | 250 | 250 | Energy | Gas Turbine | Natural Gas | 250 | [6 empty] | 250 |  |  | . | [5 empty] | FALSE
G17 | 2000-12-24 14:40 | JP Saylor and Associates | J P Saylor & Associates |  | BPA's Fairview-Rogue 230 kV line in the vicinity of Curry County, OR | WITHDRAWN | OR | Curry | GI | 2001-10-31 |  | 25 | 25 | Energy | Wind Turbine | Wind Turbine | 25 | [6 empty] | 25 |  |  | . | [5 empty] | FALSE
G16 | 2000-12-22 13:31 | 500MW Taft-Bell | Cogentrix Energy, Inc. |  | BPA's Taft-Bell 500 kV line in the vicinity of Kootenaid County, ID | WITHDRAWN | ID | Kootenai | GI | 2004-12-01 |  | 500 | 500 | Energy | Gas Turbine | Natural Gas | 500 | [6 empty] | 500 |  |  | . | [5 empty] | FALSE
G15 | 2000-12-18 14:51 | Oregon Energy Company | Oregon Energy Company LLC |  | on BPA's 115 kV Allston-St. Helens line in the vicinity of St. Helens, OR | WITHDRAWN | OR | Columbia | GI | 2002-08-01 |  | 170 | 170 | Energy | Gas Turbine | Natural Gas | 170 | [6 empty] | 170 |  |  | . | [5 empty] | FALSE
G14 | 2000-11-30 15:38 | Stateline Wind Farm | FPL Energy Vansycle L.L.C. | on-line October 2008 | on BPA's Franklin-Walla Walla line in the vicinity of Touchet, WA | ENERGIZED | OR | Umatilla | GI | 2001-09-01 |  | 90 | 90 | Energy | Wind Turbine | Wind Turbine | 90 | [6 empty] | 90 |  |  | . | [5 empty] | FALSE
G13 | 2000-10-31 14:50 | Centralia Generation | TransAlta Utilities Cooperative |  | C.W. Paul 500 kV Substation | DECOMMISSIONED | WA | Lewis | GI | 2001-06-01 |  | 50 | 50 | ERIS | Gas Turbine | Natural Gas | 50 | [6 empty] | 50 |  |  | . | [5 empty] | FALSE
G11 | 2000-09-13 16:25 | Pacific Winds Inc | Pacific Winds, Inc. |  | a new POR in the vicinity of the Franklin-McNary 230 kV line | WITHDRAWN | WA | Benton | GI | 2002-07-01 |  | 76 | 76 | Energy | Wind Turbine | Wind Turbine | 76 | [6 empty] | 76 |  |  | . | [5 empty] | FALSE
G12 | 2000-09-09 00:06 | Oregon Energy Company | Oregon Energy Company LLC | Withdrawn on July 8, 2002. | Albany-Eugene 115 kV line near Halsey, OR | WITHDRAWN | OR | Linn | GI | 2001-10-01 |  | 120 | 120 | Energy | Gas Turbine | Natural Gas | 120 | [6 empty] | 120 |  |  | . | [5 empty] | FALSE
G10 | 2000-08-28 14:52 | 1100MW Grizzly | Cogentrix Energy, Inc. |  | Grizzly 500 kV Substation | WITHDRAWN | OR | Jefferson | GI | 2004-07-01 |  | 1100 | 1100 | Energy | Gas Turbine | Natural Gas | 1100 | [6 empty] | 1100 |  |  | . | [5 empty] | FALSE
G9 | 2000-08-28 14:51 | 1100MW Paul | Cogentrix Energy, Inc. |  | Paul 500 kV Substation | WITHDRAWN | WA | Lewis | GI | 2004-07-01 |  | 1100 | 1100 | Energy | Gas Turbine | Natural Gas | 1100 | [6 empty] | 1100 |  |  | . | [5 empty] | FALSE
G8 | 2000-08-28 14:50 | 1100MW Troutdale | Cogentrix Energy, Inc. | Withdrawn by Customer | Troutdale kV Substation | WITHDRAWN | OR | Multnomah | GI | 2004-07-01 |  | 1100 | 1100 | Energy | Gas Turbine | Natural Gas | 1100 | [6 empty] | 1100 |  |  | . | [5 empty] | FALSE
G7 | 2000-08-25 14:19 | Pacific Winds Inc | Pacific Winds, Inc. | Withdrawn by Customer | Hanford-Mabton 230 kV line | WITHDRAWN | WA | Benton | GI | 2002-10-31 |  | 76 | 76 | Energy | Wind Turbine | Wind Turbine | 76 | [6 empty] | 76 |  |  | . | [5 empty] | FALSE
G6 | 2000-08-22 14:30 | Continental Energy Svcs | Continental Energy Services, Inc. | Withdrawn by Customer | Silver Bow 230 kV Substation | WITHDRAWN | MT | Silver Bow | GI | 2002-03-31 |  | 400 | 400 | Energy | Gas Turbine | Natural Gas | 400 | [6 empty] | 400 |  |  | . | [5 empty] | FALSE
G5 | 2000-08-02 07:56 | Nine Canyon Wind Project | Energy Northwest Inc |  | 115 kV McNary-Badger Canyon line (Nine Canyon Substation) | ENERGIZED | WA | Benton | GI | 2001-09-01 |  | 63 | 63 | Energy | Wind Turbine | Wind Turbine | 63 | [6 empty] | 63 |  |  | . | [5 empty] | FALSE
G4 | 2000-07-28 16:17 | Mint Farm Energy Center | Puget Sound Energy, Inc. | on-line | Longview 230 kV Substation | ENERGIZED | WA | Cowlitz | GI | 2007-11-28 |  | 320 | 320 | Energy | Gas Turbine | Natural Gas | 320 | [6 empty] | 320 |  |  | . | [5 empty] | FALSE
G3 | 2000-07-28 15:55 | Enron Power Marketing | Enron Power Marketing, Inc. | Withdrawn by Customer | Longview 230 kV Substation | WITHDRAWN | WA | Cowlitz | GI | 2003-06-01 |  | 600 | 600 | Energy | Gas Turbine | Natural Gas | 600 | [6 empty] | 600 |  |  | . | [5 empty] | FALSE
G2 | 2000-06-23 | Goldendale Energy Center | Goldendale Energy Center, LLC | on-line | Harvalum 230 kV Substation | ENERGIZED | OR | klickitat | GI | 2002-01-01 |  | 247 | 247 | Energy | Gas Turbine | Natural Gas | 247 | [6 empty] | 247 |  |  | . | [5 empty] | FALSE
G1 | 2000-06-09 16:12 | PG and E Generation | PG&E Energy Services |  | McNary 230 kv Substation | WITHDRAWN | OR | Umatilla | GI | 2000-06-09 |  | 581 | 581 | Energy | Gas Turbine | Natural Gas | 581 | [6 empty] | 581 |  |  | . | [5 empty] | FALSE