## Request List
Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
23-16749 |  | 10/26/2023 07:00 | 06/01/2028 16:00 | VALHALLA: B-280 TERMINAL OF THE VALHALLA-CHELAN CO PUD 115KV FEEDER T1 | VALHALLA: CHELAN CO PUD 115KV FEEDER T1 | CI
24-09008 | 15780159 | 05/06/2024 18:00 | 05/15/2025 15:00 | ROCK CREEK: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1719
24-05901 | 15358908 | 10/01/2024 08:00 | 04/04/2025 16:00 | WAPA - TRACY: 500KV SHUNT CAPACITOR PT10A & PT10B | WAPA - TRACY: 500KV SHUNT CAPACITOR PT10A & PT10B | COI
24-17059 | 16817941 | 10/25/2024 01:00 | 06/30/2025 16:00 | WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 |  | NOH, WOCN
24-16049 | 16778210 | 11/07/2024 12:00 | 04/04/2025 17:00 | MCNARY: PCB A-408 | MCNARY PH-MCNARY NO 2 230KV LINE | WOM, GEN, FCRPS
25-00710 | 16840870 | 01/08/2025 06:00 | 04/29/2025 16:00 | OLYMPIA: PCB A-216 |  | NOEL, RP, SOC, WOCN
25-02670 |  | 01/09/2025 08:00 | 04/07/2025 16:00 | PGE- RIVERGATE: 230/115KV TRANSFORMER VWR1 |  | LOAD, SOA
25-00203 | 16814062 | 01/27/2025 08:00 | 04/21/2025 15:00 | DRISCOLL-KNAPPA SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE | DRISCOLL: PCB B-2061, DRISCOLL: PCB B-2067
25-04018 |  | 01/27/2025 08:00 | 04/21/2025 15:00 | CLATSOP: 230/115KV TRANSFORMER 1 |  | LOAD, SOA, NOPE
25-00431 | 16923560 | 02/10/2025 07:00 | 04/03/2025 15:00 | -USBR- HUNGRY HORSE: PCBS 2182 AND 2382 | HUNGRY HORSE PH: PCB 2182, HUNGRY HORSE PH: PCB 2382 | WOH, FLAT
25-02902 | 17231404 | 02/10/2025 07:30 | 04/30/2025 16:00 | COBURG EWEB: 115KV MAIN BUS | COBURG (EWEB)-MCKENZIE (EWEB) 115KV LINE, COBURG (EWEB)-SPRING CREEK (EWEB) 115KV LINE | EWEB
25-01945 |  | 02/24/2025 07:00 | 05/02/2025 17:00 | MIDPOINT (IPC)-HEMINGWAY 500KV LINE |  | ID-NW, NWACI
25-00087 |  | 02/24/2025 18:00 | 08/20/2025 16:30 | PONDEROSA: 230KV NON-GIS NORTH BUS FROM REMOVED BUS SECTION EAST OF A-1811 DISC TO REMOVED JUMPERS FROM PCB A-1844 BUSHINGS TO A-1840 DISCONNECT INCLUDING A-1840 DISCONNECT
25-00120 | 15576631 | 02/27/2025 08:00 | 04/24/2025 08:00 | JOHN DAY: MOD 4169 | JOHN DAY: PCB 4170 | NWACI, WOCS, WOJD, PDCI
25-04200 |  | 03/03/2025 07:00 | 04/10/2025 16:00 | BROADVIEW SWITCHYARD (NWE)-COLSTRIP B 500KV LINE |  | MT-NW, GEN, STCON
25-02242 |  | 03/03/2025 07:00 | 05/04/2025 18:00 | SCL-BOTHELL: PCB 240-72 |  | SOC, NOEL
25-00245 |  | 03/10/2025 13:00 | 04/17/2025 15:00 | FRANKLIN: WEST 115 KV AUX BUS
25-00067 | 16712313 | 03/10/2025 15:00 | 05/30/2025 15:00 | MALIN: PG&E ROUND MOUNTAIN 1 500KV LINE SERIES CAP GROUP |  | COI
25-00689 |  | 03/10/2025 16:01 | 04/18/2025 07:30 | MIDWAY: PCB A-1000 INCLUDING L/S DISC AND LINE DROP | MIDWAY: PCB A-1000, MIDWAY: A-1000 LINE SIDE DISC | WOM
25-03387 | 17268155 | 03/17/2025 11:00 | 04/30/2025 14:00 | ANDERSON RANCH-MOUNTAIN HOME NO 1 115KV LINE INCLUDING DIXIE TAP AND MOUNTAIN HOME: 138/115KV TRANSFORMER 1 AND DIXIE: 115/24.9KV TRANSFORMER 1 | DIXIE: IDAHO POWER CO 24.9KV FEEDER 1, DIXIE: 115/24.9KV TRANSFORMER 1, MOUNTAIN HOME: 138/115KV TRANSFORMER 1, DIXIE TAP TO ANDERSON RANCH-MOUNTAIN HOME NO 1 115KV LINE, ANDERSON RANCH-MOUNTAIN HOME NO 1 115KV LINE | GEN
25-00070 | 16771698 | 03/20/2025 08:00 | 04/17/2025 15:00 | MALIN-ROUND MOUNTAIN NO 1 500KV LINE INCLUDING THE PG&E ROUND MOUNTAIN 500KV SERIES CAP GROUP | MALIN-ROUND MOUNTAIN NO 1 500KV LINE, MALIN: PG&E ROUND MOUNTAIN 1 500KV LINE SERIES CAP GROUP | BCHT, BCHW, NI, COI
25-01420 |  | 03/21/2025 15:00 | 04/17/2025 15:00 | ALVEY: PCB B-582 INCLUDING B-582 L/S AND A/B DISCS | ALVEY: PCB B-582
25-00123 | 16957134 | 03/24/2025 08:00 | 04/03/2025 15:00 | KEELER: 230KV SVC INCLUDING PCB A-897 | KEELER: PCB A-897, KEELER: 20KV PCB L-1675, KEELER: 230/20KV TRANSFORMER 4, KEELER: 230KV SVC | SOA, NOPE, LOAD, WOCS
25-01081 |  | 03/25/2025 08:00 | 04/11/2025 15:00 | ST JOHNS: ROSS-ST JOHNS NO 1 230KV LINE INCLUDING 230/115KV TRANSFORMER BANK 1 , 115KV AUX BUS, PCB'S B-34 AND B-80 AND 115/57KV TRANSFORMER BANK NO 5 | ROSS-ST JOHNS NO 1 230KV LINE, ST. JOHNS: 230/115KV TRANSFORMER 1, ST JOHNS: 115KV AUX BUS, ST JOHNS: PCB B-34, ST JOHNS: PCB B-80, ST. JOHNS: 115/57KV TRANSFORMER 5, ST JOHNS: PACIFICORP (PACW) 57KV FEEDER 1 TO KNOTT, ST JOHNS: PCB B-48 | LOAD, SOA, NOPE
24-15803 | 17043401 | 03/28/2025 07:00 | 04/03/2025 16:00 | OLYMPIA: 230KV WEST MAIN BUS PT'S | OLYMPIA: 230KV EAST SECTION OF WEST MAIN BUS, OLYMPIA-SHELTON NO 4 230KV LINE, OLYMPIA: 230KV CAP GROUP 2 SECTION 1, OLYMPIA: 230KV CAP GROUP 2 SECTION 2, OLYMPIA: PCB A-208, OLYMPIA: PCB A-210, OLYMPIA: PCB A-212, OLYMPIA: 230/115KV TRANSFORMER 2, OLYMPIA: LBD A-223, OLYMPIA: LBD A-225 | LOAD, PA, RP, SOA, NOPE, NOEL, SOC, WOCN
25-01488 | 17075233 | 03/31/2025 06:00 | 04/03/2025 15:00 | MINIDOKA PH: 138KV MAIN BUS |  | GEN
25-00976 | 16898377 | 03/31/2025 07:00 | 04/01/2025 16:00 | ASHE: 500KV REACTOR 1, INCLUDING PCB 4907 | ASHE: PCB 4907, ASHE: 500KV REACTOR 1 | FCRPS, NOH, NWACI
25-03545 | 17319946 | 03/31/2025 07:00 | 04/07/2025 15:00 | EAST OMAK-PINECREEK SECTION OF EAST OMAK-OROVILLE NO 1 115KV LINE | EAST OMAK: PCB B-72
25-00727 | 16807512 | 03/31/2025 08:00 | 04/17/2025 17:00 | PONDEROSA: 500/230KV TRANSFORMER 1, INCLUDING PCBs 4618, A-398 AND A-384 | PONDEROSA: PCB 4618 | NWACI, COR
25-04272 |  | 03/31/2025 08:00 | 04/06/2025 20:00 | SCL-MASSACHUSETTS-UNION-BROAD ST 115KV LINE, MASS-UNION 2 115KV LINE |  | SOC, NOEL
25-00266 | 17035415 | 03/31/2025 08:00 | 04/25/2025 15:00 | RUPPERT RD-HORN RAPIDS SECTION INCLUDING HORN RAPIDS TAP OF THE RED MOUNTAIN-WHITE BLUFFS #1 115KV LINE | HORN RAPIDS TAP TO RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE, RUPPERT ROAD-HORN RAPIDS SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE, HORN RAPIDS-WHITE BLUFFS SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE | TCLA, LOAD
25-02946 | 17251788 | 03/31/2025 09:00 | 04/03/2025 12:00 | TAHKENITCH: 115KV MAIN BUS INCLUDING PCB'S: B-1562, B-1566, B-1568, B-1570, B-1572 AND B-1574 | TAHKENITCH: PCB B-1562, TAHKENITCH: PCB B-1566, TAHKENITCH: PCB B-1568, TAHKENITCH: PCB B-1570, TAHKENITCH: PCB B-1572, TAHKENITCH: PCB B-1574, TAHKENITCH: PCB B-1569, WENDSON-TAHKENITCH NO 2 230KV LINE, TAHKENITCH: 115KV CAP GROUP 1 SECTION 1, TAHKENITCH: 115KV CAP GROUP 1 SECTION 2, TAHKENITCH-REEDSPORT NO 1 115KV LINE, WENDSON: PCB A-1581, TAHKENITCH: 115KV MAIN BUS | LOAD, SCORC
25-03056 | 17251510 | 03/31/2025 10:00 | 04/03/2025 13:00 | TAHKENITCH: 230/115KV TRANSFORMER 1 | TAHKENITCH: 13.8KV/240V/120V 3-PH STATION SERVICE TRANSFORMER | LOAD, SCORC
25-00387 | 16381454 | 04/01/2025 07:00 | 04/01/2025 19:00 | PAUL: 500KV SOUTH BUS INCLUDING PCBS 4530, 4540, 4548 AND 4810 | PAUL: 500KV SOUTH BUS, PAUL: PCB 4530, PAUL: PCB 4540, PAUL: PCB 4548, PAUL: PCB 4810 | RP, GEN, WOCS, SOA, NOPE, PA
25-01332 | 17041377 | 04/01/2025 07:00 | 04/01/2025 17:00 | COLUMBIA: 115KV NORTH MAIN BUS INCLUDING PCBS B-412 AND B-314 | COLUMBIA: 115KV NORTH MAIN BUS, COLUMBIA: PCB B-412, COLUMBIA: PCB B-314, COLUMBIA-VALHALLA NO 2 115KV LINE, COLUMBIA: 230/115KV TRANSFORMER 2 | CI, NOH, LOAD, WOCN
25-02844 |  | 04/01/2025 07:30 | 04/10/2025 17:00 | ALVEY: PCB A-654 INCLUDING A-654 M/B & A/B DISC'S | ALVEY: PCB A-654 | EWEB, NWACI
25-00701 | 16808397 | 04/01/2025 07:30 | 04/10/2025 17:00 | ALVEY: 500/230KV TRANSFORMER 5, INCLUDING 500/230KV TIE LINE NO 1 500KV LINE, 500KV SOUTH BUS, 34.5KV TERTIARY BUS, PCBs 5091, 5087, AND A-654 | ALVEY 500/230KV TIE LINE NO 1 500KV LINE, ALVEY: PCB 5091, ALVEY: PCB 5087, ALVEY: PCB A-654, ALVEY: 500KV SOUTH BUS | NWACI, EWEB
25-01365 | 17030311 | 04/01/2025 07:30 | 06/13/2025 16:00 | ALCOA: B-230 TERMINAL OF PIONEER-ALCOA NO 1 115KV LINE | FELIDA-SW48 SECTION OF PIONEER-ALCOA NO 1 115KV LINE, SW48-ALCOA SECTION OF PIONEER-ALCOA NO 1 115KV LINE | LOAD
25-01292 | 16984484 | 04/01/2025 08:00 | 04/01/2025 11:30 | CHIEF JOSEPH: PCB 4598 |  | NOEL, SOC, WOCN, NOH
25-03408 | 17269286 | 04/01/2025 08:00 | 04/03/2025 15:00 | NASELLE-HAGEN SECTION OF NASELLE-TARLETT NO 2 115KV LINE
25-00882 | 16834152 | 04/01/2025 10:00 | 04/01/2025 10:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
25-01293 | 16984525 | 04/01/2025 11:30 | 04/01/2025 16:30 | CHIEF JOSEPH: PCB 4594 |  | NOEL, SOC, WOCN, NOH
25-00883 | 16834165 | 04/01/2025 14:15 | 04/01/2025 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
25-00977 | 16898384 | 04/02/2025 07:00 | 04/03/2025 16:00 | ASHE: 500KV REACTOR 2, INCLUDING PCB 4909 | ASHE: PCB 4909, ASHE: 500KV REACTOR 2 | FCRPS, NOH, NWACI
25-00364 | 16976996 | 04/02/2025 08:00 | 04/02/2025 16:00 | SATSOP: PCB A-630 BFR | SATSOP: PCB A-630 | GEN, LOAD
25-00968 | 16977017 | 04/02/2025 14:00 | 04/02/2025 15:00 | SATSOP: PCB A-625 |  | GEN, LOAD
25-00712 | 16807884 | 04/03/2025 07:00 | 04/03/2025 15:00 | MURRAY: PCB A-1516 BFR | MURRAY: PCB A-1516 | BCHT, BCHW, NOEL, SOC
25-02988 |  | 04/03/2025 08:00 | 04/03/2025 15:00 | BIG EDDY: PCB A-818 INCLUDING 230KV CAP GROUP 2 SECTION 1 | BIG EDDY: 230KV CAP GROUP 2 SECTION 1, BIG EDDY: PCB A-816 | PDCI, NWACI, COI, WOJD
25-00484 | 16463602 | 04/04/2025 22:30 | 04/04/2025 23:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-00058 | 14840027 | 04/05/2025 08:00 | 04/06/2025 18:00 | RAS - DITTMER: RAS AC-A CONTROLLER, MUNRO: RAS AC-B CONTROLLER, RAS SYNCHROPHASOR-A CONTROLLER, RAS SYNCHROPHASOR-B CONTROLLER, MALIN FACRI A AND B | MUNRO: RAS AC-B CONTROLLER, DITTMER: RAS AC-A CONTROLLER, DITTMER: RAS SYNCHROPHASOR-A CONTROLLER, MUNRO: RAS SYNCHROPHASOR-B CONTROLLER | SIG, COI, NOH, NWACI, PDCI, WOM, WOS, NI, WOJD, WOLM
25-00461 | 16592355 | 04/07/2025 06:00 | 04/25/2025 17:00 | RAVER-COVINGTON NO 1 500KV LINE INCLUDING COVINGTON: 500/230KV TRANSFORMER 4 AND 34.5KV BANK 4 STATION SERVICE RACK, PCB A-850 AND 230KV AUX BUS SECTION 3 | COVINGTON: 230KV AUX BUS SECTION 3, COVINGTON: 500/230KV TRANSFORMER 4, RAVER-COVINGTON NO 1 500KV LINE, COVINGTON: PCB A-850, RAVER: PCB 4302, RAVER: PCB 4299, COVINGTON: PCB L-1901, COVINGTON: PCB L-1902, COVINGTON SUBSTATION TIE NO 1 230KV LINE | NOEL, RP, SIG, SOC, NI, WOCN, IROL
25-00460 | 17368003 | 04/07/2025 06:30 | 04/10/2025 17:30 | COVINGTON: 230KV MAIN BUS SECTION 3 | TACOMA-COVINGTON NO 4 230KV LINE, TACOMA-COVINGTON NO 3 230KV LINE, COVINGTON-BETTAS ROAD NO 1 230KV LINE, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 1, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 2, COVINGTON: 230KV REACTIVE GROUP 1 CAP SECTION 3, COVINGTON: 230KV REACTIVE GROUP 1 REACTOR 1 | NOEL, SOC, WOCN, RP, IROL, LOAD
25-00388 | 16381475 | 04/07/2025 07:00 | 04/08/2025 17:00 | PAUL: PCB 4818 |  | PA, RP
25-00551 | 16599564 | 04/07/2025 07:00 | 04/10/2025 14:00 | GARRISON: PCB 4418, PCB 4415, MOD 4416, MOD 4417, TAFT 1 500KV SERIES CAP GROUP 1, PCB 4461 CONTROL & ALARM CIRCUITS (FORCES OUT GARRISON-TAFT NO 1 500KV LINE) | GARRISON: PCB 4418, TAFT: PCB 4114, TAFT: PCB 4119, GARRISON: PCB 4415, GARRISON: HSGS 7885, GARRISON: PCB 4461, GARRISON-TAFT NO 1 500KV LINE, GARRISON: TAFT 1 500KV LINE SERIES CAP GROUP 1 | MT-NW, WOH, SIG
25-00754 | 17067885 | 04/07/2025 07:00 | 04/11/2025 17:00 | SPAR CANYON-ROUND VALLEY NO 1 230KV LINE | ROUND VALLEY: SALMON RIVER COOP 69KV FEEDER 1, ROUND VALLEY: 230/69KV TRANSFORMER 1
25-00979 | 16956885 | 04/07/2025 07:00 | 04/08/2025 16:00 | ASHE: PCB 4940 |  | NWACI, WOCS, WOJD, WOM, FCRPS
25-00261 | 16771750 | 04/07/2025 07:00 | 04/09/2025 16:00 | CAPTAIN JACK-MALIN NO 1 500KV LINE INCLUDING CAPTAIN JACK: PCB'S 4993, 4996; MALIN: 500 KV REACTOR 1 AND PCB'S 4327, 4064, 4066 | CAPTAIN JACK: PCB 4993, CAPTAIN JACK: PCB 4996, MALIN: PCB 4064, MALIN: PCB 4066, MALIN: 500KV REACTOR 1, MALIN: PCB 4327, CAPTAIN JACK-MALIN NO 1 500KV LINE | NWACI, COI, SIG
25-00129 | 17042845 | 04/07/2025 07:00 | 04/07/2025 15:00 | BELL: 230KV MAIN BUS SECT 0 INCLUDING 230KV MAIN BUS RING SECTION AND PCB'S A-362, A-375 AND A-377 | BELL: 230KV MAIN BUS SECTION 0, BELL: 230KV MAIN BUS RING SECTION, BELL: PCB A-362, BELL: PCB A-375, BELL: PCB A-377 | MT-NW, WOH
25-00789 | 17035549 | 04/07/2025 07:30 | 04/17/2025 15:00 | LONGVIEW: 230/115KV TRANSFORMER 3 | LONGVIEW: PCB A-106, LONGVIEW: PCB B-328 | SOA, LOAD, NOPE
25-00108 | 15543301 | 04/07/2025 08:00 | 04/10/2025 15:00 | KEELER: 230KV REACTIVE GROUP 2 REACTOR 1 | KEELER: PCB A-873 | SOA, NOPE
25-00175 | 16018275 | 04/07/2025 08:00 | 04/17/2025 16:30 | MAUPIN-REDMOND NO 1 230KV LINE |  | COR, NOH
25-00230 | 16295292 | 04/07/2025 08:00 | 04/08/2025 16:00 | KNIGHT: 500 KV EAST BUS INCLUDING PCB's 5471, 5483, 5489 | KNIGHT: PCB 5471, KNIGHT: 500KV EAST BUS, KNIGHT: PCB 5483, KNIGHT: PCB 5489 | WOCS, WOJD, WOCN, NOH, PDCI
25-04199 | 17333012 | 04/07/2025 08:00 | 04/11/2025 15:00 | ASHE: REACTOR 2 INCLUDING PCB 4909 | ASHE: 500KV REACTOR 2, ASHE: PCB 4909 | NWACI, FCRPS, NOH
25-03003 | 17251968 | 04/07/2025 08:00 | 04/08/2025 15:00 | HOLCOMB-RAYMOND SECTION OF CHEHALIS-RAYMOND NO 1 115KV LINE |  | LOAD
24-00248 | 13990438 | 04/08/2025 08:00 | 04/08/2025 16:00 | TUMBLE CREEK-SANTIAM SECTION OF JONES CANYON-SANTIAM NO. 1 230KV LINE INCLUDING SANTIAM: 230KV AUX BUS AND PCB A-528 | TUMBLE CREEK-SANTIAM SECTION OF JONES CANYON-SANTIAM NO 1 230KV LINE, SANTIAM: 230KV AUX BUS, SANTIAM: PCB A-528, SANTIAM: PCB A-530 | GEN, WOCS, WOM, SLAL, SCORC, NWACI
25-01470 |  | 04/08/2025 08:00 | 04/08/2025 17:00 | ALFALFA: PCB A-1272 INCLUDING 230/34.5KV BANK 1 | ALFALFA: YAKAMA POWER 34.5KV FEEDER 1, ALFALFA: YAKAMA POWER 34.5KV FEEDER 2
25-04030 | 17318690 | 04/08/2025 08:00 | 04/08/2025 16:00 | KERR: PCB B-600 | ELMO-KERR SECTION OF KALISPELL-KERR NO 1 115KV LINE | GEN, LOAD, FLAT, MT-NW
25-04032 | 17318727 | 04/08/2025 08:00 | 04/08/2025 12:30 | KALISPELL: PCB B-1264
25-01211 | 17268802 | 04/08/2025 08:00 | 04/24/2025 15:00 | PEARL: 230KV CAP GROUP NO. 2 INCLUDING PCB A-1170 | PEARL: PCB A-1170, PEARL: 230KV CAP GROUP 2 | SOA, NOPE, WOCS
25-04023 |  | 04/08/2025 08:00 | 04/08/2025 16:00 | KERR: KALISPELL NO 1 115KV LINE TRANSFER TRIP
25-00619 | 16689703 | 04/08/2025 10:00 | 04/08/2025 10:15 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-01302 | 16997486 | 04/08/2025 12:00 | 04/08/2025 16:30 | CHIEF JOSEPH: PCB A-586 |  | WOCN, NOH
25-03905 |  | 04/08/2025 12:00 | 04/08/2025 15:00 | FOSSIL: 69KV PCB L-1376 | FOSSIL-MUDDY RANCH SECTION OF FOSSIL-MAUPIN 69KV LINE
25-04033 |  | 04/08/2025 12:30 | 04/08/2025 16:30 | KALISPELL: PCB B-1256 | KALISPELL: 115KV AUX BUS
25-00620 | 16689737 | 04/08/2025 14:15 | 04/08/2025 14:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-00980 | 16956891 | 04/09/2025 07:00 | 04/10/2025 16:00 | ASHE: PCB 4937 |  | NOH, NWACI, FCRPS
25-00389 | 16381491 | 04/09/2025 07:00 | 04/10/2025 17:00 | PAUL: PCB 4808 INCLUDING 500KV REACTOR NO 1 | PAUL: PCB 4808, PAUL: 500KV REACTOR 1
25-02051 | 17251876 | 04/09/2025 07:00 | 04/09/2025 14:00 | SHELTON: PCB A-1757 AND A-1754 | SATSOP-SHELTON NO 1 230KV LINE | LOAD, SI
25-03863 | 17304307 | 04/09/2025 08:00 | 04/10/2025 15:00 | OLYMPIA: PCB B-671 RELAY, CONTROL, AND ALARM CIRCUITS | OLYMPIA: PCB B-671
25-00231 | 16295333 | 04/09/2025 08:00 | 04/10/2025 16:00 | KNIGHT: 500KV WEST BUS INCLUDING PCBs 5474, 5486, 5492 | KNIGHT: PCB 5474, KNIGHT: PCB 5486, KNIGHT: PCB 5492, KNIGHT: 500KV WEST BUS | WOCS, WOJD, WOCN, NOH, PDCI
25-02801 | 17252166 | 04/10/2025 07:00 | 04/10/2025 09:00 | LEXINGTON: PCB B-1471
25-02416 | 17195774 | 04/10/2025 08:00 | 04/10/2025 15:00 | HAT ROCK: 230/115KV TRANSFORMER 1 INCLUDING PCB A-1490 AND PCB B-31 | HAT ROCK: UMATILLA E COOP 115KV FEEDER 1 BY PACIFICORP (PACW), HAT ROCK: PCB A-1490, HAT ROCK: PCB B-31, HAT ROCK: 230/115KV TRANSFORMER 1, HAT ROCK: 230KV MAIN BUS, HAT ROCK: 230KV AUX BUS, HAT ROCK: 115KV MAIN BUS, HAT ROCK: 115KV AUX BUS | WOM, LOAD
25-02804 | 17252171 | 04/10/2025 11:00 | 04/10/2025 13:00 | LEXINGTON: PCB A-449
25-01306 |  | 04/10/2025 12:00 | 04/10/2025 16:30 | CHIEF JOSEPH: PCB A-584 INCLUDING 230KV AUX BUS SECTION 1 | CHIEF JOSEPH: PCB A-584, CHIEF JOSEPH: 230KV AUX BUS SECTION 1
25-03906 | 17304494 | 04/10/2025 12:00 | 04/10/2025 15:00 | HOOD RIVER: PCB B-1679 | CASCADE LOCKS-HOOD RIVER SECTION OF BONNEVILLE PH 1-HOOD RIVER NO 1 115KV LINE | GEN
25-04101 |  | 04/11/2025 08:00 | 04/14/2025 18:00 | DENNY (SCL)-BROAD ST 115KV LINE |  | NOEL, SOC
25-01082 | 17256227 | 04/11/2025 15:00 | 04/11/2025 20:00 | ST JOHNS: 115KV MAIN BUS INCLUDING PCB'S B-80, B-34 AND 115KV AUX BUS | ST. JOHNS: 230/115KV TRANSFORMER 1, ST. JOHNS: 115/57KV TRANSFORMER 5, ROSS-ST JOHNS NO 1 230KV LINE, ST JOHNS-KEELER NO 2 115KV LINE, ST JOHNS-PACW ST JOHNS NO 1 115KV LINE, ST JOHNS: PCB B-34, ST JOHNS: PCB B-40, ST JOHNS: PCB B-42, ST JOHNS: PCB B-44, ST JOHNS: PCB B-48, ST JOHNS: PCB B-80, ST JOHNS-DUTCH CANYON SECTION OF ST JOHNS-ST HELENS NO 1 115KV LINE, ST JOHNS: PACIFICORP (PACW) 57KV FEEDER 1 TO KNOTT | LOAD, SOA, NOPE
25-03487 | 17287064 | 04/11/2025 20:00 | 05/02/2025 15:00 | ROSS-ST JOHNS NO 1 230kV LINE INCLUDING ST JOHNS: 230/115KV TRANSFORMER 1 | ST. JOHNS: 230/115KV TRANSFORMER 1, ROSS-ST JOHNS NO 1 230KV LINE, ROSS: PCB A-32, ST JOHNS: PCB B-48 | LOAD, SOA, NOPE
25-00439 | 16413169 | 04/13/2025 08:00 | 04/18/2025 15:00 | GRAND COULEE: 230KV MAIN BUS SECTION 2B (FORCES OUT 500/230KV CSY TIE AND OLYMPIA-GRAND COULEE NO 1 287KV LINE) | GRAND COULEE: 500/230KV CSY TIE BANK, GRAND COULEE: PCB 1996, GRAND COULEE: PCB 8692 | GEN, NOH, SIG, FCRPS, WOCN
25-02243 |  | 04/14/2025 07:00 | 04/24/2025 18:00 | SCL-BOTHELL: 115KV BUS A | BOTHELL (SCL)-CANAL 115KV LINE, BOTHELL (SCL)-SHORELINE NO 1 115KV LINE, BOTHELL: 230/115KV TRANSFORMER 61 | NOEL, SOC, LOAD
25-04196 |  | 04/14/2025 07:00 | 05/22/2025 16:00 | BROADVIEW SWITCHYARD (NWE)-COLSTRIP A 500KV LINE |  | MT-NW, GEN, STCON
25-01049 | 16956898 | 04/14/2025 07:00 | 04/15/2025 16:00 | ASHE: PCB 4888 |  | GEN, NWACI, FCRPS
25-00553 | 16599565 | 04/14/2025 07:00 | 04/18/2025 14:00 | GARRISON: PCB-4409, PCB-4412, MOD-4410, MOD-4411, BROADVIEW #2 500KV SERIES CAPACITORS, 500 KV REACTOR #2 (FORCES OUT BROADVIEW-GARRISON #2 500KV LINE) | GARRISON: PCB 4409, GARRISON: PCB 4412, GARRISON: 500KV REACTOR 2, GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2, BROADVIEW-GARRISON NO 2 500KV LINE | MT-NW, GEN
25-04376 | 17339873 | 04/14/2025 07:00 | 05/30/2025 16:00 | OLYMPIA: 230/115KV TRANSFORMER 2 RELAYS INCLUDING PCB A-212 AND B-676 RELAYS | OLYMPIA: PCB A-212, OLYMPIA: PCB B-676, OLYMPIA: 230/115KV TRANSFORMER 2 | NOEL, RP, SOC, WOCN
25-00775 |  | 04/14/2025 07:00 | 05/01/2025 17:00 | NORTH BONNEVILLE: A-11 TERMINAL OF THE BONNEVILLE PH-NORTH BONNEVILLE NO 4 230KV LINE | BONNEVILLE PH 2-NORTH BONNEVILLE NO 4 230KV LINE, BONNEVILLE PH: 230/13.8KV BANK 12 | GEN, FCRPS, WOCS
25-03457 | 17292236 | 04/14/2025 07:30 | 04/17/2025 16:00 | LEXINGTON-PACIFIC WAY SECTION OF LEXINGTON-LONGVIEW NO 1 115KV LINE | LEXINGTON-PACIFIC WAY LOOP IN SECTION OF LEXINGTON-LONGVIEW NO 1 115KV LINE | LOAD, SOA, NOPE
25-02865 | 17263139 | 04/14/2025 08:00 | 04/14/2025 16:00 | ALLSTON: LONGVIEW NO 2 230KV LINE RELAYS | LONGVIEW-ALLSTON NO 2 230KV LINE, LONGVIEW: PCB A-104, LONGVIEW: PCB A-642, ALLSTON: PCB A-1356, ALLSTON: PCB A-1360 | SOA, NOPE
25-01308 | 17055364 | 04/14/2025 08:00 | 05/01/2025 16:30 | VANTAGE: 500/230KV TRANSFORMER 1, INCLUDING AUX BUS SECTION 2 |  | GEN, NOH, SIG, WI
25-00232 | 16295370 | 04/14/2025 08:00 | 04/14/2025 16:00 | BIG EDDY-KNIGHT 500 KV LINE INCLUDING PCBs 5471 AND 5474 | KNIGHT: MOD 5472, KNIGHT: MOD 5473, BIG EDDY-KNIGHT NO 1 500KV LINE | PDCI, SIG, WOCS, WOJD, BGEDY, NWACI
25-01317 | 17031281 | 04/14/2025 08:00 | 05/01/2025 15:00 | NORTH BONNEVILLE-ROSS NO 2 230KV LINE INCLUDING SIFTON TAP | ROSS: PCB A-22, NORTH BONNEVILLE: PCB A-14, SIFTON: PCB B-1511, SIFTON: 230KV WEST MAIN BUS, SIFTON: 230KV AUX BUS, SIFTON: 230/115KV TRANSFORMER 1, NORTH BONNEVILLE-ROSS NO 2 230KV LINE, SIFTON TAP TO NORTH BONNEVILLE-ROSS NO 2 230KV LINE | SOA, NOPE, WOCS, GEN, LOAD, FCRPS
25-01323 | 17031197 | 04/14/2025 08:00 | 05/01/2025 15:00 | NORTH BONNEVILLE-TROUTDALE NO 2 230KV LINE | TROUTDALE: PCB A-125, NORTH BONNEVILLE: PCB A-16 | GEN, LOAD, WOCS, FCRPS
24-07243 | 16556890 | 04/14/2025 08:00 | 04/18/2025 15:00 | HILLTOP: 230 KV CCVT 20H | HILLTOP: SOUTH BUS, HILLTOP: CCVT 20H, HILLTOP: PCB A-1534 | RATS, NWACI
25-01423 | 17043284 | 04/14/2025 08:00 | 04/24/2025 15:30 | FOREST GROVE: PCB B-1285 | FOREST GROVE: FOREST GROVE OR 115KV FEEDER 1 | SOA, LOAD, NOPE
25-01425 | 17114375 | 04/14/2025 08:00 | 04/17/2025 15:00 | MARION: 500KV REACTOR 1 INCLUDING PCB 4012 | MARION: 500KV REACTOR 1, MARION: PCB 4012 | NWACI
25-01655 | 17326446 | 04/14/2025 08:30 | 04/17/2025 15:00 | LAPINE: 115KV CAP GROUP 1 RELAYS | LAPINE: PCB B-1275, LAPINE: 115KV CAP GROUP 1 | COR, GRZN
25-00390 | 16381524 | 04/15/2025 07:00 | 04/17/2025 16:00 | PAUL: PCB 4550 |  | WOCS, SOA, NOPE
25-02704 | 17263163 | 04/15/2025 07:00 | 04/15/2025 09:00 | COLVILLE: 115KV CAP GROUP 1 SECTIONS 1, 2, & 3 INCLUDING PCB'S B-1769, B-1771, B-1773, & B-1780 | COLVILLE: 115KV CAP GROUP 1 SECTION 1, COLVILLE: 115KV CAP GROUP 1 SECTION 2, COLVILLE: 115KV CAP GROUP 1 SECTION 3, COLVILLE: PCB B-1769, COLVILLE: PCB B-1771, COLVILLE: PCB B-1773, COLVILLE: PCB B-1780
25-02868 | 17257859 | 04/15/2025 08:00 | 04/15/2025 16:00 | ALLSTON: LONGVIEW NO 3 230KV LINE RELAYS | LONGVIEW-ALLSTON NO 3 230KV LINE, LONGVIEW: PCB A-1386, LONGVIEW: PCB A-1378, ALLSTON: PCB A-1357, ALLSTON: PCB A-1355 | SOA, NOPE
25-03627 | 17293998 | 04/15/2025 08:00 | 04/16/2025 17:00 | BROADVIEW-GARRISON NO 2 500KV LINE | GARRISON: BROADVIEW 2 500KV LINE SERIES CAP GROUP 2 | MT-NW, GEN
25-03623 | 17293890 | 04/15/2025 08:00 | 04/16/2025 17:00 | BROADVIEW-GARRISON NO 1 500KV LINE | GARRISON: BROADVIEW 1 500KV LINE SERIES CAP GROUP 1 | MT-NW, GEN
25-00233 | 16295383 | 04/15/2025 08:00 | 04/15/2025 16:00 | KNIGHT-OSTRANDER #1 500 KV LINE INCLUDING KNIGHT: PCB's 5483 AND 5486 | KNIGHT-OSTRANDER NO 1 500KV LINE, KNIGHT: PCB 5486, KNIGHT: PCB 5483 | BCHT, BCHW, NI, SIG, WOCS, WOJD, WOCN, NOH, PDCI
25-00887 | 16834192 | 04/15/2025 10:00 | 04/15/2025 10:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-02705 | 17263173 | 04/15/2025 10:00 | 04/15/2025 11:00 | ADDY: 230KV CAP GROUP 1 INCLUDING PCB A-147 | ADDY: 230KV CAP GROUP 1, ADDY: PCB A-147 | SOB
25-02786 | 17263203 | 04/15/2025 12:00 | 04/15/2025 15:00 | DEER PARK: 115KV CAP GROUP 1 INCLUDING PCB B-1913 | DEER PARK: 115KV CAP GROUP 1, DEER PARK: PCB B-1913
25-00889 | 16834214 | 04/15/2025 14:15 | 04/15/2025 14:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-01050 | 16956902 | 04/16/2025 07:00 | 04/17/2025 16:00 | ASHE: PCB 4885 |  | GEN, NWACI, FCRPS
25-02790 | 17219317 | 04/16/2025 07:00 | 04/16/2025 12:00 | BELL: TAFT 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5320 | BELL: TAFT 1 500KV LINE SERIES CAP GROUP 1, BELL: PCB 5320 | WOH, MT-NW
25-00234 | 16295352 | 04/16/2025 08:00 | 04/16/2025 16:00 | WAUTOMA-KNIGHT #1 500 KV LINE INCLUDING KNIGHT: PCBs 5492 AND 5489 | WAUTOMA-KNIGHT NO 1 500KV LINE, KNIGHT: PCB 5492, KNIGHT: PCB 5489 | BCHT, BCHW, NI, NOH, SIG, WOCN, WOCS, WOJD, PDCI
25-02793 | 17263234 | 04/16/2025 09:00 | 04/16/2025 12:00 | BELL: 230KV CAP GRP 10 SECTIONS 1 AND 2 INCLUDING LBD'S A-925, A-926 AND CAP GRP 10 REACTIVE BUS | BELL: 230KV CAP GROUP 10 SECTION 1, BELL: 230KV CAP GROUP 10 SECTION 2, BELL: LBD A-925, BELL: LBD A-926 | MT-NW, WOH
25-02795 | 17263210 | 04/16/2025 12:00 | 04/16/2025 14:00 | BELL: 230KV CAP GROUP 9 SECTIONS 1, 2, AND 3 INCLUDING PCB'S A-931, A-932, AND A-933 | BELL: 230KV CAP GROUP 9 SECTION 1, BELL: 230KV CAP GROUP 9 SECTION 2, BELL: 230KV CAP GROUP 9 SECTION 3, BELL: PCB A-931, BELL: PCB A-932, BELL: PCB A-933, BELL: PCB A-378 | MT-NW, WOH
25-02796 | 17262970 | 04/16/2025 14:00 | 04/16/2025 16:00 | BELL: 230KV CAP GROUP 1 | BELL: PCB A-556 | MT-NW, WOH
25-01127 | 17050250 | 04/17/2025 07:00 | 04/17/2025 17:00 | A-8-A-6 SECTION OF MIDWAY-HEW NO 2 230KV LINE |  | TCLA
25-00248 | 17043403 | 04/18/2025 07:00 | 04/24/2025 15:00 | FRANKLIN: 115KV AUX BUS INCLUDING PCB B-616 | FRANKLIN: 115KV AUX BUS, FRANKLIN: PCB B-616
25-00391 | 17094634 | 04/18/2025 07:30 | 05/09/2025 17:00 | MIDWAY-HEW NO 1 230kV LINE INCLUDING ASH TAP, ASH TAP-A6 SECTION OF MIDWAY-HEW NO 2 230KV LINE, -NEW- MIDWAY-ASHE NO 1 230KV LINE AND ASHE: PCB A-401 AND MIDWAY: -NEW-PCB A-1000 | MIDWAY-HEW NO 1 230KV LINE, ASHE TAP TO MIDWAY-HEW NO 2 230KV LINE, A-6-ASHE TAP SECTION OF MIDWAY-HEW NO 2 230KV LINE, ASHE: PCB A-401, MIDWAY: PCB A-1000, MIDWAY: PCB A-336 | GEN, TCLA, LOAD, NOH, WOM
25-04102 |  | 04/18/2025 08:00 | 04/18/2025 12:00 | BOTHELL (SCL)-CANAL 115KV LINE |  | NOEL, SOC
25-00345 | 16876726 | 04/21/2025 06:00 | 04/24/2025 16:00 | BELL: PCB B-348
25-01149 | 17190312 | 04/21/2025 07:00 | 04/30/2025 17:00 | SCOOTENEY TAP-BENTON SECTION OF MIDWAY-BENTON NO 1 115KV LINE |  | TCLA, GEN
25-03482 | 17287130 | 04/21/2025 07:00 | 04/21/2025 08:00 | BONNERS FERRY: 115KV CAP GROUP 1 INCLUDING PCB B-1776 | BONNERS FERRY: PCB B-1776, BONNERS FERRY: 115KV CAP GROUP 1
25-01051 | 16956906 | 04/21/2025 07:00 | 04/22/2025 16:00 | ASHE: PCB 5463 |  | NOH, NWACI, FCRPS
25-00557 | 16586529 | 04/21/2025 07:00 | 04/22/2025 14:00 | GARRISON : 500KV REACTOR #5 INCLUDING PCB 4362 | GARRISON: PCB 4362, GARRISON: 500KV REACTOR 5 | MT-NW
25-01551 | 17323949 | 04/21/2025 07:00 | 04/24/2025 15:00 | BADGER CANYON: PCB B-253
25-00702 |  | 04/21/2025 07:00 | 04/24/2025 16:00 | ALVEY: 230KV SOUTH MAIN BUS INCLUDING PCB'S A-246, A-241, A-475, A-236, A-476 AND 230KV REACTOR NO 1 | ALVEY: PCB A-246, ALVEY: PCB A-241, ALVEY: PCB A-236, ALVEY: PCB A-476, MARCOLA A500-ALVEY SECTION OF SANTIAM-ALVEY NO 1&2 230KV LINE, ALVEY: 230/115KV TRANSFORMER 3, ALVEY: 230KV REACTOR 1, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 1, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 2, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 3, ALVEY: 230KV SOUTH MAIN BUS | EWEB, NWACI, SLAL, SCORC, PDCI
25-04082 | 17330976 | 04/21/2025 08:00 | 04/24/2025 15:00 | ALBANY: 230/115KV TRANSFORMER 1 | A539-ALBANY SECTION OF SANTIAM-ALBANY NO 1 230KV LINE | SLAL
25-00926 | 17048280 | 04/21/2025 08:00 | 04/24/2025 17:00 | ALVEY: PCB'S A-332 & A-247 CONTROL AND ALARM CIRCUITS | ALVEY: PCB A-247, ALVEY: PCB A-332 | EWEB, NWACI
25-00951 | 16863161 | 04/21/2025 08:00 | 04/23/2025 15:00 | JOHN DAY: PCB 4822 BFR and PCB DIFF | JOHN DAY: PCB 4822 | JDAY, NWACI, PDCI, WOJD
25-03624 | 17293824 | 04/21/2025 08:00 | 10/06/2025 11:00 | CARDWELL: B-1540 TERMINAL OF CARDWELL-MEEKER 115KV LINE | CARDWELL-MEEKER 115KV LINE, CARDWELL: PCB B-1540 | LOAD, SOA, NOPE
25-03121 | 17256797 | 04/21/2025 08:00 | 04/27/2025 15:00 | PEARL: PCB 4280 |  | SOA, NOPE
25-00116 | 15755547 | 04/21/2025 08:00 | 04/25/2025 15:00 | TAFT-HOT SPRINGS N0 1 500KV LINE, INCLUDING TAFT: 500KV BUS 1 AND PCBS 4148, AND 4111 | TAFT-HOT SPRINGS NO 1 500KV LINE, TAFT: PCB 4148, TAFT: PCB 4111, TAFT: PCB 4122, HOT SPRINGS: 500/230KV TRANSFORMER 1, HOT SPRINGS: 500KV REACTOR 1, HOT SPRINGS: PCB 4478 | MT-NW, SIG, WOH, FLAT, GEN, NOH
24-06255 | 16557509 | 04/21/2025 08:00 | 04/25/2025 15:00 | HOT SPRINGS: 500/230KV TRANSFORMER 1 | HOT SPRINGS: PCB 4562, HOT SPRINGS: PCB A-1478, HOT SPRINGS: 34.5KV STATION SERVICE MAIN BUS DISC, TAFT-HOT SPRINGS NO 1 500KV LINE | MT-NW, WOH, FLAT, GEN, SIG
25-00503 | 16976449 | 04/21/2025 08:00 | 05/02/2025 16:00 | ALLSTON: 500/230KV TRANSFORMER 2 |  | SIG, SOA, NOPE
25-04149 | 17330973 | 04/21/2025 08:00 | 04/21/2025 10:00 | SANTIAM-ALBANY NO 1 230KV LINE INCLUDING SANTIAM: PACW-230/69KV TRANSFORMER NO 2 | SANTIAM: PCB A-514, SANTIAM: PACW 230/69KV TRANSFORMER 2, SANTIAM: 69KV PCB L-1114, SANTIAM-ALBANY NO 1 230KV LINE, ALBANY: PCB B-520, SANTIAM: PACIFICORP (PACW) 69KV FEEDER 1, SANTIAM: CONSUMERS POWER 69KV FEEDER 1 | SLAL, NWACI, SCORC
25-03484 | 17287137 | 04/21/2025 08:00 | 04/21/2025 09:00 | BONNERS FERRY: CAP GROUP 2 SECTION 1 INCLUDING PCB B-1777 | BONNERS FERRY: PCB B-1777, BONNERS FERRY: 115KV CAP GROUP 2 SECTION 1
24-06297 |  | 04/21/2025 08:00 | 04/25/2025 15:00 | HOT SPRINGS: A-1478 A/B AND T/S DISCONNECTS | HOT SPRINGS: PCB A-1478 | GEN, MT-NW
24-03229 | 15417738 | 04/21/2025 08:00 | 05/01/2025 15:00 | CONDON-FOSSIL SECTION OF DE MOSS-FOSSIL NO 1 115KV LINE |  | BGEDY
25-01241 |  | 04/21/2025 08:00 | 05/02/2025 16:00 | ALLSTON: A-1353 T/S & A/B DISCONNECTS
25-03485 | 17287539 | 04/21/2025 12:00 | 04/21/2025 14:00 | SAND CREEK: 115KV CAP GROUP 1 SECTIONS 1, 2 AND 3 INCLUDING LBD B-1364, LBD B-1365 AND PCB B-1369 AND 115KV REACTIVE BUS | SAND CREEK: LBD B-1364, SAND CREEK: LBD B-1365, SAND CREEK: LBD B-1369, SAND CREEK: 115KV CAP GROUP 1 SECTION 1, SAND CREEK: 115KV CAP GROUP 1 SECTION 2, SAND CREEK: 115KV CAP GROUP 1 SECTION 3
25-00523 | 17037065 | 04/22/2025 07:00 | 04/22/2025 11:00 | BONNERS FERRY: PCB 1776 INCLUDING 115KV CAP GROUP 1 | BONNERS FERRY: PCB B-1776, BONNERS FERRY: 115KV CAP GROUP 1
25-00734 | 16815366 | 04/22/2025 07:00 | 04/23/2025 17:00 | JOHN DAY: 500/230KV TRANSFORMER 1 INCLUDING SPARE PHASE, 34.5KV/480V STATION SERVICE TRANSFORMER, PCB'S 4822, 4825, A-1725 & A-1728 | JOHN DAY: PCB A-1725, JOHN DAY: PCB A-1728, JOHN DAY: 500/230KV TRANSFORMER 1 | GEN, JDAY, WOJD, NWACI
25-03998 | 17337889 | 04/22/2025 07:00 | 04/23/2025 15:00 | HOT SPRINGS-RATTLESNAKE NO 1 230KV LINE | DIXON: 230/69KV TRANSFORMER 1, DIXON: MISSION VLY POWER 69KV FEEDER 1 | MT-NW, FCRPS
25-03049 | 17287936 | 04/22/2025 07:00 | 04/22/2025 14:00 | GOSHEN: 161KV WEST MAIN BUS INCLUDING WEST MAIN BUS PT'S | GOSHEN-DRUMMOND NO 1 161KV LINE, CATTLE CREEK-GOSHEN NO 1 115KV LINE, GOSHEN: 161KV MAIN BUS | GEN, LOAD, SEIL
25-02924 |  | 04/22/2025 08:00 | 04/23/2025 14:00 | PACW: GOSHEN KINPORT 345KV LINE
25-00869 |  | 04/22/2025 08:00 | 04/23/2025 15:00 | JOHN DAY: PCB'S A-1725, A-1728 AND MOD'S A-1724, A-1726, A-1727 & A-1729
25-00204 | 17055249 | 04/22/2025 08:00 | 05/27/2025 15:00 | FERN HILL-ASTORIA SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE |  | SOA, NOPE
25-00621 | 16711042 | 04/22/2025 10:00 | 04/22/2025 10:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
25-03286 | 17262742 | 04/22/2025 11:00 | 04/22/2025 13:00 | CUSICK: 230KV CAP GROUP 1 |  | SOB
25-00622 | 16711046 | 04/22/2025 14:15 | 04/22/2025 14:30 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
25-01052 | 16956914 | 04/23/2025 07:00 | 04/24/2025 16:00 | ASHE: PCB 5466 |  | NWACI, WOJD, WOM, WOS, FCRPS
25-00558 | 16586556 | 04/23/2025 07:00 | 04/24/2025 14:00 | GARRISON : 500KV REACTOR #4 INCLUDING PCB-4457 | GARRISON: PCB 4457, GARRISON: 500KV REACTOR 4 | MT-NW
25-02317 | 17181445 | 04/23/2025 08:00 | 04/24/2025 15:30 | REDMOND: 230KV WEST AND CENTER MAIN BUSSES INCLUDING PCB'S A-262, A-252, A-254, A-256, A-258 AND A-259 | REDMOND: 230KV CENTER MAIN BUS, REDMOND: PCB A-262, REDMOND: PCB A-252, REDMOND: PCB A-254, REDMOND: PCB A-256, REDMOND: PCB A-258, REDMOND: PCB A-259, REDMOND: PCB A-260, REDMOND: 230/115KV TRANSFORMER 5, REDMOND: 230/69KV TRANSFORMER 1, REDMOND: 230/69KV TRANSFORMER 2, REDMOND: 69KV MAIN BUS, REDMOND: 69KV AUX BUS, REDMOND: 69KV PCB L-212, REDMOND: 69KV PCB L-214, REDMOND: 69KV PCB L-216, REDMOND: 69KV PCB L-218, REDMOND: 69KV GROUNDING TRANSFORMER M1, REDMOND: 69KV GROUNDING TRANSFORMER K1, REDMOND: CENTRAL ELEC COOP 69KV FEEDER 1, REDMOND: PACIFICORP (PACW) 69KV FEEDER 1, REDMOND: 230KV WEST MAIN BUS | COI, PDCI, COR, NWACI, GRZN
25-04085 | 17332068 | 04/24/2025 08:00 | 04/24/2025 15:00 | ALBANY: PCB B-526 | ALBANY: PCB B-522
25-00172 | 15959314 | 04/24/2025 08:00 | 04/24/2025 15:00 | JOHN DAY- MARION 1 500KV LINE INCLUDING PCB 4170 | JOHN DAY: PCB 4170, JOHN DAY: PCB 4167, MARION: PCB 4371, MARION: PCB 4368, JOHN DAY-MARION NO 1 500KV LINE | NWACI, WOCS, WOJD, PDCI, JDAY, SIG
25-04152 | 17330975 | 04/24/2025 14:00 | 04/24/2025 16:00 | SANTIAM-ALBANY NO 1 230KV LINE INCLUDING SANTIAM: PACW-230/69KV TRANSFORMER NO 2 | SANTIAM: PCB A-514, SANTIAM: PACW 230/69KV TRANSFORMER 2, SANTIAM: 69KV PCB L-1114, SANTIAM-ALBANY NO 1 230KV LINE, ALBANY: PCB B-520, SANTIAM: PACIFICORP (PACW) 69KV FEEDER 1, SANTIAM: CONSUMERS POWER 69KV FEEDER 1 | SLAL, NWACI, SCORC
25-00370 |  | 04/24/2025 16:00 | 06/05/2025 12:00 | FRANKLIN: 115 KV EAST AUX BUS
25-02244 |  | 04/25/2025 07:00 | 04/29/2025 18:00 | SCL-BOTHELL: 230KV BUS 3 | DIABLO (SCL)-BOTHELL NO 3 230KV LINE, BOTHELL-SNO-KING NO 1 230KV LINE, BOTHELL: 230/115KV TRANSFORMER 63 | NOEL, SOC, LOAD
24-00942 | 14512553 | 04/27/2025 22:00 | 04/27/2025 22:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-00433 | 16413680 | 04/28/2025 06:00 | 05/01/2025 17:00 | ECHO LAKE-MONROE NO 1 500KV LINE, INCLUDING SNO-KING TAP | SNO-KING-MONROE SECTION OF ECHO LAKE-MONROE NO 1 500KV LINE, ECHO LAKE-SNO-KING SECTION OF ECHO LAKE-MONROE NO 1 500KV LINE, SNO-KING TAP TO ECHO LAKE-MONROE NO 1 500KV LINE | IROL, NI, NOEL, SIG, SOC, WOCN, NOH, BCHT, BCHW
25-00101 |  | 04/28/2025 07:00 | 05/09/2025 14:00 | GARRISON: RAS WM-A CONTROLLER |  | MT-NW, GEN, SIG, WOH
25-00559 | 16586578 | 04/28/2025 07:00 | 04/29/2025 14:00 | GARRISON : 500KV REACTOR #3, INCLUDING PCB 4460 | GARRISON: PCB 4460, GARRISON: 500KV REACTOR 3 | MT-NW
25-01053 | 16956926 | 04/28/2025 07:00 | 04/29/2025 16:00 | ASHE: PCB 4901 |  | NWACI, FCRPS, NOH
25-02315 | 17181686 | 04/28/2025 08:00 | 05/01/2025 15:00 | PONDEROSA: PACW 230KV FEEDER 1 INCLUDING PONDEROSA: PCB'S A-384 & A-395 | PONDEROSA: PACIFICORP (PACW) 230KV FEEDER 1, PONDEROSA: 230KV GIS NORTH BUS SECTION, PONDEROSA: PCB A-384, PONDEROSA: PCB A-395 | LOAD, COR, NWACI
25-01078 |  | 04/28/2025 08:00 | 05/02/2025 16:00 | ALVEY: PCB A-652 AND 230/115KV TRANSFORMER 4 CONTROL AND ALARM CIRCUITS | ALVEY: 230/115KV TRANSFORMER 4, ALVEY: PCB A-652 | SCORC, EWEB, NWACI
25-00267 | 17035755 | 04/28/2025 08:00 | 04/29/2025 15:00 | RED MOUNTAIN-HORN RAPIDS SECTION INCLUDING RUPPERT RD TAP OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE | RED MOUNTAIN-RUPPERT ROAD SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE, RUPPERT ROAD TAP TO RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE, RUPPERT ROAD-HORN RAPIDS SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE | TCLA
25-00912 | 17042488 | 04/28/2025 08:00 | 05/01/2025 15:00 | CARLTON-TILLAMOOK NO 1 230KV LINE | TILLAMOOK: 230/115KV TRANSFORMER 2, TILLAMOOK: PCB B-1098, CARLTON: PCB A-315 | LOAD, SOA, NOPE, NWACI
25-00176 | 16227917 | 04/28/2025 08:00 | 05/08/2025 17:00 | PILOT BUTTE-LAPINE NO 1 230KV LINE | LAPINE: PCB A-1552 | COR, NWACI
25-00173 | 15958692 | 04/28/2025 08:00 | 04/28/2025 15:00 | ROCK CREEK-JOHN DAY NO 1 500KV LINE, INCLUDING JOHN DAY PCB 4194 | JOHN DAY: PCB 4194, JOHN DAY: MOD 4195 | BCHT, BCHW, NI, NOH, SIG, WOJD, WOM, NWACI, PDCI
25-04055 | 17319534 | 04/28/2025 08:00 | 05/08/2025 15:00 | JOHN DAY: PCB 4176 SEL BFR AND BREAKER DIFF | JOHN DAY: PCB 4176 | NWACI, WOJD, PDCI
25-00454 | 16834745 | 04/28/2025 08:00 | 05/23/2025 15:00 | MALIN: 500KV REACTOR 1 INCLUDING PCB 4327 | MALIN: PCB 4327, MALIN: 500KV REACTOR 1 | COI, NWACI
25-00957 | 16898684 | 04/28/2025 08:00 | 05/02/2025 15:00 | MARION-ALVEY NO 1 500KV LINE, INCLUDING, ALVEY: MARION 1 500KV LINE SERIES CAP GROUP 1 |  | BCHT, BCHW, NI, NWACI, SIG, EWEB
24-08699 | 15696119 | 04/28/2025 08:00 | 05/01/2025 15:00 | COLUMBIA FALLS: 230/115KV TRANSFORMER 3 |  | WOCN, FLAT
24-16020 | 17042709 | 04/28/2025 08:00 | 05/01/2025 16:00 | TILLAMOOK: 230/115KV TRANSFORMER 2 | TILLAMOOK: PCB B-1098 | LOAD, SOA, NOPE
25-00174 | 16024200 | 04/28/2025 17:00 | 06/18/2025 17:00 | JOHN DAY: MOD 4193 INCLUDING PCB 4194 | JOHN DAY: PCB 4194, JOHN DAY: MOD 4193 | NOH, NWACI, PDCI, WOJD
25-02940 | 17252260 | 04/29/2025 07:00 | 04/29/2025 15:30 | COVINGTON: PCB A-92 BFR | COVINGTON: PCB A-92 | BCHT, BCHW, NOEL, RP, SOC
25-03311 | 17263988 | 04/29/2025 08:00 | 05/01/2025 15:00 | OXBOW-NASELLE SECTION OF HOLCOMB-NASELLE NO 1 115KV LINE
25-01054 | 16956932 | 04/30/2025 07:00 | 05/01/2025 16:00 | ASHE: PCB 4898 |  | NWACI, FCRPS
25-02247 |  | 04/30/2025 07:00 | 05/04/2025 18:00 | SCL-BOTHELL: 230KV BUS 4 | BOTHELL: 230/115KV TRANSFORMER 64, SNOHOMISH-BOTHELL NO 2 230KV LINE | LOAD, NOEL, SOC
25-01827 | 17088312 | 04/30/2025 07:00 | 04/30/2025 15:00 | INTALCO: PCB A-1024 BFR | INTALCO: PCB A-1024
24-06657 | 17050055 | 04/30/2025 08:00 | 04/30/2025 15:00 | PEARL: 230KV EAST MAIN BUS INCLUDING PCB A-1192 | PEARL: PCB A-1192, PEARL: PCB A-1165, MCLOUGHLIN-SHERWOOD NO 1 230KV LINE, PEARL: PCB A-1169, PEARL: 500/230KV TRANSFORMER 1, PEARL: PCB A-1170, PEARL: 230KV CAP GROUP 2, PEARL: 230KV EAST MAIN BUS | SOA, NOPE, WOCS, LOAD, SIG
25-00268 | 17035760 | 04/30/2025 08:00 | 05/29/2025 15:00 | RED MOUNTAIN-RUPPERT ROAD SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE |  | TCLA