## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
1 | 23-04125 | 13016840 | 01/28/2023 17:00 | 09/30/2026 23:59 | ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV | ROCKY REACH: 345/230KV TRANSFORMER 1, ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV, MAPLE VALLEY: 345/230KV TRANSFORMER 1 | WOCN, SOC/NOEL, CI, GEN, IROL, NOEL, NOH, SOC
2 | 23-18445 | 14853282 | 12/14/2023 06:40 | 03/31/2025 16:00 | BCH - CHAPMAN: 5CX1 | BCH - CHAPMAN: 5CX1 | NI
3 | 24-08365 |  | 04/29/2024 08:00 | 05/30/2025 16:00 | MIDWAY: PCB A-1000 RELAYS, CONTROL AND INDICATION CIRCUITS | MIDWAY: PCB A-1000 | WOM
4 | 24-09008 | 15780159 | 05/06/2024 18:00 | 05/15/2025 15:00 | ROCK CREEK: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1719
5 | 24-05901 | 15358908 | 10/01/2024 08:00 | 02/28/2025 16:00 | WAPA - TRACY: 500KV SHUNT CAPACITOR PT10A & PT10B | WAPA - TRACY: 500KV SHUNT CAPACITOR PT10A & PT10B | COI
6 | 24-17059 | 16817941 | 10/25/2024 01:00 | 06/30/2025 16:00 | WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 |  | NOH, WOCN
7 | 24-17312 | 16800775 | 11/01/2024 00:01 | 03/31/2025 23:59 | LADWP - SYLMAR: PDCI SOUTH-NORTH LIMITATION |  | PDCI
8 | 24-18308 |  | 12/06/2024 21:00 | 04/15/2025 18:00 | LADWP- SYLMAR-KENTER ELECTRODE LINE 1 |  | PDCI
9 | 24-00128 | 14702032 | 01/06/2025 07:00 | 02/07/2025 15:00 | MCNARY-COYOTE SPRINGS NO 1 500KV LINE, INCLUDING NEW LONGHORN SUB | MCNARY: PCB 4231, MCNARY: PCB 4234, COYOTE SPRINGS: PCB 5184, COYOTE SPRINGS: PCB 5187 | SIG, WOM, WOJD, NWACI, WOLM
10 | 25-00706 | 16841248 | 01/08/2025 06:00 | 03/25/2025 15:00 | OLYMPIA-SATSOP NO 2 230KV LINE INCLUDING PCB A-222 | OLYMPIA-SATSOP NO 2 230KV LINE, OLYMPIA: PCB A-222 | LOAD, SI, RP, NOEL, SOC, WOCN
11 | 25-00854 | 16813120 | 01/13/2025 07:30 | 02/10/2025 15:30 | ROSS: 230KV CAP GROUP 2 SECTION 3 INCLUDING LBD A-27 | ROSS: LBD A-27, ROSS: 230KV CAP GROUP 2 SECTION 3 | SOA, NOPE
12 | 25-00952 | 16840544 | 01/27/2025 07:30 | 02/04/2025 16:30 | KEELER-OREGON CITY NO 2 115KV LINE | KEELER: PCB B-1080, OREGON CITY: PCB B-260 | LOAD, SOA, NOPE
13 | 25-00203 | 16814062 | 01/27/2025 08:00 | 04/21/2025 15:00 | DRISCOLL-KNAPPA SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE | DRISCOLL: PCB B-2061, DRISCOLL: PCB B-2067
14 | 25-00794 |  | 01/27/2025 08:00 | 03/28/2025 15:00 | BENTON-RINGOLD SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE | CONNELL-SCOOTENEY SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE | TCLA
15 | 25-00305 | 16814573 | 01/27/2025 08:00 | 02/07/2025 17:00 | BIG EDDY: THE DALLES PH-BIG EDDY NO. 3 230KV LINE INCLUDING BIG EDDY PCB A-812 AND THE 230KV A/B SECTION 1 | THE DALLES PH-BIG EDDY NO 3 230KV LINE, BIG EDDY: PCB A-812, BIG EDDY: PCB A-696 | GEN, FCRPS, PDCI, WOJD, NWACI, COI
16 | 25-01370 |  | 01/27/2025 08:00 | 02/14/2025 15:00 | -PGE- SHERWOOD: 230KV BUS V63 |  | SOA, NOPE, LOAD
17 | 25-00749 | 16738180 | 02/02/2025 06:00 | 02/02/2025 07:00 | MALIN: PCB 4072, MALIN: PCB 4582 |  | NWACI, COI
18 | 25-00748 |  | 02/03/2025 06:00 | 02/07/2025 17:30 | PG&E - MALIN-ROUND MOUNTAIN 2 500KV LINE | MALIN-ROUND MOUNTAIN NO 2 500KV LINE | BCHT, BCHW, NI, COI
19 | 25-01405 |  | 02/03/2025 07:00 | 02/28/2025 17:00 | BONNEVILLE-ACTON SECTION OF BONNEVILLE PH-HOOD RIVER NO.1 115KV LINE INCLUDING BONNEVILLE PH 115KV SOUTH M/B AND 115KV A/B | BONNEVILLE-ACTON SECTION OF BONNEVILLE PH 1-HOOD RIVER NO 1 115KV LINE, BONNEVILLE PH: 115KV AUX BUS, BONNEVILLE PH: 115KV SOUTH MAIN BUS, BONNEVILLE PH: PCB XW151 | GEN, FCRPS, LOAD
20 | 25-00770 | 16821715 | 02/03/2025 07:00 | 02/28/2025 14:00 | LIBBY: PCB A-1589 |  | MT-NW
21 | 24-11187 | 16073026 | 02/03/2025 07:00 | 02/14/2025 16:00 | CUSTER: 4276 BFR | CUSTER: PCB 4276 | BCHT, BCHW, NOEL, SOC, NI
22 | 25-01469 |  | 02/03/2025 07:00 | 02/28/2025 17:00 | ACTON: B-1177 TERMINAL OF BONNEVILLE PH-HOOD RIVER NO.1 115KV LINE | BONNEVILLE-ACTON SECTION OF BONNEVILLE PH 1-HOOD RIVER NO 1 115KV LINE | GEN
23 | 25-00795 | 16842218 | 02/03/2025 07:00 | 02/13/2025 15:00 | NINE MILE-WALLA WALLA SECTION OF FRANKLIN-WALLA WALLA NO 1 115KV LINE |  | GEN, TCLA, WAWA
24 | 25-01465 |  | 02/03/2025 08:00 | 02/06/2025 18:00 | SCL- BOTHELL: PCB 120-13 |  | SOC, NOEL
25 | 25-00378 | 16332398 | 02/03/2025 08:00 | 02/05/2025 15:00 | HANFORD: PCB 4107 |  | NOH, WOM, WOS
26 | 24-15046 | 16883203 | 02/03/2025 08:00 | 02/04/2025 15:00 | CARLTON: 115KV MAIN BUS | CARLTON-MCMINNVILLE NO 1 115KV LINE, FOREST GROVE-MCMINNVILLE NO 1 115KV LINE, CARLTON: 230/115KV TRANSFORMER 1 | LOAD, SOA, NOPE
27 | 25-01355 | 17030940 | 02/03/2025 08:00 | 02/06/2025 14:00 | FAIRMOUNT: PCB B-1384
28 | 25-01116 | 16936318 | 02/03/2025 08:00 | 02/09/2025 17:00 | THE DALLES PH-BIG EDDY NO. 4 230KV LINE INCLUDING BIG EDDY PCB A-824 AND 230KV A/B SECTION 2 | THE DALLES PH-BIG EDDY NO 4 230KV LINE, THE DALLES PH: 230/13.8KV TRANSFORMER T5, THE DALLES PH: 230/13.8KV TRANSFORMER T6, BIG EDDY: PCB A-824, BIG EDDY: 230KV AUX BUS SECTION 2, BIG EDDY: 230/13.2KV TRANSFORMER 3, BIG EDDY: 13.2KV PCB L-1711, BIG EDDY: 13.2KV PCB L-1714, BIG EDDY: PCB A-816 | GEN, FCRPS, PDCI, WOJD, NWACI, COI
29 | 24-12406 | 16209471 | 02/03/2025 08:00 | 02/13/2025 15:00 | ASHE: PCB 4937 BFR | ASHE: PCB 4937 | NOH, NWACI, FCRPS
30 | 25-00850 | 16814483 | 02/03/2025 08:00 | 02/04/2025 15:00 | SLATT: PCB A-1801 BFR | SLATT: PCB A-1801 | WOJD, NWACI
31 | 25-00228 | 16209223 | 02/03/2025 09:00 | 02/13/2025 16:00 | GRIZZLY: PCB 4720; INCLUDING 500KV REACTOR 2 | GRIZZLY: 500KV REACTOR 2, GRIZZLY: PCB 4720 | NWACI
32 | 25-01177 | 16963759 | 02/04/2025 07:30 | 02/04/2025 16:00 | SATSOP: PCB A-619 |  | GEN, LOAD
33 | 25-00886 | 16834106 | 02/04/2025 10:00 | 02/04/2025 10:15 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
34 | 25-00888 | 16834109 | 02/04/2025 14:15 | 02/04/2025 14:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
35 | 25-00851 | 16814611 | 02/05/2025 08:00 | 02/06/2025 15:00 | SLATT: PCB A:1804 BFR | SLATT: PCB A-1804 | WOJD, NWACI
36 | 25-01183 | 16963771 | 02/05/2025 08:00 | 02/05/2025 16:00 | SATSOP: PCB A-625 |  | GEN, LOAD
37 | 25-01178 | 16963718 | 02/06/2025 07:30 | 02/06/2025 16:00 | SHELTON: PCB A-278 |  | RP
38 | 25-00381 | 16331830 | 02/06/2025 08:00 | 02/06/2025 15:00 | HANFORD: PCB 4085 INCLUDING 500KV CAP GROUP 1 | HANFORD: 500KV CAP GROUP 1, HANFORD: PCB 4085 | NOH, WOM, WOS
39 | 24-01467 | 14759867 | 02/06/2025 08:00 | 02/06/2025 11:00 | MARION: PCB 4383 |  | NWACI, WOCS
40 | 24-01465 | 14759856 | 02/06/2025 08:00 | 02/06/2025 15:00 | MARION: PCB 4386 | MARION: PCB 4386 | NWACI, WOCS
41 | 25-00359 | 16813580 | 02/06/2025 12:00 | 02/06/2025 14:00 | ABERDEEN: B/T PCB B-802 AND SATSOP: PCB'S A-630 & A-625 | ABERDEEN: 230/115KV TRANSFORMER 4, SATSOP-ABERDEEN NO 2 230KV LINE, SATSOP: PCB A-630, SATSOP: PCB A-625, ABERDEEN: PCB B-802 | LOAD, SI, GEN
42 | 25-00750 | 16738191 | 02/07/2025 16:30 | 02/07/2025 17:30 | MALIN: PCB 4072, MALIN: PCB 4582 |  | NWACI, COI
43 | 25-01059 | 16862502 | 02/10/2025 06:00 | 02/10/2025 07:00 | MALIN: PCB 4064, MALIN: PCB 4186 |  | NWACI, COI, RATS
44 | 25-01058 |  | 02/10/2025 06:00 | 02/14/2025 17:30 | MALIN: 4076/4077 TERMINAL OF MALIN-ROUND MOUNTAIN 1 500KV LINE | MALIN-ROUND MOUNTAIN NO 1 500KV LINE, MALIN: PG&E ROUND MOUNTAIN 1 500KV LINE SERIES CAP GROUP | BCHT, BCHW, NI, COI
45 | 25-01341 | 17036543 | 02/10/2025 07:00 | 02/13/2025 16:00 | MCNARY: PCB'S A-415 AND A-421 INCLUDING 230KV MAIN BUS SECTIONS 1&2 CURRENT LIMITING REACTOR | MCNARY: 230KV MAIN BUS SECTION 1-2 CURRENT LIMITING REACTOR, MCNARY: PCB A-415, MCNARY: PCB A-421 | WOM
46 | 25-00431 | 16923560 | 02/10/2025 07:00 | 04/03/2025 15:00 | -USBR- HUNGRY HORSE: PCBS 2182 AND 2382 | HUNGRY HORSE PH: PCB 2182, HUNGRY HORSE PH: PCB 2382 | WOH, FLAT
47 | 25-01113 | 16923893 | 02/10/2025 07:30 | 02/10/2025 16:00 | CARDWELL-COWLITZ NO 1 115KV LINE INCLUDING CARDWELL: PCB B-1552, 115KV AUX BUS, COWLITZ: PCB B-306, 115KV AUX BUS | CARDWELL-COWLITZ NO 1 115KV LINE, CARDWELL: 115KV AUX BUS, CARDWELL: PCB B-1552, COWLITZ: 115KV AUX BUS, COWLITZ PCB B-306 | SOA, NOPE
48 | 25-01466 |  | 02/10/2025 08:00 | 02/13/2025 18:00 | SCL- BOTHELL: PCB 120-9 |  | SOC, NOEL
49 | 25-00563 | 16821727 | 02/10/2025 08:00 | 02/13/2025 15:00 | CARLTON: PCB B-127 | CARLTON-MCMINNVILLE NO 1 115KV LINE | LOAD, NOPE, SOA
50 | 25-00470 | 16578844 | 02/10/2025 08:00 | 02/10/2025 15:30 | HANFORD: PCB 4085 INCLUDING CAP GRP 1 | HANFORD: 500KV CAP GROUP 1 | NOH, WOM, WOS
51 | 25-00473 | 16578854 | 02/10/2025 08:00 | 02/11/2025 15:00 | HANFORD: PCB 4095 |  | WOLM, NOH, WOM
52 | 25-00269 | 16242661 | 02/10/2025 08:00 | 02/11/2025 15:00 | RAVER: PCB 4876 |  | NOEL, RP, SOC, WOCN
53 | 25-01396 |  | 02/10/2025 08:00 | 02/13/2025 15:30 | TAFT: DWORSHAK-TAFT NO 1 500KV LINE INCLUDING TAFT PCB 4111, 4028 AND DWORSHAK 500KV SERIES CAPS | DWORSHAK-TAFT NO 1 500KV LINE, TAFT: PCB 4111, TAFT: PCB 4028, DWORSHAK-TAFT NO 1 500KV LINE SIERIES CAP GROUP 1 | MT-NW, NOH, WOH, WOLM, FCRPS, GEN
54 | 25-00249 | 16210295 | 02/10/2025 08:00 | 02/13/2025 15:00 | WAUTOMA: 500KV REACTOR #1 RELAYS, INCLUDING PCB 5236 BFR | WAUTOMA: 500KV REACTOR 1, WAUTOMA: PCB 5236 | NOH
55 | 25-00946 | 16836139 | 02/11/2025 07:30 | 02/13/2025 16:30 | PEARL: A-1165 TERMINAL OF MCLOUGHLIN-SHERWOOD NO 1 230KV LINE | PEARL-SHERWOOD SECTION OF MCLOUGHLIN-SHERWOOD NO 1 230KV LINE, PEARL: PCB A-1165 | SOA, NOPE
56 | 25-01191 | 16956309 | 02/11/2025 09:00 | 02/11/2025 11:00 | OLYMPIA-SOUTH ELMA NO 1 115KV LINE | OLYMPIA: PCB B-690 | LOAD, SI, RP
57 | 25-00611 | 16689497 | 02/11/2025 10:00 | 02/11/2025 10:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
58 | 25-00612 | 16689499 | 02/11/2025 14:15 | 02/11/2025 14:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
59 | 25-01120 | 16924007 | 02/12/2025 07:30 | 02/12/2025 16:00 | LEXINGTON-LONGVIEW NO 2 230KV LINE INCLUDING LONGVIEW: PCB A-1374 AND 230KV NORTH AUX BUS | LEXINGTON-LONGVIEW NO 2 230KV LINE, LONGVIEW: PCB A-1374, LONGVIEW: PCB A-1378, LONGVIEW: 230KV NORTH AUX BUS | SOA, NOPE
60 | 25-00410 | 16387920 | 02/12/2025 07:30 | 02/12/2025 16:00 | ECHO LAKE: PCB 5114 |  | BCHT, BCHW, NOEL, SOC, WOCN, NI
61 | 25-00411 | 16387925 | 02/13/2025 07:00 | 02/13/2025 16:00 | RAVER: PCB 4914 |  | NOEL, RP, SOC
62 | 25-01157 | 16970921 | 02/13/2025 08:00 | 02/13/2025 16:30 | LONGVIEW: 230KV NORTH MAIN BUS INCLUDING PCB'S A-1374, A-1378, AND A-1380 | LONGVIEW: 230KV NORTH MAIN BUS, LEXINGTON-LONGVIEW NO 2 230KV LINE, LONGVIEW: PCB A-1374, LONGVIEW: PCB A-1375, LONGVIEW: PCB A-1378, LONGVIEW: PCB A-1380, LONGVIEW: PCB A-1386, LONGVIEW: PCB A-1058 (230KV MAIN BUS SECTIONALIZING) | SOA, LOAD, NOPE
63 | 24-11189 | 16073025 | 02/14/2025 16:00 | 02/14/2025 16:30 | CUSTER: PCB 4272 |  | BCHT, BCHW, NOEL, SOC, NI
64 | 25-01060 | 16862508 | 02/14/2025 16:30 | 02/14/2025 17:30 | MALIN: PCB 4064, MALIN: PCB 4186 |  | NWACI, COI, RATS
65 | 25-00412 | 16388009 | 02/17/2025 07:00 | 02/20/2025 16:00 | RAVER: 500KV REACTOR 2 INCLUDING PCB 4844 | RAVER: PCB 4844, RAVER: 500KV REACTOR 2 | NOEL, RP, SOC
66 | 25-01057 | 16977172 | 02/17/2025 07:00 | 02/17/2025 17:00 | ST JOHNS: 115KV MAIN AND AUX BUSSES | ST. JOHNS: 230/115KV TRANSFORMER 1, ST. JOHNS: 115/57KV TRANSFORMER 5, ROSS-ST JOHNS NO 1 230KV LINE, ST JOHNS-KEELER NO 2 115KV LINE, ST JOHNS-PACW ST JOHNS NO 1 115KV LINE, ST JOHNS-ST HELENS NO 1 115KV LINE, ST JOHNS: PCB B-34, ST JOHNS: PCB B-40, ST JOHNS: PCB B-42, ST JOHNS: PCB B-80, ST JOHNS: PCB B-44, ST JOHNS: PCB B-48 | LOAD, SOA, NOPE
67 | 25-00688 | 16841660 | 02/17/2025 08:00 | 05/02/2025 15:00 | ROSS-ST JOHNS NO 1 230kV LINE INCLUDING ST JOHNS: 230/115KV TRANSFORMER 1 | ST. JOHNS: 230/115KV TRANSFORMER 1, ROSS-ST JOHNS NO 1 230KV LINE, ROSS: PCB A-32, ST JOHNS: PCB B-48 | LOAD, SOA, NOPE
68 | 25-00262 | 16376245 | 02/17/2025 08:00 | 02/20/2025 15:00 | MALIN: PCB 4182 INCLUDING 500 KV CAP GROUP 3 | MALIN: PCB 4182, MALIN: 500KV CAP GROUP 3 | COI, NWACI
69 | 25-01376 |  | 02/17/2025 08:00 | 03/07/2025 15:00 | -PGE- SHERWOOD: VWR2 230/115KV TRANSFORMER 2 |  | SOA, NOPE, LOAD
70 | 25-00229 | 17035225 | 02/17/2025 08:00 | 03/28/2025 15:00 | RUPPERT ROAD-HORN RAPIDS SECTION OF RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE
71 | 24-11306 | 16048768 | 02/17/2025 08:00 | 02/27/2025 15:00 | ALLSTON: PCB 4474, BFR |  | SOA, NOPE
72 | 25-00235 | 16209996 | 02/17/2025 09:00 | 02/17/2025 12:00 | MCNARY: 500/230KV TRANSFORMER 1 INCLUDING PCB'S 4228 AND 4231 | MCNARY: 500/230KV TRANSFORMER 1, MCNARY: PCB 4228, MCNARY: PCB 4231 | WOM, NWACI
73 | 25-01061 |  | 02/17/2025 18:00 | 03/24/2025 08:00 | ST JOHNS: 115KV WEST MAIN BUS INCLUDING THE B-50 MAIN BUS SECTIONALIZING DISC, 115KV WEST AUX BUS, PCB'S B-44 AND B-48, THE 230/115KV TRANSFORMER 1 INCLUDING THE ROSS-ST JOHNS NO 1 230KV LINE, AND THE ST JOHNS-PACW ST JOHNS NO 1 115KV LINE | ST JOHNS-PACW ST JOHNS NO 1 115KV LINE, ST JOHNS: 115KV WEST MAIN BUS, ST JOHNS: 115KV AUX BUS, ST JOHNS: PCB B-44, ST JOHNS: PCB B-48, ST. JOHNS: 230/115KV TRANSFORMER 1, ROSS-ST JOHNS NO 1 230KV LINE, ST JOHNS: B-50 MAIN BUS SECTIONALIZING DISC | LOAD, SOA, NOPE
74 | 25-00483 | 16463596 | 02/17/2025 22:00 | 02/17/2025 22:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
75 | 25-00325 | 16835564 | 02/18/2025 06:00 | 02/19/2025 13:00 | BELL: 230KV CAP GROUP 9 SECTIONS 1, 2, AND 3 INCLUDING PCB'S A-931, A-932, AND A-933 | BELL: 230KV CAP GROUP 9 SECTION 1, BELL: 230KV CAP GROUP 9 SECTION 2, BELL: 230KV CAP GROUP 9 SECTION 3, BELL: PCB A-931, BELL: PCB A-932, BELL: PCB A-933, BELL: PCB A-378 | MT-NW, WOH
76 | 24-10998 | 16930070 | 02/18/2025 07:00 | 02/19/2025 16:00 | COVINGTON: 500/230KV TRANSFORMER 5 INCLUDING 34.5KV PCBS L-1907 AND L-1908 | COVINGTON: 500/230KV TRANSFORMER 5, RAVER-COVINGTON NO 2 500KV LINE, COVINGTON: PCB L-1907, COVINGTON: PCB L-1908 | NOEL, RP, SIG, SOC, NI, WOCN, IROL
77 | 24-11120 | 16072993 | 02/18/2025 07:00 | 02/28/2025 16:00 | CUSTER: 4272 BFR | CUSTER: PCB 4272 | BCHT, BCHW, NOEL, SOC, NI
78 | 24-16156 |  | 02/18/2025 07:00 | 02/28/2025 09:00 | PG&E - ROUND MOUNTAIN-TABLE MOUNTAIN #2 500KV LINE |  | COI, NWACI
79 | 25-00237 | 17049202 | 02/18/2025 08:00 | 02/18/2025 12:00 | MCNARY: 500/230KV TRANSFORMER BANK #2 INCLUDING PCB'S 5198 AND 5204 | MCNARY: 500/230KV TRANSFORMER 2, MCNARY: PCB 5198, MCNARY: PCB 5204 | WOM, NWACI
80 | 25-00251 | 16192554 | 02/18/2025 08:00 | 02/27/2025 15:00 | ASHE: PCB 4940 BFR | ASHE: PCB 4940 | NWACI, WOCS, WOJD, WOM, FCRPS
81 | 25-00360 | 16890711 | 02/18/2025 08:00 | 02/18/2025 16:00 | SATSOP: PCB A-622 BFR | SATSOP: PCB A-622 | GEN, LOAD
82 | 25-00590 | 16689983 | 02/18/2025 09:00 | 02/19/2025 15:00 | SUMMER LAKE: PCB 4959 BFR | SUMMER LAKE: PCB 4959 | NWACI
83 | 25-00965 | 16890800 | 02/18/2025 15:01 | 02/18/2025 16:00 | SATSOP: PCB A-625 |  | GEN, LOAD
84 | 25-00238 | 16210088 | 02/19/2025 08:00 | 02/19/2025 11:00 | MCNARY-JOHN DAY NO 2 500KV LINE INCLUDING MCNARY PCB'S 5217 AND 5211 | MCNARY-JOHN DAY NO 2 500KV LINE, MCNARY: PCB 5211, MCNARY: PCB 5217 | WOM, WOS, WOCS, NWACI, PDCI, WOJD
85 | 25-00136 | 15830217 | 02/19/2025 08:00 | 02/19/2025 12:00 | TAFT: PCB 4114 |  | MT-NW, WOH
86 | 25-00361 | 16963790 | 02/19/2025 08:00 | 02/19/2025 16:00 | SATSOP: PCB A-625 BFR | SATSOP: PCB A-625 | GEN, LOAD
87 | 25-00138 | 15830056 | 02/19/2025 12:00 | 02/19/2025 15:00 | TAFT: PCB 4119 |  | MT-NW, WOH
88 | 25-00239 | 16201167 | 02/19/2025 12:00 | 02/19/2025 16:00 | MCNARY: PCB'S 5211 AND 5214 (OPEN ENDS LOWER MONUMENTAL-MCNARY NO 1 500KV LINE) | MCNARY: PCB 5211, MCNARY: PCB 5214, SACAJAWEA-MCNARY SECTION OF LOWER MONUMENTAL-MCNARY NO 1 500KV LINE | WOCS, WOJD, WOM, NWACI, GEN, SIG, WOLM, FCRPS
89 | 25-00966 | 16963808 | 02/19/2025 16:01 | 02/19/2025 17:00 | SATSOP: PCB A-622 |  | GEN, LOAD
90 | 24-10995 | 16930139 | 02/20/2025 07:00 | 02/21/2025 16:00 | COVINGTON: 500/230KV TRANSFORMER 4 INCLUDING 34.5KV PCBS L-1901 AND L-1902 | COVINGTON: 500/230KV TRANSFORMER 4, COVINGTON: PCB L-1901, COVINGTON: PCB L-1902, RAVER-COVINGTON NO 1 500KV LINE | NOEL, RP, SIG, SOC, NI, WOCN, IROL
91 | 25-00364 | 16976996 | 02/20/2025 08:00 | 02/20/2025 16:00 | SATSOP: PCB A-630 BFR | SATSOP: PCB A-630 | GEN, LOAD
92 | 24-13845 | 16628179 | 02/20/2025 08:00 | 02/20/2025 15:00 | HEBO: LBD B-501 | HEBO: 115KV CAP GROUP 1 | SOA
93 | 25-00968 | 16977017 | 02/20/2025 14:00 | 02/20/2025 15:00 | SATSOP: PCB A-625 |  | GEN, LOAD
94 | 25-00484 | 16463602 | 02/21/2025 22:30 | 02/21/2025 23:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
95 | 25-00041 | 11095420 | 02/23/2025 03:00 | 03/27/2025 17:00 | -USBR- GRAND COULEE: PCB 5382 | -USBR- GRAND COULEE: PCB 5382 | NOH, WOCN, COI, NWACI, PDCI
96 | 25-00385 | 16361690 | 02/24/2025 07:00 | 02/26/2025 16:00 | PAUL: PCB 4810 |  | PA, RP
97 | 25-01232 | 16977123 | 02/24/2025 07:00 | 02/27/2025 16:00 | ALVEY: 115KV AUX BUS | ALVEY: PCB B-586
98 | 24-10643 | 16762906 | 02/24/2025 07:30 | 02/27/2025 16:00 | LA GRANDE: 230KV CAP GROUP 1 SECTION 1 RELAYS INCLUDING PCB A-267 BFR | LA GRANDE: PCB A-267, LA GRANDE: 230KV CAP GROUP 1 | ID-NW
99 | 25-00059 | 14974927 | 02/24/2025 08:00 | 02/24/2025 16:30 | PONDEROSA: 230KV NORTH NON-GIS BUS SECTION INCLUDING PCB A-1844 | PONDEROSA: PCB A-1844, PONDEROSA: 230KV NORTH NON-GIS BUS SECTION | LOAD, COR, NWACI
100 | 25-00369 | 16456544 | 02/24/2025 08:00 | 02/27/2025 15:00 | KEELER: PCB 4322 RELAYS | KEELER: PCB 4322 | SOA, NOPE
101 | 25-00263 | 16376251 | 02/24/2025 08:00 | 02/27/2025 15:00 | MALIN: PCB 4184 INCLUDING 500KV CAP GROUP 4 | MALIN: PCB 4184, MALIN: 500KV REACTOR 4 | COI, NWACI
102 | 25-00714 | 16723220 | 02/24/2025 08:00 | 02/28/2025 16:00 | CUSTER-INGLEDOW NO 1 500KV LINE |  | BCHT, BCHW, NOEL, SIG, SOC, NI
103 | 25-00087 |  | 02/24/2025 18:00 | 08/20/2025 16:30 | PONDEROSA: 230KV NON-GIS NORTH BUS FROM REMOVED BUS SECTION EAST OF A-1811 DISC TO REMOVED JUMPERS FROM PCB A-1844 BUSHINGS TO A-1840 DISCONNECT INCLUDING A-1840 DISCONNECT
104 | 25-00771 | 16930575 | 02/25/2025 06:00 | 02/25/2025 17:00 | NOXON-LIBBY NO 1 230KV LINE, LIBBY: PCB A-1593 |  | WOH, FCRPS, GEN, FLAT, MT-NW
105 | 25-00567 | 16805982 | 02/25/2025 07:00 | 02/25/2025 11:00 | CUSTER: PCB A-1238 |  | BCHT, BCHW, NOEL, SOC, NI
106 | 25-01342 | 17035324 | 02/25/2025 07:30 | 02/25/2025 11:30 | MORROW FLAT: PCB B-2244
107 | 25-00613 | 16689501 | 02/25/2025 10:00 | 02/25/2025 10:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
108 | 25-01343 | 17035346 | 02/25/2025 11:30 | 02/25/2025 16:00 | MORROW FLAT: PCB B-2231
109 | 25-00801 | 16805996 | 02/25/2025 11:30 | 02/25/2025 15:30 | CUSTER: PCB A-1242 |  | BCHT, BCHW, NOEL, SOC, NI
110 | 25-00614 | 16689504 | 02/25/2025 14:15 | 02/25/2025 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
111 | 25-00568 | 16797981 | 02/26/2025 07:00 | 02/26/2025 15:00 | CUSTER-INTALCO 1 230KV LINE INCLUDING CUSTER: PCBS A-1238, A-1242, AND INTALCO: PCBS A-1012 AND A-1036 | CUSTER-INTALCO NO 1 230KV LINE, CUSTER: PCB A-1238, CUSTER: PCB A-1242, INTALCO: PCB A-1012, INTALCO: PCB A-1036 | LOAD, NOEL, SOC, BCHT, BCHW, NI
112 | 25-00772 | 16941636 | 02/26/2025 07:00 | 02/26/2025 17:00 | LIBBY: PCB A-1589 RELAYS INCLUDING FLATHEAD NO.1 230KV LINE FOTT CKT 7H58 AND 7H59 | FLATHEAD: PCB A-1957, FLATHEAD: PCB A-1959, FLATHEAD: 230KV AUX BUS
113 | 25-01344 | 17035361 | 02/26/2025 07:30 | 02/26/2025 11:30 | MORROW FLAT: PCB: B-2221
114 | 25-00163 | 15916571 | 02/26/2025 08:00 | 02/26/2025 15:00 | ASHE: PCB 4940 |  | NWACI, WOCS, WOJD, WOM, FCRPS
115 | 25-00334 | 16835477 | 02/26/2025 11:00 | 02/26/2025 16:00 | BELL: PCB A-388 |  | MT-NW, WOH
116 | 25-01345 | 17035365 | 02/26/2025 11:30 | 02/26/2025 16:00 | MORROW FLAT: PCB B-2241
117 | 25-00335 | 16835544 | 02/27/2025 06:00 | 02/27/2025 11:00 | BELL: PCB A-366
118 | 25-01346 | 17035374 | 02/27/2025 07:30 | 02/27/2025 11:30 | MORROW FLAT: PCB A-1884
119 | 25-00119 | 15576556 | 02/27/2025 08:00 | 02/27/2025 17:00 | JOHN DAY-MARION NO 1 500KV LINE INCLUDING JOHN DAY: PCB 4170, PCB 4167 | JOHN DAY: PCB 4167, JOHN DAY: PCB 4170, JOHN DAY-MARION NO 1 500KV LINE | JDAY, NWACI, WOCS, WOJD, PDCI, SIG
120 | 25-00120 | 15576631 | 02/27/2025 08:00 | 04/24/2025 08:00 | JOHN DAY: MOD 4169 | JOHN DAY: PCB 4170 | NWACI, WOCS, WOJD, PDCI
121 | 25-00164 | 15916586 | 02/27/2025 08:00 | 02/27/2025 15:00 | WAUTOMA: PCB 5256 |  | NOH, WOCN
122 | 25-00336 | 16835539 | 02/27/2025 11:00 | 02/27/2025 16:00 | BELL: PCB A-368 | BELL: 230KV CAP GROUP 10 SECTION 1, BELL: 230KV CAP GROUP 10 SECTION 2, BELL: LBD A-925, BELL: LBD A-926 | MT-NW, WOH
123 | 25-01347 | 17035382 | 02/27/2025 11:30 | 02/27/2025 16:00 | MORROW FLAT: PCB A-1887
124 | 25-00972 | 16862753 | 02/27/2025 15:00 | 02/27/2025 17:00 | ALLSTON: PCB 4470 |  | SOA, NOPE
125 | 24-11157 | 16073008 | 02/28/2025 16:00 | 02/28/2025 16:30 | CUSTER: PCB 4268 |  | BCHT, BCHW, NOEL, SOC, NI