## Request List
Row | Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
1 | 17-00008 |  | 08/25/2017 16:30 | 02/28/2030 17:00 | MCC - OLYMPIA-GRAND COULEE NO 1 287KV LINE - OPERATING AT 230KV | MCC - OLYMPIA-GRAND COULEE NO 1 287KV LINE - OPERATING AT 230KV
2 | 23-04125 | 13016840 | 01/28/2023 17:00 | 09/30/2026 23:59 | ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV | ROCKY REACH: 345/230KV TRANSFORMER 1, ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV, MAPLE VALLEY: 345/230KV TRANSFORMER 1 | WOCN, SOC/NOEL, CI, GEN, IROL, NOEL, NOH, SOC
3 | 23-01684 | 11460660 | 02/03/2023 15:30 | 01/21/2025 09:00 | PG&E -TABLE MOUNTAIN: ROUND MOUNTAIN 1 500KV LINE SERIES CAP 1 | PG&E -TABLE MOUNTAIN: ROUND MOUNTAIN 1 500KV LINE SERIES CAP 1 | COI, NWACI
4 | 23-03222 | 11461724 | 02/10/2023 18:30 | 01/31/2025 09:00 | PG&E- TABLE MOUNTAIN: ROUND MOUNTAIN 500KV LINE SERIES CAP GROUP 2 | PG&E- TABLE MOUNTAIN: ROUND MOUNTAIN 500KV LINE SERIES CAP GROUP 2 | NWACI, COI
5 | 23-18445 | 14853282 | 12/14/2023 06:40 | 03/31/2025 16:00 | BCH - CHAPMAN: 5CX1 | BCH - CHAPMAN: 5CX1 | NI
6 | 24-03190 | 15142411 | 01/15/2024 18:00 | 01/31/2025 15:00 | ECHO LAKE: 500KV CAP GRP 2 INCLUDING PCB 5127 | ECHO LAKE: PCB 5127, ECHO LAKE: 500KV CAP GROUP 2 | BCHT, NOEL, SOC, WOCN, NI, BCHW, IROL
7 | 24-03188 | 15061704 | 01/15/2024 18:00 | 01/31/2025 15:00 | ECHO LAKE: 500KV CAP GRP 1 INCLUDING PCB 5125 | ECHO LAKE: 500KV CAP GRP 1 INCLUDING PCB 5125, ECHO LAKE: PCB 5125, ECHO LAKE: 500KV CAP GROUP 1 | BCHT, BCHW, NOEL, SOC, WOCN, NI, IROL
8 | 24-09008 | 15780159 | 05/06/2024 18:00 | 05/15/2025 15:00 | ROCK CREEK: 230KV CAP GROUP 1 SECTION 1 INCLUDING PCB A-1719
9 | 24-13950 |  | 08/16/2024 00:06 | 12/01/2025 17:00 | PG&E - PACIRAS CONTROLLER A
10 | 24-05901 | 15358908 | 10/01/2024 08:00 | 02/28/2025 16:00 | WAPA - TRACY: 500KV SHUNT CAPACITOR PT10A & PT10B | WAPA - TRACY: 500KV SHUNT CAPACITOR PT10A & PT10B | COI
11 | 24-17059 | 16817941 | 10/25/2024 01:00 | 06/30/2025 16:00 | WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 |  | NOH, WOCN
12 | 24-13394 | 16799234 | 11/18/2024 08:00 | 01/17/2025 17:00 | MCNARY-B-1345 SECTION OF THE MCNARY-BADGER CANYON NO 1 115KV LINE INCLUDING THE PLYMOUTH TAP BC-165 AND PLYMOUTH TAP 2 BC-495 DISC | MCNARY: PCB B-980, MCNARY-B-1345 SECTION OF MCNARY-BADGER CANYON NO 1 115KV LINE, PLYMOUTH TAP TO MCNARY-BADGER CANYON NO 1 115KV LINE | GEN, LOAD, WOM, TCLA
13 | 24-00924 | 16813588 | 12/30/2024 07:00 | 01/31/2025 17:00 | MCNARY: 115KV AUX BUS INCLUDING B-979 A/B DISC | MCNARY: PCB B-988, MCNARY: 115KV AUX BUS
14 | 24-17137 | 16835232 | 12/30/2024 08:00 | 01/03/2025 16:00 | FAIRGROUNDS-ST HELENS SECTION OF ST JOHNS-ST HELENS NO 1 115KV LINE |  | LOAD, SOA, NOPE
15 | 24-10447 | 16187838 | 01/06/2025 06:00 | 01/17/2025 17:00 | GRIZZLY: PCB 5025 |  | NWACI
16 | 25-00700 | 16812664 | 01/06/2025 06:00 | 01/06/2025 20:00 | OLYMPIA: 230KV WEST AUX BUS | OLYMPIA: PCB A-216 | NOEL, RP, SOC, WOCN
17 | 24-00128 | 14702032 | 01/06/2025 07:00 | 02/07/2025 15:00 | MCNARY-COYOTE SPRINGS NO 1 500KV LINE, INCLUDING NEW LONGHORN SUB | MCNARY: PCB 4231, MCNARY: PCB 4234, COYOTE SPRINGS: PCB 5184, COYOTE SPRINGS: PCB 5187 | SIG, WOM, WOJD, NWACI, WOLM
18 | 24-11305 | 16048756 | 01/06/2025 07:00 | 01/16/2025 15:00 | ALLSTON: PCB 4500, BFR |  | SOA, NOPE
19 | 25-00114 | 15651209 | 01/06/2025 08:00 | 01/09/2025 15:00 | GARRISON-TAFT #2 500KV LINE INCLUDING TAFT: PCB'S 4125 AND 4148 | TAFT: PCB 4125, TAFT: PCB 4148, GARRISON-TAFT NO 2 500KV LINE, GARRISON: TAFT 2 500KV LINE SERIES CAP GROUP 2 | MT-NW, WOH, SIG
20 | 25-00104 | 15629193 | 01/06/2025 08:00 | 01/06/2025 15:00 | MARION: PCB 4368 |  | NWACI, WOCS
21 | 25-00160 | 15916558 | 01/06/2025 08:00 | 01/06/2025 15:00 | ASHE: PCB 5466 |  | NWACI, WOJD, WOM, WOS, FCRPS
22 | 24-17419 | 16892015 | 01/06/2025 08:00 | 01/09/2025 15:00 | WHITE BLUFFS: PCB B-207 RELAYS | WHITE BLUFFS: PCB B-207, WHITE BLUFFS: PCB B-215, RED MOUNTAIN-WHITE BLUFFS NO 1 115KV LINE | TCLA
23 | 24-13540 | 16798578 | 01/06/2025 08:00 | 01/06/2025 13:00 | SIFTON: SIFT-NBON CKT 7A21 & SIFT-ROSS CKT 7A23 TT | SIFTON TAP TO NORTH BONNEVILLE-ROSS NO 1 230KV LINE, NORTH BONNEVILLE: PCB A-13, ROSS: PCB A-34, SIFTON: PCB A-163, NORTH BONNEVILLE-ROSS NO 1 230KV LINE | GEN, LOAD, SOA, WOCS, NOPE, FCRPS
24 | 25-00605 | 16812761 | 01/07/2025 06:00 | 01/07/2025 20:00 | OLYMPIA: 230KV WEST MAIN BUS | OLYMPIA: PCB A-222, OLYMPIA: PCB A-220, OLYMPIA: PCB A-218, OLYMPIA: PCB A-216, OLYMPIA-SATSOP NO 2 230KV LINE, CHEHALIS-OLYMPIA NO 1 230KV LINE, OLYMPIA: 230/115KV TRANSFORMER 1, OLYMPIA: 230KV CAP GROUP 2 SECTION 1, OLYMPIA: 230KV CAP GROUP 2 SECTION 2, OLYMPIA-SHELTON NO 4 230KV LINE | RP, LOAD, NOEL, SI, SOC, WOCN, SOA, NOPE
25 | 25-00725 | 16835720 | 01/07/2025 07:00 | 01/07/2025 17:00 | ICE HARBOR-FRANKLIN NO 1 115KV LINE |  | GEN, TCLA
26 | 24-17147 | 16841642 | 01/07/2025 07:00 | 01/07/2025 14:00 | CONKELLEY: 230KV EAST MAIN BUS | FLATHEAD-CONKELLEY #1 230KV LINE, COLUMBIA FALLS-CONKELLEY NO 1 230KV LINE, HUNGRY HORSE-CONKELLEY NO 1 230KV LINE, CONKELLEY: 230/13.8KV TRANSFORMER 4 | MT-NW, FLAT, GEN, LOAD, FCRPS
27 | 25-00106 | 15583027 | 01/07/2025 08:00 | 01/07/2025 15:00 | SANTIAM: 230KV REACTIVE GROUP 1 REACTOR 1 INCLUDING PCB A-504 | SANTIAM: 230KV REACTIVE GROUP 1 REACTOR 1, SANTIAM: PCB A-504 | SLAL, NWACI
28 | 25-00162 | 15916564 | 01/07/2025 08:00 | 01/07/2025 15:00 | ASHE: PCB 5463 |  | NOH, NWACI, FCRPS
29 | 24-13579 | 16799785 | 01/07/2025 08:00 | 01/07/2025 13:00 | SIFTON: SIFT-NBON CKT 7A22 & SIFT-ROSS CKT 7A24 TT | SIFTON TAP TO NORTH BONNEVILLE-ROSS NO 2 230KV LINE, ROSS: PCB A-22, NORTH BONNEVILLE: PCB A-14, SIFTON: PCB B-1511, SIFTON: 230KV WEST MAIN BUS, SIFTON: 230KV AUX BUS, SIFTON: 230/115KV TRANSFORMER 1, NORTH BONNEVILLE-ROSS NO 2 230KV LINE | GEN, SOA, WOCS, LOAD, NOPE, FCRPS
30 | 25-00874 | 16821873 | 01/07/2025 10:00 | 01/07/2025 10:15 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
31 | 25-00875 | 16821887 | 01/07/2025 14:15 | 01/07/2025 14:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
32 | 25-00706 | 16841248 | 01/08/2025 06:00 | 03/25/2025 15:00 | OLYMPIA-SATSOP NO 2 230KV LINE INCLUDING PCB A-222 | OLYMPIA-SATSOP NO 2 230KV LINE, OLYMPIA: PCB A-222 | LOAD, SI, RP, NOEL, SOC, WOCN
33 | 25-00710 | 16840870 | 01/08/2025 06:00 | 04/29/2025 16:00 | OLYMPIA: PCB A-216 |  | NOEL, RP, SOC, WOCN
34 | 25-00728 | 16835832 | 01/08/2025 07:00 | 01/09/2025 17:00 | ICE HARBOR-SACAJAWEA SECTION OF ICE HARBOR-FRANKLIN NO 2 115KV LINE |  | TCLA
35 | 25-00838 | 16807858 | 01/08/2025 07:30 | 01/09/2025 15:30 | ROSS: 230/115KV TRANSFORMER 1 | ROSS: PCB A-26, ROSS: PCB B-2, ROSS: 13.2KV PCB L-25 | LOAD, SOA, NOPE
36 | 24-00247 | 13975578 | 01/08/2025 08:00 | 01/08/2025 16:00 | SANTIAM-ALBANY NO. 1 230KV LINE INCLUDING SANTIAM: PACW 230/69KV TRANSFORMER 2, 230KV LBD A-538, AND 230KV AUX BUS | SANTIAM-ALBANY NO 1 230KV LINE, SANTIAM: 230KV AUX BUS, SANTIAM: PACW 230/69KV TRANSFORMER 2, SANTIAM: LBD A-538, SANTIAM: PCB A-514, SANTIAM: 69KV PCB L-1114, ALBANY: 230/115KV TRANSFORMER 1, ALBANY: PCB B-520 | SLAL, NWACI, SCORC
37 | 24-12404 | 16889939 | 01/08/2025 08:00 | 01/16/2025 17:00 | ASHE: PCB 4901 BFR | ASHE: PCB 4901 | NWACI, FCRPS, NOH
38 | 24-00248 | 13990438 | 01/09/2025 08:00 | 01/09/2025 16:00 | TUMBLE CREEK-SANTIAM SECTION OF JONES CANYON-SANTIAM NO. 1 230KV LINE INCLUDING SANTIAM: 230KV AUX BUS AND PCB A-528 | TUMBLE CREEK-SANTIAM SECTION OF JONES CANYON-SANTIAM NO 1 230KV LINE, SANTIAM: 230KV AUX BUS, SANTIAM: PCB A-528, SANTIAM: PCB A-530 | GEN, WOCS, WOM, SLAL, SCORC, NWACI
39 | 25-01155 | 16921661 | 01/09/2025 21:00 | 01/10/2025 05:00 | KEELER: A-866 TERMINAL OF KEELER-PGE ST MARYS NO 1 230KV LINE | KEELER-PGE ST MARYS NO 1 230KV LINE, KEELER: PCB A-866 | LOAD, SOA, NOPE
40 | 25-00854 | 16813120 | 01/13/2025 07:30 | 02/10/2025 15:30 | ROSS: 230KV CAP GROUP 2 SECTION 3 INCLUDING LBD A-27 | ROSS: LBD A-27, ROSS: 230KV CAP GROUP 2 SECTION 3 | SOA, NOPE
41 | 25-00165 |  | 01/13/2025 08:00 | 01/31/2025 18:00 | SCL- EAST PINE 230KV BUS 1, BANK 96 AND SOUTH-EAST PINE 230KV LINE | EAST PINE (SCL)-SOUTH 230KV LINE | NOEL, SOC
42 | 25-00115 | 15613679 | 01/13/2025 08:00 | 01/16/2025 15:00 | TAFT: PCB 4125 |  | MT-NW, WOH
43 | 25-00167 |  | 01/13/2025 08:00 | 01/31/2025 18:00 | SCL - EAST PINE-SOUTH 230KV LINE |  | SOC/NOEL
44 | 25-00156 | 15916623 | 01/13/2025 09:00 | 01/13/2025 15:00 | CHIEF JOSEPH: A-588 BUS SECTIONALIZING BREAKER FAILURE RELAY
45 | 25-00607 | 16689421 | 01/14/2025 10:00 | 01/14/2025 10:15 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
46 | 25-00608 | 16689459 | 01/14/2025 14:15 | 01/14/2025 14:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
47 | 25-00053 | 14565872 | 01/15/2025 06:00 | 01/15/2025 17:00 | GRAND COULEE: PCBS 7182 AND 7382 | GRAND COULEE: PCB 7382, GRAND COULEE: PCBS 7182 AND 7382, GRAND COULEE: PCB 7182 | GEN, NOH, WOCN
48 | 25-00729 | 16836091 | 01/16/2025 07:00 | 01/16/2025 17:00 | ICE HARBOR-SACAJAWEA SECTION OF ICE HARBOR-FRANKLIN NO 2 115KV LINE |  | TCLA
49 | 25-00532 | 16820250 | 01/16/2025 07:00 | 01/16/2025 16:00 | BETTAS ROAD-COLUMBIA NO 1 230KV LINE INCLUDING COLUMBIA PCB A-341 AND BETTAS ROAD PCB'S A-3050 & A-3043 | COLUMBIA: PCB A-341, BETTAS ROAD: BETTAS ROAD: PCB A-3050, BETTAS ROAD: PCB A-3043, BETTAS ROAD-COLUMBIA NO 1 230KV LINE | WOCN, NOH, NOEL, SOC, CI, IROL
50 | 24-01923 | 14887595 | 01/16/2025 08:00 | 01/16/2025 15:00 | MARION: PCB 4020 | MARION: 500KV REACTOR 2 | NWACI
51 | 25-00184 | 16208771 | 01/16/2025 08:00 | 01/16/2025 10:00 | HATWAI: PCB 4700 |  | MT-NW, NOH, WOH, WOLM
52 | 25-00185 | 16208816 | 01/16/2025 10:00 | 01/16/2025 12:00 | HATWAI: PCB 4708 |  | MT-NW, NOH, WOH, WOLM
53 | 25-00186 | 16208844 | 01/16/2025 12:00 | 01/16/2025 14:00 | HATWAI: PCB 4710 |  | MT-NW, NOH, WOH, WOLM
54 | 25-00970 | 16862749 | 01/16/2025 15:00 | 01/16/2025 17:00 | ALLSTON: PCB 4502 |  | SOA, NOPE
55 | 25-00978 | 16898626 | 01/20/2025 07:00 | 01/22/2025 15:30 | ROSS: PCB A-142 |  | SOA, WOCS, NOPE
56 | 25-00730 | 16841917 | 01/21/2025 07:00 | 01/22/2025 17:00 | FRANKLIN: B-1528 TERMINAL OF ICE HARBOR-FRANKLIN NO1 115KV LINE | ICE HARBOR-FRANKLIN NO 1 115KV LINE, FRANKLIN: PCB B-1528 | GEN, TCLA
57 | 24-11120 | 16072993 | 01/21/2025 07:00 | 01/31/2025 16:00 | CUSTER: 4272 BFR | CUSTER: PCB 4272 | BCHT, BCHW, NOEL, SOC, NI
58 | 24-00976 | 14881049 | 01/21/2025 07:30 | 01/22/2025 16:00 | CAPTAIN JACK-MALIN NO 2 500KV LINE INCLUDING CAPTAIN JACK: PCB 4924 AND PCB 4986 | CAPTAIN JACK-MALIN NO 2 500KV LINE, CAPTAIN JACK: PCB 4924, CAPTAIN JACK: PCB 4986 | NWACI, SIG, COI
59 | 25-00444 | 16427363 | 01/21/2025 07:30 | 01/21/2025 15:30 | ALVEY: PCB B-586
60 | 25-00788 | 16856664 | 01/21/2025 07:30 | 01/21/2025 16:00 | WARREN TAP TO ST JOHNS-ST HELENS #1 115KV LINE INCLUDING WARREN 115/34.5KV TRANSFORMER #1 AND CRPUD TARBELL 115KV FEEDER #1 | WARREN: 115/34.5KV TRANSFORMER 1, WARREN: 34.5KV PCB L-680, WARREN: WEST OREGON ELEC 34.5KV FEEDER 1, DUTCH CANYON-WARREN SECTION OF ST JOHNS-ST HELENS NO 1 115KV LINE, WARREN-FAIRGROUNDS SECTION OF ST JOHNS-ST HELENS NO 1 115KV LINE, WARREN TAP TO ST JOHNS-ST HELENS NO 1 115KV LINE, TARBELL: COLUMBIA RIVR PUD 115KV FEEDER 1 | LOAD, SOA, NOPE
61 | 24-12405 | 16192409 | 01/21/2025 08:00 | 01/30/2025 15:00 | ASHE: PCB 4898 BFR | ASHE: PCB 4898 | NWACI, FCRPS
62 | 25-00880 | 16822175 | 01/21/2025 10:00 | 01/21/2025 10:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
63 | 25-00881 | 16834102 | 01/21/2025 14:15 | 01/21/2025 14:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
64 | 25-00985 | 16856671 | 01/22/2025 08:00 | 01/22/2025 14:00 | KERR: PCB B-600 | ELMO-KERR SECTION OF KALISPELL-KERR NO 1 115KV LINE | GEN, LOAD, FLAT, MT-NW
65 | 24-01476 | 14887282 | 01/23/2025 08:00 | 01/23/2025 11:00 | MARION: PCB 4355 |  | NWACI, WOCS, NOPE
66 | 25-00038 | 11036047 | 01/23/2025 09:00 | 01/23/2025 17:00 | DWORSHAK PH: PCB XJ-7 | DWORSHAK PH: PCB XJ-7, DWORSHAK PH: PCB XJ-7
67 | 24-01477 | 14887291 | 01/23/2025 12:00 | 01/23/2025 15:00 | MARION: PCB 4946 |  | NWACI, WOCS, NOPE
68 | 25-00952 | 16840544 | 01/27/2025 07:30 | 02/04/2025 16:30 | KEELER-OREGON CITY NO 2 115KV LINE | KEELER: PCB B-1080, OREGON CITY: PCB B-260 | LOAD, SOA, NOPE
69 | 25-00305 | 16814573 | 01/27/2025 08:00 | 02/02/2025 17:00 | BIG EDDY: THE DALLES PH-BIG EDDY NO. 3 230KV LINE INCLUDING BIG EDDY PCB A-812 AND THE 230KV A/B SECTION 1 | THE DALLES PH-BIG EDDY NO 3 230KV LINE, BIG EDDY: PCB A-812, BIG EDDY: PCB A-696 | GEN, FCRPS, PDCI, WOJD, NWACI, COI
70 | 25-00549 | 16806332 | 01/27/2025 08:00 | 01/27/2025 15:00 | OREGON CITY: 115KV CAP GROUP 1 INCLUDING PCB B-266 | OREGON CITY: 115KV CAP GROUP 1, OREGON CITY: PCB B-266
71 | 25-00203 | 16814062 | 01/27/2025 08:00 | 04/21/2025 15:00 | DRISCOLL-KNAPPA SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE | DRISCOLL: PCB B-2061, DRISCOLL: PCB B-2067
72 | 25-00794 |  | 01/27/2025 08:00 | 03/28/2025 15:00 | BENTON-RINGOLD SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE | CONNELL-SCOOTENEY SECTION OF BENTON-SCOOTENEY NO 1 115KV LINE | TCLA
73 | 25-00491 | 16498048 | 01/28/2025 08:00 | 01/28/2025 15:00 | SCHULTZ: PCB 5160 BFR | SCHULTZ: PCB 5160 | WOCN, NOEL
74 | 25-00609 | 16689482 | 01/28/2025 10:00 | 01/28/2025 10:15 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
75 | 25-00610 | 16689490 | 01/28/2025 14:15 | 01/28/2025 14:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
76 | 25-00492 | 16498052 | 01/28/2025 15:00 | 01/28/2025 15:30 | SCHULTZ: PCB 5157 |  | WOCN, NOEL
77 | 25-01163 | 16930735 | 01/29/2025 07:30 | 01/30/2025 15:30 | LONGVIEW: PCB B-330 | LONGVIEW: 115KV AUX BUS
78 | 25-01164 | 16930743 | 01/30/2025 15:30 | 01/30/2025 17:00 | LONGVIEW: PCB B-324
79 | 24-11157 | 16073008 | 01/31/2025 16:00 | 01/31/2025 16:30 | CUSTER: PCB 4268 |  | BCHT, BCHW, NOEL, SOC, NI