## Request List
Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
23-04125 | 13016840 | 01/28/2023 17:00 | 07/07/2025 07:00 | ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV | ROCKY REACH: 345/230KV TRANSFORMER 1, MAPLE VALLEY: 345/230KV TRANSFORMER 1 | WOCN, SOC/NOEL, CI, GEN, IROL, NOEL, NOH, SOC
23-16749 |  | 10/26/2023 07:00 | 06/01/2028 16:00 | VALHALLA: B-280 TERMINAL OF THE VALHALLA-CHELAN CO PUD 115KV FEEDER T1 | VALHALLA: CHELAN CO PUD 115KV FEEDER T1 | CI
23-18445 | 14853282 | 12/14/2023 06:40 | 12/31/2025 16:00 | BCH - CHAPMAN: 5CX1 | BCH - CHAPMAN: 5CX1 | NI
24-06648 | 16848796 | 03/20/2024 13:25 | 12/31/2026 15:00 | PG&E - PACIRAS CONTROLLER B
24-13950 |  | 08/16/2024 00:06 | 12/01/2025 17:00 | PG&E - PACIRAS CONTROLLER A
24-15794 | 16851914 | 09/26/2024 11:00 | 07/31/2025 16:00 | BOUNDARY: PCB A-1226
24-16579 | 17543676 | 10/16/2024 08:00 | 10/31/2025 15:00 | BOUNDARY: PCB A-1230 |  | SOB
24-17474 | 16890420 | 11/06/2024 10:20 | 06/30/2025 15:00 | CENTRAL FERRY: 500/230KV TRANSFORMER BANK NO. 1 (DERATE)
25-01365 | 17030311 | 04/01/2025 07:30 | 06/13/2025 16:00 | ALCOA: B-230 TERMINAL OF PIONEER-ALCOA NO 1 115KV LINE | FELIDA-SW48 SECTION OF PIONEER-ALCOA NO 1 115KV LINE, SW48-ALCOA SECTION OF PIONEER-ALCOA NO 1 115KV LINE | LOAD
25-06862 |  | 04/01/2025 10:00 | 10/01/2025 17:00 | MCNARY: A-436 TERMINAL OF MCNARY-WANAPA NO 1 230KV LINE
25-04924 | 17406712 | 04/17/2025 12:00 | 06/02/2025 08:00 | COLUMBIA: PCB B-398 INCLUDING B-398 MAIN BUS AND AUX BUS DISCs | COLUMBIA: PCB B-398
25-03624 | 17293824 | 04/21/2025 08:00 | 10/06/2025 11:00 | CARDWELL: B-1540 TERMINAL OF CARDWELL-MEEKER 115KV LINE | CARDWELL-MEEKER 115KV LINE, CARDWELL: PCB B-1540 | LOAD, SOA, NOPE
25-00370 |  | 04/24/2025 16:00 | 06/05/2025 12:00 | FRANKLIN: 115 KV EAST AUX BUS
25-06129 |  | 05/05/2025 07:00 | 06/06/2025 17:00 | MIDPOINT (IPC)-HEMINGWAY 500KV LINE |  | ID-NW, NWACI
25-00606 |  | 05/19/2025 06:00 | 06/20/2025 16:00 | -OTEC- HINES-WEST JOHN DAY 138KV LINE
25-07358 | 17678518 | 05/19/2025 08:00 | 06/05/2025 18:00 | MAPLE VALLEY: A-1116 TERMINAL OF MAPLE VALLEY-EAST PINE 1 230KV LINE | MAPLE VALLEY-EAST PINE NO 1 230KV LINE | NOEL, SOC
25-04561 | 17583210 | 05/19/2025 12:00 | 07/17/2025 10:00 | MIDWAY-HEW NO 2 230kV LINE INCLUDING MIDWAY: PCB A-114 AND A-114 AUX BUS DISC | MIDWAY: PCB A-114, MIDWAY: A-114 AUX BUS DISC, MIDWAY-HEW NO 2 230KV LINE | WOM, GEN, TCLA, LOAD
25-03902 | 17304188 | 05/22/2025 08:00 | 06/02/2025 16:00 | REDMOND: A-262 TERMINAL OF REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | REDMOND-PGE ROUND BUTTE NO 1 230KV LINE | SIG, COR, NWACI
25-01370 |  | 05/26/2025 08:00 | 06/13/2025 15:00 | -PGE- SHERWOOD: 230KV BUS V63 |  | SOA, NOPE, LOAD
25-02092 | 17133685 | 05/27/2025 08:00 | 06/01/2025 15:00 | CHEHALIS-OLYMPIA NO 1 230KV LINE | CHEHALIS: PCB A-228, OLYMPIA: PCB A-220 | RP, LOAD, SI, NOEL, SOC, WOCN
25-00205 | 17095338 | 05/28/2025 08:00 | 07/28/2025 15:00 | KNAPPA-FERN HILL SECTION OF DRISCOLL-ASTORIA NO 1 115KV LINE |  | SOA
25-02222 | 17182100 | 05/29/2025 10:00 | 06/30/2025 15:00 | NOTI CREEK TAP: B-971 AND B-972 TERMINALS OF NOTI CREEK TAP TO LANE-WENDSON NO 1 115KV LINE | FERN RIDGE-NOTI CREEK SECTION OF LANE-WENDSON NO 1 115KV LINE, NOTI CREEK-WALTON SECTION OF LANE-WENDSON NO 1 115KV LINE, NOTI CREEK TAP TO LANE-WENDSON NO 1 115KV LINE | LOAD, SCORC
25-00285 |  | 06/01/2025 22:00 | 06/05/2025 17:00 | GRAND COULEE: 2193 DSC, GRAND COULEE: 2197 DSC, GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-02597 | 17208082 | 06/02/2025 06:00 | 06/05/2025 15:00 | PALISADES PH-SNAKE RIVER 115KV LINE | PALISADES PH: LOWER VALLEY ENG 115KV FEEDER 1 BY USBR GENERAL | GEN, LOAD, SEIL
25-01491 |  | 06/02/2025 06:00 | 06/05/2025 15:00 | PALISADES PH: 762 TERMINAL OF THE PALISADES PH-SNAKE RIVER 115KV LINE | PALISADES PH: PCB 762, PALISADES PH: LOWER VALLEY ENG 115KV FEEDER 1 BY USBR GENERAL | GEN, LOAD, SEIL
25-06014 | 17536036 | 06/02/2025 06:45 | 06/02/2025 07:30 | WINTHROP: 115KV CAP GROUP 1 SECTION 1 AND 2 INCLUDING LBDs B-454 AND B-455 | WINTHROP: 115KV CAP GROUP 1 SECTION 1, WINTHROP: 115KV CAP GROUP 1 SECTION 2 | OKLA
25-00940 | 16840136 | 06/02/2025 07:00 | 06/13/2025 15:00 | LANE: 500/230KV TRANSFORMER 3 | MARION-LANE NO 1 500KV LINE | SIG, NWACI, EWEB
25-02193 | 17181316 | 06/02/2025 07:00 | 06/11/2025 16:00 | GRAND COULEE-SCHULTZ NO 2 500KV LINE | COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2, SCHULTZ: PCB 5148, SCHULTZ: PCB 5151, GRAND COULEE: PCB 9192, GRAND COULEE: PCB 2296, COLUMBIA: PCB 4693 | IROL, NOEL, NOH, SOC, WOCN, GEN, FCRPS, SIG
25-06261 | 17557287 | 06/02/2025 07:00 | 06/03/2025 16:00 | LANCASTER-NOXON NO 1 230KV LINE | LANCASTER: PCB A-1184, LANCASTER: PCB A-1186 | MT-NW, WOH, FLAT
25-00840 | 17268835 | 06/02/2025 07:00 | 06/27/2025 14:00 | SWAN VALLEY-TETON NO 2 115KV LINE INCLUDING SWAN VALLEY PCB B-1675 | SWAN VALLEY-TETON NO 2 115KV LINE, SWAN VALLEY: PCB B-1675 | SEIL, GEN
25-02778 | 17294313 | 06/02/2025 07:00 | 06/02/2025 09:00 | MONROE: 500KV CAP GROUP 4, INCLUDING PCB 4508 | MONROE: PCB 4508 | IROL, NI, NOEL, SOC, WOCN, STCON
25-00103 | 16778049 | 06/02/2025 07:00 | 06/15/2025 15:00 | PAUL-OLYMPIA NO 1 500KV LINE INCLUDING OLYMPIA 500/230KV BANK NO 5 | PAUL-OLYMPIA NO 1 500KV LINE, OLYMPIA: 500/230KV TRANSFORMER 5 | LOAD, RP, SIG, NOEL, IROL, SI
25-05708 | 17663901 | 06/02/2025 07:30 | 06/05/2025 17:00 | THURSTON-MCKENZIE (EWEB) NO 1 115KV LINE |  | EWEB
25-00455 | 17080343 | 06/02/2025 07:30 | 06/03/2025 15:30 | CAPTAIN JACK: PCB 4983 |  | NWACI, COI
25-04244 | 17333405 | 06/02/2025 07:30 | 06/03/2025 16:00 | JONES CANYON: 230KV REACTOR #1 INCLUDING PCB A-1673 | JONES CANYON: 230KV REACTOR 1, JONES CANYON: PCB A-1673
25-02096 | 17127573 | 06/02/2025 08:00 | 06/05/2025 16:00 | CENTRAL FERRY: PCB A-1780 BFR | CENTRAL FERRY: PCB A-1780
25-06917 | 17616764 | 06/02/2025 08:00 | 10/30/2025 16:00 | -CPUD- 7TH AVE-EAST KELSO 115KV LINE | 7TH AVE-EAST KELSO 115KV LINE | LOAD
25-06919 |  | 06/02/2025 08:00 | 06/15/2025 15:00 | WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 INCLUDING PCBS 5513 AND 5514 | WAUTOMA: PCB 5514, WAUTOMA: PCB 5513, WAUTOMA: SCHULTZ 1 500KV LINE SERIES CAP GROUP NO 1 | NOH, WOCN
25-03593 |  | 06/02/2025 08:00 | 06/06/2025 16:00 | -PGE- PELTON-ROUND BUTTE 230KV LINE |  | COR, NWACI
25-01373 | 17159231 | 06/02/2025 08:00 | 06/04/2025 16:30 | SCHULTZ: PCB 5160 |  | WOCN, NOEL
25-06093 | 17531097 | 06/02/2025 08:00 | 06/02/2025 16:30 | PORT ORFORD-ROGUE SECTION OF THE BANDON-ROGUE NO 1 115KV LINE INCLUDING GEISEL MONUMENT TAP | GEISEL MONUMENT-ROGUE SECTION OF BANDON-ROGUE NO 1 115KV LINE, GEISEL MONUMENT TAP TO BANDON-ROGUE NO 1 115KV LINE, PORT ORFORD-GEISEL MONUMENT SECTION OF BANDON-ROGUE NO 1 115KV LINE, GEISEL MONUMENT: COOS-CURRY COOP 115KV FEEDER 1
25-02196 | 17191320 | 06/02/2025 08:00 | 06/20/2025 12:00 | COLUMBIA: GRAND COULEE-SCHULTZ NO 2 500KV LINE SERIES CAP GROUP 2 INCLUDING PCB 4693 | COLUMBIA: PCB 4693, COLUMBIA: GRAND COULEE-SCHULTZ 2 500KV LINE SERIES CAP GROUP 2 | NOH, WOCN, IROL, NOEL, SOC
25-02091 | 17268467 | 06/02/2025 08:00 | 06/13/2025 15:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE |  | PA
25-00526 | 17109271 | 06/02/2025 08:00 | 06/05/2025 16:30 | BIG EDDY-CHEMAWA NO 1 230KV LINE |  | PDCI, WOCS, WOJD, NWACI
25-03489 | 17287068 | 06/02/2025 08:00 | 06/06/2025 15:00 | ST JOHNS-KEELER NO 2 115KV LINE INCLUDING KEELER: PCB B-1072 | ST JOHNS: PCB B-42, KEELER: PCB B-1072, ST JOHNS-KEELER NO 2 115KV LINE | LOAD, SOA, NOPE
25-04069 | 17320344 | 06/02/2025 08:00 | 06/02/2025 14:30 | KEELER: 115KV AUX BUS | KEELER: PCB B-1076
25-04315 | 17338012 | 06/02/2025 08:00 | 06/02/2025 15:00 | SNO-KING: 230KV CAP GROUP 1 SECTIONS 1 & 2 INCLUDING LBDS A-1197, A-1199 AND 230KV REACTIVE BUS | SNO-KING: PCB A-1434, SNO-KING: LBD A-1197, SNO-KING: LBD A-1199, SNO-KING: 230KV CAP GROUP 1 SECTION 1, SNO-KING: 230KV CAP GROUP 1 SECTION 2 | NOEL, SOC, WOCN
25-06453 | 17663913 | 06/02/2025 08:30 | 06/05/2025 16:00 | HOLDEN CREEK (EWEB) - THURSTON NO 1 115KV LINE | THURSTON: PCB 2360, HOLDEN CREEK: PCB 7150, HOLDEN CREEK: PCB 7190, HOLDEN CREEK-THURSTON NO 1 115KV LINE | GEN, EWEB
25-06019 | 17536027 | 06/02/2025 08:45 | 06/02/2025 09:30 | EAST OMAK: 115KV CAP GROUP 1 INCLUDING PCB B-81 | EAST OMAK: 115KV CAP GROUP 1 | OKLA
25-02776 | 17294326 | 06/02/2025 09:00 | 06/02/2025 11:00 | MONROE: 500KV CAP GROUP 2, INCLUDING PCB 4715 | MONROE: PCB 4715 | IROL, NI, NOEL, SOC, WOCN
25-06152 | 17535895 | 06/02/2025 10:30 | 06/02/2025 12:30 | CHIEF JOSEPH: BRAKING RESISTOR | CHIEF JOSEPH: PCB A-594 | NOH, SIG, NWACI, WOCN
25-02775 | 17294320 | 06/02/2025 11:00 | 06/02/2025 12:00 | MONROE: 500KV CAP GROUP 3, INCLUDING PCB 5047 | MONROE: PCB 5047 | IROL, NOEL, SOC, WOCN, NI
25-02779 | 17298042 | 06/02/2025 12:00 | 06/02/2025 14:00 | MONROE: 230KV REACTIVE GROUP 1 CAP SECTION 1 INCLUDING PCB A-1433 | MONROE: PCB A-1433, MONROE: 230KV REACTIVE GROUP 1 CAP SECTION 1 | WOCN, NOEL, SIG, SOC
25-04881 | 17407115 | 06/02/2025 12:00 | 06/02/2025 17:00 | COLUMBIA: 115KV SOUTH MAIN BUS INCLUDING PCB B-398 AND (NEW) B-398 M/B AND A/B DISCs | COLUMBIA: 115KV SOUTH MAIN BUS, COLUMBIA: 230/115KV TRANSFORMER 1, COLUMBIA-B408 SECTION OF COLUMBIA-ELLENSBURG NO 1 115KV LINE, COLUMBIA-ROCKY FORD NO 1 115KV LINE | TCLA, CI, NOH, LOAD, WOCN
25-00906 | 16822111 | 06/03/2025 07:30 | 06/03/2025 07:45 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-01265 | 16978079 | 06/03/2025 08:00 | 06/03/2025 16:00 | CENTRAL FERRY: PCB 5432, INCLUDING 500KV REACTOR 1 | CENTRAL FERRY: PCB 5432, CENTRAL FERRY: 500KV REACTOR 1 | WOH, WOLM
25-02258 | 17160287 | 06/03/2025 08:00 | 06/04/2025 15:00 | CUSTER: PCB A-1246 |  | BCHT, BCHW, NOEL, SOC, NI
25-01349 | 17049777 | 06/03/2025 08:00 | 06/04/2025 15:00 | MONROE: PCB 4522 | MONROE: PCB 5502 | BCHT, BCHW, NOEL, SOC, NI, WOCN
25-04190 | 17332913 | 06/03/2025 08:00 | 06/03/2025 12:00 | ADDY: 230KV CAP GROUP 1 INCLUDING PCB A-147 | ADDY: PCB A-147, ADDY: 230KV CAP GROUP 1 | SOB
25-07061 | 17642430 | 06/03/2025 10:00 | 06/03/2025 21:00 | CELILO: PACIFIC HVDC PROBING SIGNAL TEST | CHIEF JOSEPH: BRAKING RESISTOR | NOH, SIG, NWACI
25-00907 | 16822070 | 06/03/2025 11:15 | 06/03/2025 11:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-04375 | 17339163 | 06/04/2025 07:00 | 06/04/2025 15:00 | MAPLE VALLEY: PCB A-1130 |  | NOEL, SOC
25-00457 | 17080347 | 06/04/2025 07:30 | 06/05/2025 15:30 | CAPTAIN JACK: PCB 4990 |  | NWACI, COI
25-07350 | 17678078 | 06/04/2025 08:00 | 06/04/2025 15:00 | ELLENSBURG: 115KV CAP GROUP 1 INCLUDING PCB B-183 | ELLENSBURG: 115KV CAP GROUP 1, ELLENSBURG: PCB B-183 | TCLA
25-03526 |  | 06/04/2025 09:00 | 06/04/2025 14:00 | SANTIAM: 500/230KV TRANSFORMER 4 |  | SIG, WOCS, NWACI, SLAL
25-06889 | 17617808 | 06/04/2025 10:30 | 06/04/2025 12:30 | HOLCOMB: PCB B-440 | HOLCOMB-OXBOW SECTION OF HOLCOMB-NASELLE NO 1 115KV LINE | RP
25-00680 | 16808065 | 06/05/2025 07:00 | 06/05/2025 15:00 | MURRAY: PCB B-1745 BFR | MURRAY: PCB B-1745, MURRAY: 115KV CAP GROUP 1 SECTION 1, MURRAY: 115KV CAP GROUP 1 SECTION 2
25-02162 | 17145808 | 06/05/2025 08:00 | 06/05/2025 12:00 | SCHULTZ: PCB 5157 |  | WOCN, NOEL
25-05787 | 17490714 | 06/05/2025 08:00 | 06/11/2025 16:00 | MARION-LANE NO 1 500KV LINE |  | NWACI, SIG, EWEB
25-02259 | 17160292 | 06/05/2025 08:00 | 06/05/2025 15:00 | CUSTER: PCB A-1242 |  | BCHT, BCHW, NOEL, SOC, NI
25-02164 | 17145810 | 06/05/2025 12:00 | 06/05/2025 16:00 | SCHULTZ: PCB 5160 |  | WOCN, NOEL
25-00458 |  | 06/05/2025 13:00 | 06/05/2025 15:00 | CAPTAIN JACK: MOD 4989 & 4991 | CAPTAIN JACK: MOD 4989, CAPTAIN JACK: MOD 4991
25-00371 | 17116156 | 06/05/2025 13:00 | 06/05/2025 16:00 | FRANKLIN: 115KV AUX BUS | FRANKLIN: PCB B-616
25-01361 | 17095274 | 06/06/2025 08:00 | 06/12/2025 15:00 | SALEM-GRAND RONDE NO 1 115KV LINE | SALEM: PCB B-56 | LOAD, SOA, SLAL, NOPE
25-04502 |  | 06/06/2025 09:00 | 06/20/2025 16:00 | DIXONVILLE: ALVEY 1 500KV LINE SERIES CAP |  | NWACI, PDCI
25-01314 | 17003901 | 06/06/2025 22:30 | 06/06/2025 23:00 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-03604 | 17293189 | 06/07/2025 08:00 | 06/08/2025 16:00 | GRIZZLY: 4053/5039 TERMINALS OF GRIZZLY-ROUND BUTTE 500KV LINE | GRIZZLY: PCB 5040, GRIZZLY: PCB 4052, GRIZZLY-PGE ROUND BUTTE NO 1 500KV LINE | NWACI, WOJD, SIG
25-00486 | 17373639 | 06/07/2025 23:00 | 06/08/2025 09:00 | HOOD RIVER: 115KV M/B INCLUDING PCB'S B-1678, B-1679, B-1680, 115KV M/B PT'S AND B-1690 M/B DISCONNECT | HOOD RIVER: PCB B-1678, HOOD RIVER: PCB B-1680, CASCADE LOCKS-HOOD RIVER SECTION OF BONNEVILLE PH 1-HOOD RIVER NO 1 115KV LINE, HOOD RIVER-THE DALLES NO 1 115KV LINE, HOOD RIVER: PCB B-1679, HOOD RIVER: 115KV MAIN BUS, HOOD RIVER: HOOD RIVER ELEC 115KV FEEDER 1, HOOD RIVER: PACIFICORP (PACW) 115KV FEEDER 1, HOOD RIVER-COOP SERVICE NO 1 115KV LINE | GEN, WOCS, FCRPS, LOAD
25-00287 |  | 06/08/2025 22:00 | 06/27/2025 23:00 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
25-05884 |  | 06/09/2025 07:00 | 06/09/2025 07:30 | BIG EDDY: PCB A-812 OF THE DALLES PH-BIG EDDY NO 3 230KV LINE | THE DALLES PH-BIG EDDY NO 3 230KV LINE | GEN, FCRPS
25-04889 | 17400171 | 06/09/2025 07:00 | 06/12/2025 14:00 | COLUMBIA FALLS: PCB A-307 RELAYS | COLUMBIA FALLS: PCB A-307 | MT-NW, FLAT
25-00973 | 16929824 | 06/09/2025 07:00 | 06/12/2025 15:00 | OSTRANDER: PCB 4448 |  | WOCS
25-01432 |  | 06/09/2025 08:00 | 06/12/2025 15:00 | DWORSHAK: HSGS 7117
25-01079 | 17080834 | 06/09/2025 08:00 | 06/12/2025 16:00 | ALVEY: 230KV REACTOR 1, INCLUDING PCB A-241 |  | EWEB, NWACI, SLAL
25-07236 | 17657453 | 06/09/2025 08:00 | 06/26/2025 15:30 | BIG EDDY: PCB 4866 BFR | BIG EDDY: PCB 4866 | GEN, PDCI, WOJD, BGEDY
25-05403 |  | 06/09/2025 08:00 | 06/13/2025 18:00 | SCL - NORTH: 120KV BUS 7 INCLUDING BANK 56 AND PCB'S 120-80 & -81 |  | SOC/NOEL
25-01375 | 17180938 | 06/09/2025 08:00 | 06/09/2025 16:30 | SCHULTZ: PCB 5148 |  | WOCN, NOEL
25-07031 |  | 06/09/2025 08:00 | 06/10/2025 16:30 | PORT ORFORD-GEISEL MONUMENT SECTION OF BANDON-ROGUE NO 1 115KV LINE | BANDON-ROGUE NO 1 115KV LINE | SCORC
25-01204 | 17036887 | 06/09/2025 08:00 | 06/09/2025 16:00 | CARLTON: PCB A-315 | CARLTON-TILLAMOOK NO 1 230KV LINE, TILLAMOOK: 230/115KV TRANSFORMER 2 | LOAD, SOA, NOPE, NWACI
25-00527 | 17115999 | 06/09/2025 08:00 | 06/12/2025 15:30 | BIG EDDY-CHEMAWA NO 1 230KV LINE |  | PDCI, WOCS, WOJD, NWACI
25-01067 | 17068922 | 06/09/2025 08:00 | 06/12/2025 15:00 | CANAL-EAST HILLS SECTION OF MINIDOKA PH-UNITY NO 1 138KV LINE
25-04597 | 17379989 | 06/09/2025 08:00 | 06/12/2025 15:00 | HAPPY VALLEY: 230/115KV TRANSFORMER 1 INCLUDING 115KV MAIN BUS, PCB B-1839, AND 115KV MAIN BUS PTs | HAPPY VALLEY: CLALLAM CO PUD 115KV FEEDER 1, HAPPY VALLEY: 230/115KV TRANSFORMER 1
25-05944 | 17535214 | 06/09/2025 08:00 | 06/27/2025 15:00 | CARLTON-WINDISHAR SECTION OF CARLTON-MCMINNVILLE NO 1 115KV LINE INCLUDING CARLTON: PCB B-127 AND THE 115KV AUX BUS | CARLTON-WINDISHAR SECTION OF CARLTON-MCMINNVILLE NO 1 115KV LINE
25-06748 | 17611238 | 06/09/2025 08:00 | 06/11/2025 15:00 | MONROE: 230KV REACTOR 1 INCLUDING PCB A-1431 | MONROE: PCB A-1431, MONROE: 230KV REACTIVE GROUP 1 REACTOR 1 | NOEL, SOC, WOCN
25-01307 | 17004753 | 06/09/2025 08:00 | 06/10/2025 15:00 | KEELER: PCB 4763 INCLUDING 500KV CAP GROUP 3 | KEELER: 500KV CAP GROUP 3, KEELER: PCB 4763 | SOA, WOCS, NOPE
25-04059 | 17320365 | 06/09/2025 08:00 | 07/09/2025 15:00 | KEELER: PCB A-873 INCLUDING 230KV REACTIVE GROUP 2 REACTOR 1 | KEELER: PCB A-873, KEELER: 230KV REACTIVE GROUP 2 REACTOR 1 | SOA, NOPE
25-02759 | 17339709 | 06/09/2025 12:00 | 06/18/2025 16:00 | ALVEY: 115KV NORTH MAIN BUS, INCLUDING PCBs: B-584, B-586, B-588, B-590, B-594, B-1660, AND B-1662 | ALVEY: PCB B-586, ALVEY: PCB B-588, ALVEY: PCB B-590, ALVEY: PCB B-594, ALVEY: PCB B-1660, ALVEY: PCB B-1662, ALVEY: PCB B-584, ALVEY PACW-GOSHEN SECTION OF ALVEY-MARTIN CREEK NO 1 115KV LINE, ALVEY: EWEB (EUGENE OR) 115KV FEEDER 1 TO CURRIN, PLEASANT HILL-ALVEY SECTION OF LOOKOUT POINT-ALVEY NO 1 115KV LINE, ALVEY: 115KV CAP GROUP 1 SECTION 1, ALVEY: 115KV CAP GROUP 1 SECTION 2, ALVEY: 230/115KV TRANSFORMER 4, ALVEY: SPRNGFLD UTIL BRD 115KV FEEDER 1 TO 10TH STREET, ALVEY: 115KV AUX BUS | LOAD, EWEB, NWACI, GEN, SCORC
25-03045 | 17269074 | 06/10/2025 07:00 | 06/12/2025 14:00 | GOSHEN: 115KV MAIN BUS INCLUDING 161/115KV TRANSFORMERS #1 AND #2, 13.2KV/240V/120V PRIMARY SS PADMOUNT XFMR, PCBs B-1346, B-703, B-705, AND 115KV MB PTs | GOSHEN: 161/115KV TRANSFORMER 1, GOSHEN: 161/115KV TRANSFORMER 2, GOSHEN: PCB B-703, GOSHEN: PCB B-705, GOSHEN: 115KV MAIN BUS, GOSHEN: 115KV AUX BUS, 13.2KV/240V/120V PRIMARY SS PADMOUNT TRANSFORMER, GOSHEN: PCB B-1346, CATTLE CREEK-GOSHEN NO 1 115KV LINE | SEIL, LOAD, GEN
25-07147 | 17649664 | 06/10/2025 07:00 | 06/11/2025 16:00 | COLUMBIA: A-344 TERMINAL OF COLUMBIA-WANAPUM NO 2 230KV LINE | COLUMBIA-ANCIENT LAKE SECTION OF COLUMBIA-WANAPUM NO 2 230KV LINE
25-00884 | 16841117 | 06/10/2025 07:30 | 06/10/2025 07:45 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
25-04206 | 17333043 | 06/10/2025 08:00 | 06/10/2025 15:00 | ADDY: 115KV AUX BUS INCLUDING PCB B-1141 | ADDY: 115KV AUX BUS, ADDY: PCB B-1141
25-01381 | 17175423 | 06/10/2025 08:00 | 06/12/2025 16:30 | SCHULTZ: PCB 5151 |  | WOCN, NOEL
25-07063 | 17642451 | 06/10/2025 10:00 | 06/10/2025 21:00 | CELILO: PACIFIC HVDC PROBING SIGNAL TEST, (ALTERNATE DATE) | CHIEF JOSEPH: BRAKING RESISTOR | NOH, SIG, NWACI
25-00885 | 16841123 | 06/10/2025 11:15 | 06/10/2025 11:30 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
25-04186 | 17333046 | 06/11/2025 07:00 | 06/11/2025 16:00 | DEER PARK: 115KV CAP GROUP 1 INCLUDING PCB B-1913 | DEER PARK: 115KV CAP GROUP 1, DEER PARK: PCB B-1913
25-01246 | 17116199 | 06/11/2025 08:00 | 06/12/2025 16:00 | NORWAY-MORRISON SECTION OF FAIRVIEW-BANDON NO 1 115KV LINE |  | SWORE
25-02117 | 17127835 | 06/11/2025 08:00 | 06/12/2025 16:00 | CENTRAL FERRY: PCB 5432 INCLUDING 500KV REACTOR 1 | CENTRAL FERRY: PCB 5432, CENTRAL FERRY: 500KV REACTOR 1 | WOH, WOLM
25-01654 | 17094302 | 06/12/2025 07:00 | 06/12/2025 11:00 | RAVER: PCB 4308 |  | NOEL, RP, SOC, WOCN
25-06027 | 17596724 | 06/12/2025 07:00 | 06/12/2025 11:00 | CUSTER: PCB A-1250 |  | BCHT, BCHW, NOEL, SOC, NI
25-06449 |  | 06/12/2025 08:00 | 06/12/2025 13:00 | -PGE- GRAND RONDE: PCB W152
25-01656 | 17094294 | 06/12/2025 11:00 | 06/12/2025 15:00 | RAVER: PCB 4311 |  | NOEL, RP, SOC, WOCN
25-06623 | 17596731 | 06/12/2025 11:30 | 06/12/2025 15:00 | CUSTER: PCB A-1540 |  | BCHT, BCHW, NOEL, SOC, NI
25-03803 | 17298468 | 06/15/2025 22:00 | 06/30/2025 17:00 | GRAND COULEE: PCB 6886 |  | NOH, WOCN
25-05888 |  | 06/16/2025 07:00 | 06/16/2025 07:30 | THE DALLES PH-BIG EDDY NO 3 230KV LINE | THE DALLES PH: 230/13.8KV TRANSFORMER T3, THE DALLES PH: 230/13.8KV TRANSFORMER T4 | GEN, FCRPS
25-05037 | 17424584 | 06/16/2025 07:00 | 06/17/2025 12:00 | OLYMPIA: PCB A-352 RELAY, CONTROL AND ALARM CIRCUITS | OLYMPIA: PCB A-352
25-07220 | 17656948 | 06/16/2025 07:00 | 07/10/2025 14:00 | LIBBY PH-LIBBY NO 2 230KV LINE INCLUDING LIBBY: PCB A-1587 AND THE 230KV AUX BUS | LIBBY PH-LIBBY NO 2 230KV LINE | GEN, FCRPS
25-04047 | 17530908 | 06/16/2025 07:00 | 06/19/2025 16:00 | LIBBY-LIBBY FEC SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE | LIBBY: 230/115KV TRANSFORMER 1, LIBBY: PCB B-1300 | FLAT, SOB
25-01179 | 17191219 | 06/16/2025 07:00 | 06/16/2025 15:00 | GRAND COULEE-BELL NO 3 230KV LINE INCLUDING BELL: 230KV AUX BUS SECTION 5 AND PCB A-558 | GRAND COULEE-BELL NO 3 230KV LINE, BELL: 230KV AUX BUS SECTION 5, BELL: PCB A-558, BELL: PCB A-552 | NOH, WOH, MT-NW
25-00939 | 16841149 | 06/16/2025 07:00 | 06/29/2025 16:00 | SNOHOMISH-BOTHELL NO 1 230KV LINE |  | NOEL, SOC
25-05636 | 17518430 | 06/16/2025 07:00 | 06/16/2025 16:00 | SHELTON: PCB A-1667 |  | RP
25-06751 | 17643935 | 06/16/2025 08:00 | 06/16/2025 16:00 | OLYMPIA: 230/115KV TRANSFORMER 1 | OLYMPIA: PCB A-218, OLYMPIA: PCB B-682 | NOEL, RP, WOCN, SOC
25-01360 | 17298724 | 06/16/2025 08:00 | 06/17/2025 15:00 | KEELER-FOREST GROVE NO 2 115KV LINE |  | LOAD, SOA, NOPE
25-04291 | 17337016 | 06/16/2025 08:00 | 07/02/2025 15:00 | ROSS: 230/115KV TRANSFORMER 1 | ROSS: PCB A-26, ROSS: PCB B-2, ROSS: 13.2KV PCB L-25 | LOAD, SOA, NOPE
25-04252 | 17339570 | 06/16/2025 08:00 | 06/17/2025 15:00 | COLUMBIA-VALHALLA NO 2 115KV LINE |  | CI, NOH
25-01378 | 17299613 | 06/16/2025 08:00 | 06/18/2025 16:30 | SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5163 | SCHULTZ: PCB 5163, SCHULTZ: RAVER 1 500KV LINE SERIES CAP GROUP 1 | WOCN, NOEL, IROL, SOC, SIG
25-01248 | 17075964 | 06/16/2025 08:00 | 06/17/2025 16:00 | GLASGOW-SUMNER SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE |  | LOAD, SCORC
25-02087 | 17208207 | 06/16/2025 08:00 | 06/18/2025 15:00 | FAIRMOUNT-HAPPY VALLEY SECTION OF FAIRMOUNT-PORT ANGELES NO 2 230KV LINE |  | SOA, RP, NOPE
25-02086 | 17268975 | 06/16/2025 08:00 | 06/22/2025 15:00 | T3BA'DAS-FAIRMOUNT SECTION OF SHELTON-FAIRMOUNT NO 2 115KV LINE |  | PA
25-01080 | 17122618 | 06/16/2025 08:00 | 06/26/2025 15:00 | ALVEY: 230KV REACTIVE GROUP 2, CAP SECTIONS 1, 2, AND 3 INCLUDING: PCBs A-476, A-235, A-237, AND A-239 | ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 1, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 2, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 3, ALVEY: PCB A-476, ALVEY: PCB A-235, ALVEY: PCB A-237, ALVEY: PCB A-239 | EWEB, NWACI
25-00459 | 17116209 | 06/16/2025 08:00 | 06/17/2025 15:00 | HILLTOP: PCB A-1525 |  | RATS, NWACI
25-05405 |  | 06/16/2025 08:00 | 06/21/2025 18:00 | SCL - BOTHELL-NORTH 120KV LINE INCLUDING NORTH: 120KV BUS 1 AND PCB'S 120-75 & -81 |  | SOC/NOEL
25-06811 |  | 06/16/2025 08:00 | 06/25/2025 15:30 | PACE: THEIR THREE MILE KNOLL 121A TERMINAL | HOOPER SPRINGS-THREE MILE KNOLL NO 1 138KV LINE, HOOPER SPRINGS: 138/115KV BANK 1 | ID-NW
25-02115 | 17287919 | 06/16/2025 11:00 | 06/18/2025 15:00 | HARNEY: PCB B-1710
25-01180 | 17191638 | 06/17/2025 07:00 | 06/17/2025 15:00 | GRAND COULEE-BELL NO 5 230KV LINE INCLUDING BELL: 230KV AUX BUS SECTION 3 AND PCB A-382 | GRAND COULEE-BELL NO 5 230KV LINE, BELL: 230KV AUX BUS SECTION 3, BELL: PCB A-382, BELL: PCB A-372, GRAND COULEE: PCB 7286 | NOH, WOH, MT-NW, WOCN
25-00908 | 16821985 | 06/17/2025 07:30 | 06/17/2025 07:45 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-05256 | 17490879 | 06/17/2025 07:30 | 06/17/2025 16:00 | ABERDEEN: 230/115KV TRANSFORMER 5 | SATSOP-ABERDEEN NO 3 230KV LINE, ABERDEEN: PCB B-807, SATSOP: PCB A-619, SATSOP: PCB A-616 | LOAD, SI, GEN
25-01068 | 17074912 | 06/17/2025 08:00 | 06/17/2025 15:00 | EAST HILLS-UNITY SECTION OF MINIDOKA PH-UNITY NO 1 138KV LINE
25-00462 | 16842562 | 06/17/2025 08:00 | 06/17/2025 17:00 | GOBLE-RAINIER SECTION OF ST HELENS-ALLSTON NO 1 115KV LINE |  | SOA, NOPE
25-00909 | 16821976 | 06/17/2025 11:15 | 06/17/2025 11:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-01411 | 17037305 | 06/18/2025 07:00 | 06/18/2025 16:00 | -USCOE- BONNEVILLE POWERHOUSE 1 - 115KV ROOF BUS PCB'S XW-102, XW-106, XW-151, XW-174, XW-176 AND XW-178 | BONNEVILLE PH: PCB XW102, BONNEVILLE PH: PCB XW106, BONNEVILLE PH: PCB XW174, BONNEVILLE PH: PCB XW176, BONNEVILLE PH: PCB XW178, BONNEVILLE PH: PCB XW151
25-01181 | 17191535 | 06/18/2025 07:00 | 06/18/2025 15:00 | BELL-USK NO 1 230KV LINE INCLUDING BELL: 230KV AUX BUS SECTION 3 AND PCB A-394 | BELL-USK NO 1 230KV LINE, BELL: 230KV AUX BUS SECTION 3, BELL: PCB A-372, BELL: PCB A-394, USK: PCB A-955, USK: PCB A-958 | SOB, GEN, WOH, MT-NW
25-05637 | 17518950 | 06/18/2025 07:00 | 06/18/2025 16:00 | SHELTON: PCB A-971 |  | RP
25-05259 | 17569733 | 06/18/2025 08:00 | 06/18/2025 15:00 | KEELER-FOREST GROVE NO 1 115KV LINE | KEELER: PCB B-1086, FOREST GROVE: PCB B-650 | LOAD, SOA, NOPE
25-00463 | 16842566 | 06/18/2025 08:00 | 06/18/2025 17:00 | RAINIER-ALLSTON SECTION OF ST HELENS-ALLSTON NO 1 115KV LINE | ALLSTON: PCB B-1901 | SOA, NOPE
25-03625 | 17293918 | 06/18/2025 08:00 | 07/02/2025 16:00 | GRIZZLY: 4047/4049 TERMINALS AND MALIN: 4071/4073/4341 TERMINALS OF GRIZZLY-MALIN 2 500KV LINE | GRIZZLY-MALIN PGE NO 2 500KV LINE, SAND SPRINGS: GRIZZLY-MALIN 2 500KV LINE SERIES CAP GROUP 2, FORT ROCK: GRIZZLY-MALIN 2 500KV LINE SERIES CAP GROUP 2, SYCAN: GRIZZLY-MALIN 2 500KV LINE SERIES CAP GROUP 2 | BCHT, BCHW, NI, NWACI, SIG
25-02088 | 17208676 | 06/19/2025 08:00 | 06/23/2025 15:00 | FAIRMOUNT-PORT ANGELES NO 1 230KV LINE |  | RP
25-05889 |  | 06/19/2025 16:30 | 06/19/2025 17:00 | THE DALLES PH-BIG EDDY NO 3 230KV LINE | THE DALLES PH: 230/13.8KV TRANSFORMER T3, THE DALLES PH: 230/13.8KV TRANSFORMER T4 | GEN, FCRPS
25-02204 |  | 06/20/2025 12:30 | 06/20/2025 17:00 | COLUMBIA: GRAND COULEE-SCHULTZ NO 1 500KV SERIES CAP GROUP 1 INCLUDING PCB 4694 | COLUMBIA: PCB 4694, COLUMBIA: GRAND COULEE-SCHULTZ 1 500KV LINE SERIES CAP GROUP 1 | NOH, WOCN, IROL, NOEL, SOC
25-04414 | 17360986 | 06/21/2025 03:00 | 06/22/2025 20:00 | CELILO: 9085 TERMINAL OF CELILO-SYLMAR POLE 3 AND 9084 TERMINAL OF CELILO-SYLMAR POLE 4 1000KV LINE, CELILO: 9054/9092 TERMINAL OF RICE FLATS ELECTRODE, BIG EDDY: 4214 TERMINAL OF BIG EDDY-CELILO #1 500KV LINE, BIG EDDY: 4207 TERMINAL OF BIG EDDY-CELILO #2 500KV LINE | BIG EDDY-CELILO NO 1 500KV LINE, BIG EDDY-CELILO NO 2 500KV LINE, CELILO-SYLMAR POLE NO 3 1000KV LINE, CELILO-SYLMAR POLE NO 4 1000KV LINE, CELILO: POLE 3 540/240/240KV TRANSFORMER, CELILO: POLE 3 CONVERTER 1, CELILO: POLE 4 540/240/240KV TRANSFORMER, CELILO: POLE 4 CONVERTER 2, CELILO: PCB 4741, CELILO: PCB 4740 | PDCI, SIG, BGEDY, NWACI, GEN
25-04415 |  | 06/21/2025 03:00 | 06/22/2025 20:00 | CELILO: 9085 TERMINAL OF CELILO-SYLMAR POLE 3 AND 9084 TERMINAL OF CELILO-SYLMAR POLE 4 1000KV LINE (GROUNDED) |  | PDCI
25-01184 | 17074733 | 06/23/2025 06:00 | 06/23/2025 11:00 | BELL: PCB A-372
25-03605 | 17299738 | 06/23/2025 07:00 | 07/02/2025 15:00 | KELLER-NESPELEM SECTION OF GRAND COULEE-OKANOGAN NO 2 115KV LINE |  | LOAD
24-02160 | 14854315 | 06/23/2025 07:00 | 06/23/2025 16:30 | GARRISON: 4428/4436/4437 TERMINAL OF BROADVIEW-GARRISON 1 500KV LINE | GARRISON: 4428/4436/4437 TERMINAL OF BROADVIEW-GARRISON 1 500KV LINE, BROADVIEW-GARRISON NO 1 500KV LINE | MT-NW, GEN
25-00394 | 16425606 | 06/23/2025 07:00 | 06/26/2025 16:30 | ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE INCLUDING ROCKY REACH: 345/230KV TRANSFORMER 1 | MAPLE VALLEY: 345/230KV TRANSFORMER 1, ROCKY REACH: 345/230KV TRANSFORMER 1, ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE | NOEL, SOC, WOCN, IROL, GEN, NOH, CI
25-04051 | 17531725 | 06/23/2025 07:00 | 06/27/2025 16:00 | TROY-YAAK SECTION OF LIBBY-BONNERS FERRY NO 1 115KV LINE |  | LOAD, FLAT
25-03132 | 17269033 | 06/23/2025 07:00 | 06/23/2025 14:00 | TARGHEE: PCB B-1422 | TARGHEE-DRUMMOND NO 1 115KV LINE | SEIL, GEN
25-01069 | 17209058 | 06/23/2025 07:00 | 06/24/2025 16:00 | ASHE: PCB A-924 |  | COI, NOH, PDCI
25-06146 |  | 06/23/2025 07:00 | 07/02/2025 16:00 | -CPUD- GARDENERS CORNER: SUBSTATION
25-02307 | 17209101 | 06/23/2025 08:00 | 06/26/2025 16:30 | HOOD RIVER-THE DALLES NO 1 115KV LINE |  | WOCS, FCRPS, GEN
25-00464 | 16842576 | 06/23/2025 08:00 | 06/28/2025 17:00 | ST HELENS-DEER ISLAND SECTION OF ST HELENS-ALLSTON NO 1 115KV LINE
25-03595 |  | 06/23/2025 08:00 | 06/23/2025 15:00 | PEARL: A-1165 TERMINAL OF THE PEARL TAP TO PGE MCLOUGHLIN SHERWOOD NO.1 230KV LINE
25-01254 | 17087091 | 06/23/2025 08:00 | 06/24/2025 16:00 | GLASGOW-SUMNER SECTION OF REEDSPORT-FAIRVIEW NO 1 115KV LINE |  | LOAD, SCORC
25-01379 | 17175351 | 06/23/2025 08:00 | 06/23/2025 12:00 | SCHULTZ: PCB 5132 |  | WOCN, NOEL
25-01518 | 17080315 | 06/23/2025 08:00 | 06/23/2025 16:00 | LOWER GRANITE: PCB 4775 |  | MT-NW, WOH, WOLM, GEN
25-05407 |  | 06/23/2025 08:00 | 06/27/2025 18:00 | SCL - NORTH: 120KV BUS 2 INCLUDING BANK 55 AND PCB'S 120-75 & -76
25-00661 | 16841107 | 06/23/2025 08:00 | 06/24/2025 15:00 | LOWER MONUMENTAL: PCB 4676 |  | WOLM
25-00913 | 17087584 | 06/23/2025 08:00 | 06/26/2025 15:00 | TAFT: PCB 4119, BFR |  | MT-NW, WOH
25-06210 | 17542325 | 06/23/2025 09:00 | 06/27/2025 15:00 | REDMOND: A-252 TERMINAL OF REDMOND-PACW PILOT BUTTE NO 1 230KV LINE | REDMOND-PILOT BUTTE PACW NO 1 230KV LINE | LOAD, COR, NWACI
25-01380 | 17175403 | 06/23/2025 12:30 | 06/23/2025 16:30 | SCHULTZ: PCB 5129 |  | WOCN, NOEL
25-01186 | 17074773 | 06/24/2025 06:00 | 06/24/2025 11:00 | BELL: PCB A-370 |  | MT-NW, WOH
25-06368 | 17570340 | 06/24/2025 07:00 | 06/24/2025 16:00 | COLUMBIA FALLS-KALISPELL NO 1 115KV LINE |  | GEN, LOAD, MT-NW, FLAT
25-00890 | 16842232 | 06/24/2025 07:30 | 06/24/2025 07:45 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-01256 | 16978112 | 06/24/2025 08:00 | 06/24/2025 16:00 | CENTRAL FERRY: PCB 5391 | CENTRAL FERRY: PCB 5391 | GEN, WOLM
25-01377 | 17299573 | 06/24/2025 08:00 | 06/26/2025 16:00 | SCHULTZ: ECHO LAKE 1 500KV LINE SERIES CAP GROUP 1 INCLUDING PCB 5142 | SCHULTZ: PCB 5142, SCHULTZ: ECHO LAKE 1 500KV LINE SERIES CAP GROUP 1 | WOCN, NOEL, IROL, SOC
25-00044 | 13333778 | 06/24/2025 08:00 | 06/24/2025 15:00 | KEELER: 230/115KV TRANSFORMER 1 | KEELER: 230/115KV TRANSFORMER 1, KEELER: PCB A-860, KEELER: PCB B-1066, KEELER: 13.8KV PCB 1W STATION SERVICE 1, KEELER: 13.8KV SVC SS #1 | SOA, LOAD
25-00891 | 16842244 | 06/24/2025 11:15 | 06/24/2025 11:30 | GRAND COULEE: PCB 2492, GRAND COULEE: PCB 2496 |  | GEN, NOH, WOCN
25-06088 | 17529260 | 06/24/2025 12:00 | 06/24/2025 15:00 | BELL: A-571 AND MOD A-577 M/B DISCS | BELL: A-571 MBD, BELL: MOD A-577 MAIN BUS
25-06600 | 17604158 | 06/25/2025 07:00 | 06/25/2025 15:00 | BELL: 230KV MAIN BUS SECTION 1 | DAY MT SPOKANE-BELL SECTION OF SACHEEN-BELL NO 1 230KV LINE, BELL: 230KV CAP GROUP 10 SECTION 1, BELL: 230KV CAP GROUP 10 SECTION 2, BELL: PCB A-366, BELL: PCB A-368, BELL: PCB A-374, BELL: PCB A-370, BELL: PCB A-375, BELL: LBD A-925, BELL: LBD A-926, BELL: 230KV AUX BUS SECTION 1, BELL: 230KV AUX BUS SECTION 2 | MT-NW, WOH, SOB
25-04074 | 17574416 | 06/25/2025 08:00 | 06/25/2025 15:00 | REDMOND: PCB B-1558
25-00663 | 17318986 | 06/25/2025 08:00 | 06/25/2025 15:00 | LOWER MONUMENTAL: PCB 4290 |  | WOLM
25-01263 | 17133514 | 06/25/2025 08:00 | 06/26/2025 16:00 | MORRISON-BANDON SECTION OF FAIRVIEW-BANDON NO 1 115KV LINE |  | SWORE
25-01245 | 17074776 | 06/25/2025 08:00 | 06/25/2025 15:00 | TUCANNON RIVER: PCB B-2021
25-00483 | 16463596 | 06/25/2025 22:00 | 06/25/2025 22:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-03360 | 17319826 | 06/26/2025 07:30 | 06/26/2025 15:00 | LOWER MONUMENTAL: PCB 4624 |  | WOLM
25-01339 | 17009965 | 06/26/2025 08:00 | 06/26/2025 15:00 | SLATT-JOHN DAY NO 1 500KV LINE INCLUDING SLATT PCB'S 5018 AND 5021 AND JOHN DAY PCB'S 4128 AND 4131 | SLATT: PCB 5018, SLATT: PCB 5021, JOHN DAY: PCB 4131, JOHN DAY: PCB 4128 | WOJD, NWACI, WOS, PDCI
25-07279 | 17676830 | 06/26/2025 12:00 | 06/26/2025 13:00 | BIG EDDY: PCB 4870 |  | GEN, PDCI, WOJD, BGEDY, SOA, NOPE
25-06096 | 17530014 | 06/26/2025 16:00 | 11/14/2025 08:00 | ROCKY REACH: 345/230KV TRANSFORMER 1 INCLUDING MODS A-3017, A-3016 AND THE A-1001 DISCONNECTS | ROCKY REACH: 345/230KV TRANSFORMER 1 | GEN, IROL, NOEL, NOH, SOC, WOCN
25-02696 | 17269356 | 06/26/2025 22:00 | 06/27/2025 06:00 | PORT ANGELES-SILVERADO SECTION OF PORT ANGELES-SAPPHO NO 1 115KV LINE INCLUDING PORT ANGELES: PCB B-647 AND 115KV A/B | PORT ANGELES-SAPPHO NO 1 115KV LINE, SILVERADO: CLALLAM CO PUD 115KV FEEDER 1, SAPPHO: CLALLAM CO PUD 69KV FEEDER 1, SAPPHO: CLALLAM CO PUD 69KV FEEDER 2, SAPPHO: 115/69KV TRANSFORMER 1
25-02085 |  | 06/26/2025 22:00 | 06/27/2025 06:00 | SILVERADO-SAPPHO SECTION OF PORT ANGELES-SAPPHO NO 1 115KV LINE
25-06511 | 17576986 | 06/27/2025 08:00 | 06/30/2025 15:00 | ALVEY: PCB 5087, MODS 5086, 5088, 5089 CONTROL AND ALARM CIRCUITS | ALVEY: 500KV SOUTH BUS, ALVEY: PCB 5087 | NWACI, EWEB
25-00484 | 16463602 | 06/27/2025 22:30 | 06/27/2025 23:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN
25-06557 |  | 06/28/2025 06:00 | 06/28/2025 17:00 | -IPC- HELLS CANYON-HURRICANE 230KV LINE | HELLS CANYON (IPC)-HURRICANE 230KV LINE | ID-NW, WOH
25-06251 |  | 06/29/2025 06:00 | 06/29/2025 16:00 | -IPCO- BROWNLEE-HELLS CANYON 230KV LINE
25-02007 | 17115714 | 06/29/2025 22:00 | 06/29/2025 22:15 | GRAND COULEE: PCB 2392, GRAND COULEE: PCB 2396 |  | GEN, NOH, WOCN
25-00310 | 17116530 | 06/30/2025 06:30 | 07/02/2025 17:00 | OLYMPIA: A-206 TERMINAL OF OLYMPIA-GRAND COULEE NO 1 230KV LINE | OLYMPIA: PCB A-206, GRAND COULEE: PCB 6886, OLYMPIA-GRAND COULEE NO 1 230KV LINE | NOEL, RP, SOC, WOCN, NOH, IROL
25-06899 | 17618688 | 06/30/2025 08:00 | 06/30/2025 15:30 | -LVE- HOOPER SPRINGS: PCB HV-741 | HOOPER SPRINGS: PCB HV-741
25-00956 | 17005005 | 06/30/2025 08:00 | 07/01/2025 16:00 | JOHN DAY: PCB 4170 (108E) BFR and PCB DIFF | JOHN DAY: PCB 4170 | NWACI, WOCS, WOJD, PDCI
25-01083 | 17292520 | 06/30/2025 08:00 | 07/25/2025 15:00 | SWAN VALLEY-TARGHEE TAP SECTION OF SWAN VALLEY-TETON NO 1 115KV LINE INCLUDING SWAN VALLEY PCB B-1676 | SWAN VALLEY-TARGHEE TAP SECTION OF SWAN VALLEY-TETON NO 1 115KV LINE, SWAN VALLEY: PCB B-1676 | SEIL, GEN, LOAD
25-01382 | 17175502 | 06/30/2025 08:00 | 06/30/2025 15:00 | SCHULTZ: PCB 5154 |  | WOCN, NOEL
25-00849 | 17326275 | 06/30/2025 08:00 | 08/08/2025 15:00 | MARTIN CREEK: 230/115KV TRANSFORMER 1 INCLUDING PCB A-443 | MARTIN CREEK: 230/115KV TRANSFORMER 1, MARTIN CREEK: PCB A-443, MARTIN CREEK TAP TO ALVEY-FAIRVIEW NO 1 230KV LINE | SCORC, LOAD
25-05945 | 17503965 | 06/30/2025 08:00 | 07/22/2025 15:00 | CARLTON-TILLAMOOK NO 1 230KV LINE INCLUDING PCB A-315 AND 230KV AUX BUS
25-04079 | 17333427 | 06/30/2025 08:30 | 06/30/2025 16:00 | LAPINE: PCB A-1494 INCLUDING 230/115KV TRANSFORMER 1 | LAPINE: 230/115KV TRANSFORMER 1, LAPINE: PCB A-1494, LAPINE: 230/115KV TRANSFORMER 2 | COR, GRZN, NWACI