## Request List
Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected
20-00283 | 11219795 | 12/31/2020 15:00 | 12/15/2031 23:59 | PAUL: 4569 TERMINAL OF PAUL-CENTRALIA THERMAL PH NO 1 500KV LINE | PAUL: 4569 TERMINAL OF PAUL-CENTRALIA THERMAL PH NO 1 500KV LINE | GEN, PA
23-04125 | 18099097 | 01/28/2023 17:00 | 06/30/2026 15:00 | ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV | ROCKY REACH: 345/230KV TRANSFORMER 1, MAPLE VALLEY: 345/230KV TRANSFORMER 1 | WOCN, SOC/NOEL, CI, GEN, IROL, NOEL, NOH, SOC
23-16749 |  | 10/26/2023 07:00 | 06/01/2028 16:00 | VALHALLA: B-280 TERMINAL OF THE VALHALLA-CHELAN CO PUD 115KV FEEDER T1 | VALHALLA: CHELAN CO PUD 115KV FEEDER T1 | CI
25-10823 | 18178294 | 06/23/2025 08:00 | 03/31/2026 16:00 | ECHO LAKE: 500KV CAP GROUP 2 INCLUDING PCB 5127 | ECHO LAKE: PCB 5127, ECHO LAKE: 500KV CAP GROUP 2 | BCHT, NOEL, SOC, WOCN, NI, BCHW, IROL
25-10824 | 18178297 | 06/23/2025 08:00 | 03/31/2026 16:00 | ECHO LAKE: 500KV CAP GROUP 1 INCLUDING PCB 5125 | ECHO LAKE: PCB 5125, ECHO LAKE: 500KV CAP GROUP 1 | BCHT, BCHW, NOEL, SOC, WOCN, NI, IROL
25-12245 |  | 09/30/2025 08:00 | 04/10/2026 16:00 | WAPA- TRACY: 500KV SHUNT CAP PT8A & PT8B |  | COI
25-14949 | 18806562 | 10/01/2025 06:30 | 01/01/2026 19:00 | GRAND COULEE: PCB 9092 |  | GEN, NOH, WOCN
25-14320 | 18697895 | 11/01/2025 00:01 | 03/31/2026 23:59 | BREWSTER-FOSTER CREEK 115KV LINE |  | OKLA, NOH
25-14326 | 18698092 | 11/01/2025 00:01 | 03/31/2026 23:59 | BREWSTER-OKANOGAN 115KV LINE |  | OKLA, NOH
25-10659 | 18263663 | 11/03/2025 08:00 | 01/16/2026 15:00 | HORSE HEAVEN: 230KV MAIN BUS INCLUDING 115KV MAIN & AUX BUS, 230/115KV TRANSFORMER 1, HORSE HEAVEN-BC1022 SECTION OF HORSE HEAVEN-BENTON PUD NO 1 115KV LINE, HORSE HEAVEN: PCB A-287, PCB B-334 AND 13.8KV STATION SERVICE | HORSE HEAVEN: PCB A-287, HORSE HEAVEN: PCB B-334, HORSE HEAVEN: 230KV MAIN BUS, HORSE HEAVEN: 115KV MAIN BUS, HORSE HEAVEN: 115KV AUX BUS, PRIMARY STATION SERVICE, HORSE HEAVEN: 230/115KV TRANSFORMER 1, HORSE HEAVEN-BPUD NO 1 115KV LINE | WOM, LOAD, SOA, NOPE
25-16042 |  | 11/12/2025 08:00 | 01/16/2026 18:00 | LADWP - VICTORVILLE SS: 500kV BUS 1/BANK K/SS3 |  | PDCI
25-08871 |  | 11/15/2025 08:00 | 02/01/2026 16:00 | -IPC- LOLO-OXBOW 230KV LINE |  | NWACI, SEIL
25-10540 | 18142035 | 11/16/2025 12:00 | 02/02/2026 09:00 | OSTRANDER: PCB 4432, INCLUDING MOD'S 4433 & 4435 |  | WOCS
25-15260 | 18860077 | 12/01/2025 07:00 | 01/28/2026 16:00 | KITSAP: B-954 TERMINAL OF THE KITSAP-BANGOR NO 1 115KV LINE | KITSAP: PCB B-954 | RP
25-15259 | 18860081 | 12/01/2025 07:00 | 01/28/2026 16:00 | -USN- BANGOR: 115KV BUS 1 & 3 INCLUDING THE KITSAP-BANGOR NO 1 115KV LINE AND THE BANGOR-STATION 2 NO 1 115KV Line | KITSAP-BANGOR NO 1 115KV LINE, BANGOR: PCB 11 | RP
25-15102 | 18826782 | 12/01/2025 08:00 | 03/31/2026 15:00 | PEARL TAP TO MCLOUGHLIN-SHERWOOD NO 1 230KV LINE |  | SOA, WOCS, NOPE
25-15095 | 18889922 | 12/12/2025 17:00 | 01/09/2026 17:00 | COLUMBIA: PCB B-410 INCLUDING THE COLUMBIA-VALHALLA #2 115KV LINE | COLUMBIA: PCB B-410, COLUMBIA-VALHALLA NO 2 115KV LINE | CI, NOH
26-00542 | 18638569 | 01/05/2026 07:00 | 01/23/2026 17:00 | FRANKLIN: B-1528 TERMINAL OF ICE HARBOR-FRANKLIN NO 1 115KV LINE | ICE HARBOR-FRANKLIN NO 1 115KV LINE | GEN, TCLA
26-00145 | 18011834 | 01/05/2026 07:00 | 02/16/2026 17:00 | PGE - MCLOUGHLIN-PEARL-SHSERWOOD 1 230KV LINE |  | NOPE, SOA, WOCS
26-00142 | 18012196 | 01/05/2026 07:00 | 02/16/2026 17:00 | PEARL: A-1165 TERMINAL OF PEARL TAP TO PGE MCLOUGHIN-SHERWOOD NO 1 230KV LINE | PEARL TAP TO MCLOUGHLIN-SHERWOOD NO 1 230KV LINE, PEARL: PCB A-1165 | SOA, WOCS, NOPE
26-00473 |  | 01/05/2026 07:00 | 01/08/2026 16:00 | ALLSTON: PCB A-1361 RELAYS | ALLSTON: PCB A-1361, ALLSTON: PCB A-1355 | SOA, NOPE
26-00470 | 18579864 | 01/05/2026 08:00 | 01/15/2026 15:00 | ASHE: PCB 4898 BFR | ASHE: PCB 4898 | NWACI, FCRPS, NOH
26-00341 | 18487658 | 01/05/2026 08:00 | 01/05/2026 15:00 | MARION: PCB 4355 |  | NWACI, NOPE, WOCS
26-00297 | 18461431 | 01/05/2026 08:00 | 01/07/2026 15:00 | CARLTON: 115KV MAIN BUS INCLUDING NEW 115KV MAIN BUS EXTENSION | CARLTON-MCMINNVILLE NO 1 115KV LINE, FOREST GROVE-MCMINNVILLE NO 1 115KV LINE, CARLTON: 230/115KV TRANSFORMER 1, CARLTON: 115KV MAIN BUS | SOA, LOAD, NOPE
26-00084 | 18150927 | 01/05/2026 08:00 | 02/27/2026 15:00 | MIST-DRISCOLL SECTION OF ALLSTON-DRISCOLL NO 2 115KV LINE INCLUDING DRISCOLL PCB B-2067 & PCB B-2064 | MIST-DRISCOLL SECTION OF ALLSTON-DRISCOLL NO 2 115KV LINE | LOAD, SOA, NOPE
25-06101 | 17530243 | 01/05/2026 08:00 | 01/09/2026 16:00 | ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE INCLUDING ROCKY REACH: 345/230KV TRANSFORMER 1 | MAPLE VALLEY: PCB A-1118, ROCKY REACH: 345/230KV TRANSFORMER 1, ROCKY REACH-MAPLE VALLEY NO 1 345KV LINE, ROCKY REACH: PCB 7-740 | NOEL, SOC, WOCN, GEN, IROL, NOH, CI
26-00097 | 17771597 | 01/05/2026 09:00 | 02/19/2026 09:00 | KEELER: A-870 TERMINAL OF KEELER-PGE HORIZON NO 1 230KV LINE | KEELER-PGE HORIZON NO 1 230KV LINE, KEELER: PCB A-870 | SOA, NOPE
26-00196 | 17771467 | 01/05/2026 09:00 | 02/19/2026 09:00 | PGE - KEELER-HORIZON 1 230KV LINE |  | SOA, NOPE
26-00799 | 18734400 | 01/07/2026 07:00 | 01/13/2026 08:00 | PG&E - ROUND MOUNTAIN-TABLE MOUNTAIN 2 500KV LINE |  | COI
25-14971 | 18862290 | 01/09/2026 07:00 | 01/09/2026 12:00 | COLUMBIA: 115KV NORTH MAIN BUS | COLUMBIA-VALHALLA NO 2 115KV LINE, COLUMBIA: 230/115KV TRANSFORMER 2 | CI, NOH, LOAD, WOCN
25-13706 | 18646226 | 01/09/2026 17:00 | 01/30/2026 17:00 | COLUMBIA: PCB B-404 INCLUDING THE B-1188 M/B SECTIONALIZING DISCONNECT AND THE COLUMBIA-VALHALLA #1 115KV LINE | COLUMBIA: PCB B-404, COLUMBIA: B-1188 MAIN BUS SECTIONALIZING DISC, COLUMBIA-VALHALLA NO 1 115KV LINE | CI, NOH
25-13669 | 18609775 | 01/12/2026 07:30 | 01/13/2026 16:30 | ALVEY: PCB A-235, A-237 & A-239 DC CONTROL CIRCUITS | ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 1, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 2, ALVEY: 230KV REACTIVE GROUP 2 CAP SECTION 3, ALVEY: PCB A-235, ALVEY: PCB A-237, ALVEY: PCB A-239, ALVEY: PCB A-476 | EWEB, NWACI
26-00236 | 18543286 | 01/12/2026 09:00 | 01/15/2026 15:00 | DWORSHAK: 500KV REACTOR NO 2 RELAYS | DWORSHAK: PCB 4650, DWORSHAK: 500KV REACTOR 2 | MT-NW, GEN, WOH
26-00219 | 18270887 | 01/13/2026 10:00 | 01/13/2026 10:15 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 |  | GEN, NOH, WOCN
26-00220 | 18270893 | 01/13/2026 14:15 | 01/13/2026 14:30 | GRAND COULEE: PCB 2092, GRAND COULEE: PCB 2096 |  | GEN, NOH, WOCN
26-00638 | 18134687 | 01/16/2026 07:00 | 02/21/2026 08:00 | PG&E - ROUND MOUNTAIN-TABLE MOUNTAIN 2 500KV LINE |  | COI
26-00294 | 18713031 | 01/19/2026 08:00 | 05/31/2026 15:00 | SNYDER-STEVENS DRIVE SECTION OF WHITE BLUFFS-STEVENS DRIVE NO 2 115KV LINE, INCLUDING STEVENS DRIVE B-937, B-1024, B-1026, B-1028, B-1027, B-1025, B-1563, B-2196 (NEW), B-2197(NEW) DISCONNECTS, STEVENS DRIVE BANK 3 AND THE FIRST STREET-STEVENS DRIVE SECTION OF THE WHITE BLUFFS-RICHLAND NO 1 115KV LINE. | SNYDER-STEVENS DRIVE SECTION OF WHITE BLUFFS-STEVENS DRIVE NO 2 115KV LINE, FIRST STREET-STEVENS DRIVE SECTION OF WHITE BLUFFS-RICHLAND NO 1 115KV LINE, STEVENS DRIVE: CITY OF RICHLAND 115KV FEEDER 1, STEVENS DRIVE: CITY OF RICHLAND 115KV FEEDER 3 | LOAD, TCLA
26-00906 | 18962396 | 01/20/2026 08:00 | 01/22/2026 15:00 | ALCOA: PCB B-1893 RELAYS | ALCOA: PCB B-1893 | SOA, GEN, LOAD, NOPE
26-00221 | 18270896 | 01/20/2026 10:00 | 01/20/2026 10:15 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
26-00222 | 18270946 | 01/20/2026 14:15 | 01/20/2026 14:30 | GRAND COULEE: PCB 2192, GRAND COULEE: PCB 2196 |  | GEN, NOH, WOCN
25-09283 | 17929852 | 01/21/2026 08:00 | 01/21/2026 15:00 | ASHE-WHITE BLUFFS NO 1 230KV LINE | WHITE BLUFFS: 230/115/13.8KV TRANSFORMER 1 | GEN, TCLA, LOAD, FCRPS
25-09216 |  | 01/21/2026 08:00 | 01/21/2026 15:00 | WHITE BLUFFS: 230/115/13.8KV TRANSFORMER 1 |  | GEN, TCLA, LOAD
26-00182 | 18112362 | 01/22/2026 07:00 | 01/22/2026 11:00 | RAVER: PCB 4220 |  | NOEL, RP, SOC, WOCN
26-00183 |  | 01/22/2026 11:00 | 01/22/2026 15:00 | RAVER: PCB 4293 |  | NOEL, RP, SOC, WOCN
26-00172 |  | 01/26/2026 05:00 | 02/01/2026 18:00 | CGS: DG -3 OUTAGE -STAY NORMAL- | MIDWAY-ASHE NO 1 230KV LINE, BENTON-WHITE BLUFFS NO 2 115KV LINE, ASHE-WHITE BLUFFS NO 1 230KV LINE, COLUMBIA GENERATING STATION-ASHE NO 2 230KV LINE | GEN, FCRPS, LOAD, SIG
26-00230 | 18360120 | 01/26/2026 07:00 | 01/29/2026 16:00 | GARRISON: 500KV REACTOR NO 4 RELAYS | GARRISON: PCB 4457, GARRISON: 500KV REACTOR 4 | MT-NW
26-01040 | 18969182 | 01/26/2026 07:00 | 02/05/2026 17:00 | JOHN DAY: 4138/4139 TERMINAL OF JOHN DAY PH-JOHN DAY NO 1 500KV LINE | JOHN DAY PH-JOHN DAY NO 1 500KV LINE | GEN, NWACI, FCRPS, SIG, WOJD
26-00482 | 18594501 | 01/26/2026 08:00 | 02/12/2026 15:30 | BIG EDDY: PCB 4202 BFR | BIG EDDY: PCB 4202 | PDCI, WOCS, WOJD, BGEDY
26-00471 | 18579912 | 01/26/2026 08:00 | 02/05/2026 15:00 | ASHE: PCB 4937 BFR | ASHE: PCB 4937 | NOH, NWACI, FCRPS
26-00907 | 18962410 | 01/26/2026 08:00 | 01/27/2026 15:00 | ALCOA: PCB B-224 RELAYS | ALCOA: PCB B-224 | SOA, GEN, LOAD, NOPE
26-00279 | 18409646 | 01/26/2026 10:00 | 01/26/2026 15:00 | MORROW FLAT: PCB B-2231 BFR | MORROW FLAT: PCB B-2231 | WOM
26-00303 | 18442056 | 01/27/2026 10:00 | 01/27/2026 10:15 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
26-00281 |  | 01/27/2026 12:00 | 01/27/2026 16:00 | MORROW FLAT: PCB B-2244 BFR | MORROW FLAT: PCB B-2244 | WOM
26-00304 | 18442066 | 01/27/2026 14:15 | 01/27/2026 14:30 | GRAND COULEE: PCB 2292, GRAND COULEE: PCB 2296 |  | GEN, NOH, WOCN
26-00908 | 18962417 | 01/28/2026 08:00 | 01/29/2026 15:00 | ALCOA: PCB B-234 RELAYS | ALCOA: PCB B-234 | GEN, LOAD, SOA, NOPE
26-00938 | 18930637 | 01/29/2026 08:00 | 01/29/2026 15:00 | MONROE-NOVELTY HILL NO 1 230KV LINE INCLUDING MONROE: PCBS A-1422 AND A-1426 AND 230KV AUX BUS | MONROE-NOVELTY HILL NO 1 230KV LINE, MONROE: PCB A-1422, MONROE: PCB A-1426, MONROE: 230KV AUX BUS | NOEL, SOC, BCHT, BCHW
26-00168 | 18101334 | 01/29/2026 08:00 | 01/29/2026 12:00 | MCNARY: PCB 5199 |  | WOM, WOS, NWACI
26-00169 | 18101338 | 01/29/2026 12:00 | 01/29/2026 15:00 | MCNARY: PCB 5198 |  | WOM, NWACI
26-00811 |  | 01/30/2026 07:00 | 01/30/2026 12:00 | COLUMBIA: 115KV NORTH MAIN BUS | COLUMBIA-ANCIENT LAKE NO 1 115KV LINE, COLUMBIA: 230/115KV TRANSFORMER 2, COLUMBIA-VALHALLA NO 1 115KV LINE, COLUMBIA: PCB B-314, COLUMBIA: PCB B-412, COLUMBIA: PCB B-410, COLUMBIA: PCB B-404 | CI, NOH, LOAD, WOCN