## Request List
Request# | CAISO# | Start | End | Main Element Impacted | Elements Involved | Path Affected | Status | Work to be Performed | Work Type
21-01711 | 15666227 | 02/03/2021 09:00 | 02/28/2030 17:00 | -USBR- GRAND COULEE 287/230KV TRANSFORMER KX-17-A (OLYMPIA-GRAND COULEE NO 1 287KV LINE OPERATING AT 230KV) | OLYMPIA: 287/230KV TRANSFORMER 3, GRAND COULEE: 287/230KV TRANSFORMER 1 | NOEL, RP, SOC, WOCN, IROL, NOH, OKLA | ACTIVE | #1421102 -USBR WORK-4 YEAR MAINTENANCE ON TRANSFORMER KX-17-A. LINE RETURNED TO SERVICE AT 230KV | Info
23-04125 | 13016840 | 01/28/2023 17:00 | 09/30/2026 23:59 | ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV | ROCKY REACH: 345/230KV TRANSFORMER 1, ROCKY REACH-MAPLE VALLEY NO 1 345kV LINE OPERATING AT 230KV, MAPLE VALLEY: 345/230KV TRANSFORMER 1 | WOCN, SOC/NOEL, CI, GEN, IROL, NOEL, NOH, SOC | ACTIVE | ROCKY REACH-MAPLE VALLEY 1 345KV LINE OPERATING AT 230KV DUE TO MAPLE VALLEY 345/230KV BANK 1 GASSING | Info
26-00036 |  | 01/12/2026 22:00 | 01/12/2026 22:30 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN | SUBMITTED | Bay outage to support removing G-19 from service for maintenance. | Info
26-00032 |  | 01/15/2026 07:00 | 01/15/2026 17:00 | DWORSHAK PH: PCB XJ-7 |  |  | SUBMITTED | XJ-7 NEEDS TO BE OPEN DURING CAPABILITY CURVE TESTING OF UNIT 1 | Info
26-00037 |  | 01/15/2026 22:30 | 01/15/2026 23:00 | GRAND COULEE: PCB 1992, GRAND COULEE: PCB 1996 |  | GEN, NOH, WOCN | SUBMITTED | Bay outage to support returning G-19 to service after maintenance. | Info